BUNDIBUGYO DISTRICT LOCAL GOVERNMENT

FIVE YEAR DISTRICT DEVELOPMENT PLAN

2025/2026-2029/2030

Vision

“A transformed community with improved Household incomes and livelihood by 2040”.

Mission Statement

To provide quality services to the community through an effective service delivery system with an emphasis on national and local priorities that promote a sustainable socio-economic development of the district.

Table of Contents

LIST OF ABBREVIATIONS AND ACRONYMS	vi

1.1 Background and Development Context	21

HUMUN CAPITAL DEVELOPMENT	Error! Bookmark not defined.

1.4 Outstanding Development issues/ Challenges	22

1.5 Key Lessons Leant from implementation of the previous plan	24

1.5 Formulation Process and Approach	24

The District Development Plan Formulation Process	24

Back ground to Planning / Steps	25

1.6 Structure of Plan	26

2.1	Geographical Location, Land Area and Population	29

Table 1     Population of selected age groups	31

Table 2:  Population by sub county/Town Council	31

Figure 1: Population pyramid	33

2.1.5 Settlement Patterns	34

2.1.6 Ethnic Groups	34

2.1.7 Cultural Diversity	34

2.1.8 Languages	34

2.1.9 Population Issues	34

2.1.10 Life Standards Indicators and Statistics	35

Average Life Expectancy:	35

2.1.12 Political and Administrative Issues	35

2.2 Socio-Economic Situation	35

2.2.1 Poverty Situation in Bundibugyo district.	35

2.2.2 Unemployment Situation in Bundibugyo District.	36

2.3.1 Agro- Industrialization	36

2.3.2 TO

SM	37

2.3.3 SCIENCE AND TECHNOLOGY	37

2.3	Economic Infrastructure and services	38

Urbanization	38

FINANCIAL SERVICES	39

Table 3: List of Primary schools	40

Table 4: Health infrastructure and ownership	46

Table 5	47

Health Manpower	47

iii.	Poor road network to the tourism site especially in the mountains	49

vi.	Farmer exploitation by the middle men.	49

vii.	Limited entrepreneurial skills and business knowledge	49

CHAPTER 3: LGDP STRATEGIC DIRECTION	52

Vision	52

3.2	LGDP Strategic Direction	52

3.3	Alignment of LGDP direction with the NDPIV Programmes	53

3.4	Key LG Development Plan Results and Targets	56

3.4	LGDP Development Results and Targets	59

3.4.1	Programme 1: Agro-industrialization	59

Table 7: Agro- Industrialization Development Results and Targets	59

3.5.5 Natural Resources, Environment, Climate Change, Land, and Water Management	83

.4.1 PUBLIC SECTOR TRANSFORMATION	112

3.5.10 Development Plan Implementation Programme.	128

Table: 17 Financing Framework	142

4.3	Resource Mobilization Strategy	173

CHAPTER FIVE: INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTING THE PLAN	175

5.1 Implementation arrangements	175

5.2.1 Role of Key Stakeholders	177

5.2 Coordination and Partnership Framework	179

5.3.2 Strong Political will and commitment to transparency, accountability and results	180

6.2 Communication Plan	183

6.3.1	The Importance of an effective Communication and feedback strategy in the DDP framework	185

6.3.1: Roles/Responsibilities of Stakeholders of LG in Communication and Provision of Feedback to Stakeholders	188

8.1 Monitoring and Evaluation (M&E) Frameworks	194

8.2 M&E Roles and Responsibilities of Key Actors	195

8.3 Major Monitoring and Evaluation Events	195

ANNEXES	198

Annex 1: Project Profiles	198

Annex 3: Results and Reporting Framework	218

# LIST OF ABBREVIATIONS AND ACRONYMS

| ACAO | Assistant Chief Administrative officer |
| --- | --- |
| ACCRA | Africa Climate Change Resilience Alliance |
| AIDS | Acquired Immune-Deficiency Syndrome |
| BBC | Belgian Bilateral Co-operation |
| BDR | Birth and Death Registration |
| BFP | Budget Frame work Paper |
| BIDP | Bundibugyo Integrated Development Programme |
| BOQs | Bills of Quantities |
| CAO | Chief Administrative Officer |
| CBG | Capacity Building Grant |
| CBMIS | Community Based Management Information System |
| CBMP | Cross Border Mobile Population |
| CBO | Community Based Organization |
| CBS | Community Based Services |
| CC | Contracts Committee |
| CDA | Community Development Assistant |
| CDD | Community Driven Development |
| CDO | Community Development Officer |
| CF | Community Facilitator |
| CFO | Chief Finance Officer |
| CHW | Community Health Worker |
| CLWH | Children living with HIV/AIDS |
| CSO | Civil Society Organisation |
| CWD | Children With Disabilities |
| DAC | District Aids Committee |
| DAO | District Agriculture Officer |
| DAT | District Aids Task force |
| DCDO | District Community Development officer |
| DDMC | District Disaster Management committee |
| DDP | District Development Plan |
| DE | District Engineer |
| DEAP | District Environment Action Plan |
| DEO | District Education Officer |
| DFO | District Fisheries Officer |
| DHI | District Health Inspector |
| DHO | District Health Officer |
| DIT | District Implementation Team |
| DPU | District Planning Unit |
| DSC | District Service Commission |
| DTPC | District Technical Planning Committee |
| DWO | District Water Officer |
| ECD | Early Child Hood Development centre |
| EG | Equalization Grant |
| EIA | Environmental Impact Assessment |
| EO | Environment Officer |
| FAL | Functional Adult Literacy |
| FDS | Fiscal Decentralization Strategy |
| FO | Forest Officer |
| FP | Family Planning |
| FY | Financial Year |
| GFS | Gravity Flow Scheme |
| GoU | Government of Uganda |
| HC | Health Centre |
| HI | Health Inspector |
| HIV | Human Immune-Deficiency Virus |
| HMIS | Health Management Information system |
| ICRC | International Committee for Red Cross |
| IDC | Internally Displaced Children |
| IDP | Internally Displaced People |
| IMT | Intermediate means of transport |
| IRAP | Integrated Rural Accessibility Planning |
| KAPB | Knowledge Attitude Practice And Behaviour |
| LC | Local Council |
| LGMSD | Local Government Management Service Delivery |
| LLG | Lower Local Government |
| LR | Local Revenue |
| M&O | Maintenance and Operation |
| MCH | Maternal and Child Health |
| MFI | Micro-finance Institution |
| MMR | Maternal Mortality Rate |
| MoFPED | Ministry of Finance, Planning and Economic Development |
| MoH | Ministry of Health |
| MoLG | Ministry of Local Government |
| MoPS | Ministry of Public Service |
| MSF | Medicine Sans Frontier |
| MTEF | Medium Term Expenditure Framework |
| NDP | National Development Plan |
| NEMA | National environment management Authority |
| NFA | National Forestry Authority |
| NGO | Non-Governmental Organisation |
| NPA | National Planning Authority |
| OVC | Other Vulnerable Children |
| PAF | Poverty Action Fund |
| PDC | Parish Development Committee |
| PEAP | Poverty Eradication Action Plan |
| PIC | Parish Investment committee |
| PLE | Primary Leaving Examination |
| PLWH | People living with HIV/AIDS |
| PMA | Programme For Modernization of Agriculture |
| PPAs | Priority Programme Areas |
| PPDA | Public Procurement and Disposal of Assets |
| PRA | Participatory Rural Appraisal |
| PWD | People with Disability |
| REF | Rural Electrification Fund |
| REFLECT | Regenerated Frierean Literacy Through Empowering Community Techniques |
| SACCO | Savings and Credit Cooperative Organization |
| SCDO | Senior Community Development Officer |
| SFG | School Facility Grant |
| SIC | Sub-county Investment committee |
| SIT | Sub-county Implementation Team |
| SMC | School Management Committee |
| SNV | Netherlands Development Organization |
| SRH | Sexual Reproductive Health |
| STD | Sexually Transmitted Disease |
| STPC | Sub-county Technical Planning committee |
| TBA | Traditional Birth |
| TDMS | Teacher Development management System |
| UAC | Uganda Aids Commission |
| UBoS | Uganda Bureau of Statistics |
| UCG | Un conditional Grant |
| ULGA | Uganda Local Government Association |
| UNEB | Uganda National Examination Board |
| UNICEF | United Nations Children’s Fund |
| UPE | Universal primary Education |
| USE | Universal Secondary Education |
| UWA | Uganda Wild Life Authority |
| VCT | Voluntary Counselling and Testing |
| VIP | Ventilated Improved Latrine |
| WFP | World Food Programme |
| WSC | Water Source Committee |

FOREWORD

The District Development Plan 2025/26- 2029/30 was prepared in accordance with the new guidelines. The Local Government development plan comes at a critical time in the physical, economic and social development of Bundibugyo. The plan provides a clear direction and focus for development over the next five years, while settling the scene for on-going growth in the context of the district and Nation as a whole.

There were significant changes in the national planning framework with the adoption of the Fourth National Development Plan and various legislative and policy documents at National Level. All the new provisions make for a much more complex, comprehensive, document that provides detailed guidance and direction for all those concerned with development of entire Bundibugyo community over the coming five years.

The plan addresses a range of development pressures and needs that are facing the Council during the period of the Plan and beyond. In doing so, It sets out the goal and objectives for the Council to follow, as well as the policies recommended to guide planning decisions and the activities of the Planning Authority over the period of the Plan.

Decentralized planning is a continuous, never ending process. It includes not just the document preparations and the many details that provide database and justification for projects but also the actual implementation of the projects in the plan.

Over the years, Bundibugyo district has made significant strides in enhancing its infrastructure, public services, and community engagement. However, there are still many challenges that lie ahead. This Fourth District Development Plan serves as a response to those challenges, providing a clear and structured framework to address the current needs while preparing for future opportunities. This therefore requires monitoring schemes for the projects during implementation to determine if they were designed properly. Final evaluation of the implementation of projects is needed to decide their effectiveness in achieving the local government objectives as well as the national objectives.

The commitment, however, poses a great challenge for the whole district because there is a big resource gap to finance all the desired interventions that would most likely result in maximum progress towards poverty eradication. I therefore, appeal to all development partners including the private sector in the district to complement the district efforts Some of the lessons learnt during executions of our respective roles in the previous financial years are that deliberate efforts need to be directed towards harnessing and involvement of communities in planning and implementing their own identified projects. This underscores the fact that improving the quality of life of the poor requires inputs from several sectors and the community itself.

I wish to extend my appreciation to all those who have contributed to the achievements recorded in the previous financial year and those who have supported us to compile this new five year DDP. The strong partnership, which has bonded us together, gives me confidence that we shall all; collectively and boldly face the even more challenging future. Let us all aspire for more success and achievements as we strive to improve the quality of life of our people

TIBAKUNIRWA ROBERT

DISTRICT CHAIRPERSON BUNDIBUGYO

ACKNOWLEDGEMENT

The development of the Bundibugyo Development Plan has been and ambitious yet essential undertaking, and it is with profound appreciation that we acknowledge the invaluable contributions from all individuals, groups, and institutions and Development partners- World Vision, UNHCR and the entire planning fraternity at all levels of governance, who played a key role in bringing this plan in place. This plan represents the collective desires and needs of our community, and its successful realization is the result of the hard work and collaboration of many stakeholders

Special thanks are extended to the Council, technical staff and the Executive committee for the cooperation and partner ships expressed during the process of developing the development plan.

I would also like to thank the District Councilors and Lower Council leaders for the assistance given to the field technical staff and contributions that was very instrumental in the planning process.

As we implement this plan, greater support is required from all stakeholders and the entire community of Bundibugyo in order to realize the development plan objectives.

Lastly, I thank the people of Bundibugyo for their support, cooperation, and commitment to the development of our District. It is through your active participation that we can create a brighter, more prosperous future for all

OUMA CHARLES

CHIEF ADMINISTRATIVE OFFICER BUNDIBUGYO

EXECUTIVE SUMMARY

The development of the District Development Plan IV (DDP IV) was informed by the Constitution of the Republic of Uganda Article 190, and in the LGA Cap 138, section 3, the NDPIV, Vision 20240 and the TenFold Growth Strategy, as well as the review of the previous plans. The District Development Plan for 2025/2026-2029/2030 provides a framework for guiding development directions over the next five years, in order to realize the district vision.

This District Plan (2025/26- 2029/30), has laid out 11 programmes that comprehensively cover the development issues faced by the district. The DDP 1V planning activities were adequately harmonized with sector and national development planning processes and frameworks providing enough time to allow sufficient time to mobilize and execute effective participation of the different stakeholders within the district as coordinated by the Planning Department. During the five-year period, the district intends to improve the quality of life of the people of Bundibugyo by enhancing, transparency, good governance, co- existence and security.

Plan Theme: “Sustainable Industrialization for Inclusive Growth, Employment and Wealth Creation”

Several milestones were achieved during the implementation of the previous plan (2020/2021-2024/2025): Facility Deliveries significantly improved from 52% of women giving birth at the facility to 90% following an incentive program, demonstrating successful uptake of specific initiatives; Maternal and Infant Mortality: The district's maternal mortality rate was reported at 1.4% (or 336 deaths per 100,000 live births, in line with the national average); Safe water coverage has improved from 65% to 70% while sanitation is at 67% from 59%. There has been a reduction in the water borne disease and the distance walked to the nearest water source has improved; There has been improvement in roads infrastructure through Manual routine maintenance of 50km of selected feeder roads. Mechanized routine maintenance carried out on 18km of feeder roads

Key Lessons Learnt

- Strong inter-departmental collaboration and political support are critical.

- Timely capacity building, retooling, supervision, and enforcement of rewards/sanctions drive performance.

- Regular monitoring, evaluation, and adaptive management are indispensable.

Challenges in the implementation of the previous plan are: natural disasters like flash floods that affected the constructed roads and water facilities; uncompleted projects due to the procurement method especially those supported under UGIFT; budget cuts and under staffing in some of the key service delivery departments like health, education and works

DISTRICT STRATEGIG DIRECTION

Bundibugyo District Development plan will focus on achieving the district

Vision which is “A transformed community with improved Household incomes and livelihood by 2040”.

Mission Statement: To provide quality services to the community through an effective service delivery system with an emphasis on national and local priorities that promote a sustainable socio-economic development of the district

District Goal: “To improve the quality of life of the people of Bundibugyo by enhancing, transparency, good governance, co- existence and security

Plan objectives

- Sustainably increase production, productivity and value addition in agriculture, minerals, tourism, ICT, and financial services.

- Enhance human capital development along the entire life cycle;

- Support the private sector to drive growth and create jobs;

- Build and maintain strategic sustainable infrastructure in transport; and

- Strengthen good governance, security, and the role of the district in development

Thirteen programmes have been adopted and these are: Agro- Industrialization, Tourism development,  Private sector Development, Public sector Transformation, Human Capital Development, Transport and infrastructure Development, Sustainable Urbanization, Development plan implementation, climate Change, and Natural Resources management, water and land management, Governance and security, Legislation, oversight and Representation, Regional Development.

The Priority Interventions for the period (2025/26–2029/30) are:

- Infrastructure & Urban Development – upgraded roads, both community access roads under DUCAR and Urban roads in all the 7 Town councils

- Economic Development & Industrialization –agro-processing of cocoa and coffee.

- Social Services – expanded health and education infrastructure and social protection.

- Environment & Climate Resilience – reduction on tree cutting and encroachment on Forest Reserves, urban greening, wetland restoration, and climate adaptation.

- Governance & Institutional Strengthening – capacity building, e-governance, citizen engagement, and data systems.

- Human Capital Development – construction and renovation of School facilities/infrastructure, skills training, vocational education, and youth empowerment, Improvement of the health sector by constructing health facility infrastructure and supply of equipment.

Financing plan for the Five Years

Over the five-year period FY2025/26–FY2029/30, Bundibugyo District  is projected to receive a total of UGX 257,389,207,290, primarily financed by the Central Government, which contributes the largest share at 248,117,180,000 (96%), followed by Development Partners/Donors contributing UGX 3,406,235,000 (1%), and Local Revenue generating UGX 5,865,792,290 (3%),.

Implementation, Coordination & Risk Management

The implementation of this Plan will be undertaken through the decentralized local government system, coordinated by the Chief Administrative officer (CAO). The CAO will ensure effective oversight, alignment with national priorities, and timely reporting on progress. Key implementation and coordination structures include the District Technical Planning Committee (DTPC), which provides technical guidance and reviews development priorities; the Political and Standing Committees of Council, which offer policy direction and oversight; and the District Planning Department, responsible for local-level planning and implementation. Additionally, Parish/ Ward Development Committees will support grassroots participation and ownership, while Programme Working Groups and Heads of Department will oversee sector-specific interventions and ensure effective execution of activit

Monitoring & Evaluation

A strengthened Monitoring and Evaluation (M&E) framework will systematically track the Districts outputs, outcomes, and long-term impacts through annual performance assessments, mid-term reviews, and an end-term evaluation. The framework will emphasize real-time data collection, regular reporting, and structured feedback mechanisms to support adaptive management and ensure that planning and resource allocation remain evidence-based throughout the implementation period.

CHAPTER ONE: INTRODUCTION

## 1.1 Background and Development Context

In the Constitution of the Republic of Uganda Article 190, and in the LGA Cap 243, section 3, The NPA Act further provides a mandate to support local capacity development for national planning and, in particular, to provide support and guidance to national and local bodies responsible for the decentralized planning process (NPA Act, section 7(2) (d)). It also mandates the Authority to design and implement programs to develop planning capacity in Local Governments (NPA Act, section 7 (2) (i)); and to monitor the performance of the decentralized system of development planning, The physical planning Act, 2010 (section 6(1)) calls for integration of physical planning with social and economic planning at the national and local levels., The 1995 National Population Policy (NPP) highlights the need to promote the integration of population factors in development planning at the national (ministries, institutions) and lower level (DPUs and DPTCs) (section 98(i), and 99 (a) of the policy) The National NGO policy 2010 (Section 5.3) requires the “CAO to provide the NGO community in the district with guidelines to enable the NGOs to participate effectively and in a coordinated manner in the district planning and program implementation”.  mandates District councils shall prepare comprehensive and integrated development plans incorporating the plans of lower level local governments for submission to the National Planning Authority.

The District Development Plan for 2025/2026-2029/2030 provides a framework for guiding development directions over the next five years, in order to realize the district vision. It is a more comprehensive plan, which will go beyond economic recovery and poverty eradication to economic transformation and wealth creation. This is the very fourth edition of the Five-Year District Development Plan; and it has been formulated in line with the National Development Plan IV goal geared towards Achieving higher household incomes and employment for sustainable socio-economic transformation” and this goal is to be achieved under the theme “Sustainable Industrialization for Inclusive Growth, Employment, and Wealth Creation”. While the district goal is “To Transform the community by improving Household Incomes and Livelihoods by 2040” with emphasis of “Partnering with the community with an aim of delivering excellent services and plans for the future while preserving, protecting, and enhancing the quality of life

1.2 Key achievements from the previous Plan

Over the past five planning period, the district has registered tremendous improvement in the different programs

Bundibugyo District has improved infrastructure from 10% to 60% through construction of infrastructure. The district has constructed/ elevated 8 HC11 to HC 111 level there by improving quality service delivery provided in these facilities. The department has continuously improved in conducting outreaches in conducting immunization and offering maternal and child health. It should be noted that with support from development partners, the district has been able to cover up some hard to reach

There is graet improvement in quality of infrastructure for primary and secondary education. Bughendera County, pupil desk ration has improved from 1: 6 to 1: 5. There has been an increase in the number of classrooms constructed thus improving on pupil performance ratio and retention in some sub counties.  With the above infrastructure in place improvement has been exhibited in the number of pupils passing in Grade 1. From 20% to 40%. The number of failures have reduced, while the enrolment as also increased by 19%

Safe water coverage and sanitation has improved in the district. Safe water coverage has improved from 65% to 70% while sanitation is at 67% from 59%. There has been a reduction in the water borne disease and the distance walked to the nearest water source has improved

The state of  in roads infrastructure in the district and urban areas has improved in the past five years through Manual routine maintenance of 50km of selected feeder roads. Mechanised routine maintenance carried out on 18km of feeder roads which include; Busaru Mkt – Rwabatwa road 8km, Rwabatwa – Mirambi SDA road 6km, Bundibuturo road 2km. Farmers are now able to access market for their produce while schools and health facilities can also be accessed by the community

The number of SACCOs have increased from 60 to 180. This has been as result of introduction of PDM that has been centered at parish level. Two modern coffee hullers and one border market has been constructed. This has improved on post-harvest handling of coffee and access to credit by the communities

Generally in the last 5 years the district has registered great improvement in tree coverage. 1,786,000 trees have been supplied to the community with funding from the district and development partners like CRS, UHNCR, and WWF. There is reduction in encroachment on the government forest reserves and degradation of the river banks and wetlands in search of firewood as cooking materials

It can therefore be concluded that in last 5 years there was great improvement in infrastructure development, coordination, oversight monitoring, mainstreaming of cross-cutting issues and promotion of environmental and social safeguards and compared to the DDP 11

## 1.3 Outstanding Development issues/ Challenges

Despite significant improvement in the development plan 2020/2021-2024/2025, Bundibugyo district during its implementation faced a number challenges

Slow implementation of core projects under Education, Health, water, and works. The challenges were due to natural disasters like flash floods that affected the constructed roads and water facilities.  Slow implementation of projects was mainly due to inadequate funds to complete the projects, delays in mobilizing for funding, delayed procurement process especially UGIFT projects in health, education and MSI Under Agro- Industrialization the following remain development challenges there is still widespread low labor productivity among most small-scale farmers

A large proportion of households, is still stuck in the subsistence economy, there is a wide gap in yields between research stations and farmer fields. Support services such as extension services, entrepreneurial training, R&D, innovations, regulation of agricultural inputs and weather information are still inadequate, The sector is still constrained by  limited access by farmers to financial services such as credit and insurance, Whereas post-harvest handling and storage of agricultural commodities has generally improved, farmers are  still faced with a shortage of standard and modern storage  facilities, Whereas the District has realized some progress on access and use of water for agricultural production as mentioned earlier, further improvement is still constrained by factors such as inadequate local capacity of private sector players; land acquisition constraints; rapid degradation of watersheds; inadequate extension services; lack of

The district is faced with frequent natural and manmade disaster such as flooding, landslides and wind storms. Environment degradation is common. Manmade disaster include wars in neighboring DRC responsible for refuges influx.

The district has big part covered by Ruwenzori Mountains which has no road net is bid challenge for communities to access extension services. The communities in this area are generally poor and eke a living from cultivating fragile land, charcoal burning and hunting. This area experience most landslides which often result into death.

Landslides and mud slides have destroyed part of the road network. Heavy flooding has affected/dislodged drainage structures. Deterioration of the road network after a single rainy season.

Constant breakdown of equipment coupled with inadequate mechanical imprest. By the nature of climate, terrain and soil types, Bundibugyo District is highly prone to Disasters such as flush floods and landslides. Water infrastructure in this District therefore continues to be greatly affected by floods and landslides thereby affecting functionality and hence water supply reliability.

All piped water systems in Bundibugyo originate from the streams of mountain Ruwenzori. This mountain is densely inhabited by the Bakonzo Community who are traditionally cultivators. Thus, due to human activities in these mountain settlements, the catchments of these water systems, are highly degraded leading to high levels of soil erosion as well as high levels of contamination and pollution.  Yet, all the old piped water systems were not provided with sufficient treatment facilities at the time of construction.

Other Development challenges that are worth noting are

- Low local revenue realization leading to non-implementation of some planned activities

- Corruption, transparency and accountability issues

- Increased influx of asylum seekers has exerted pressure on social services and infrastructure

## 1.4 Key Lessons Leant from implementation of the previous plan

Periodization of interventions/ projects and agreeing on order of implementation is critical in guiding efficient allocation

The sector will continue to support extension service development and the provision of quality inputs to minimize the likelihood of shocks to farming households. It will also promote the organization of farmers into cooperatives and farmer organizations, which have the potential to provide socio-economic support in the event of shocks.

Low funding in the program has limited identification of more tourism sites and potentials in the district.

Involvement of local tourism groups and guides has improved tourism activities in the district especially in mountainous areas

Development partners and private sector play an important role in environment and natural resources management by providing resources and capacity building.

Introduction of government funded SACCOs and groups like Emyooga, PDM, UWEP and YLP has increased number of people doing business in the district.

Barraza’s have contributed improved transparency and accountability

Monitoring and supervision government programs improves on the services offered

Timely Procurement of works, and services improves service delivery

Participatory planning enhances ownership; integration of planning and budgeting improves efficiency; data-driven approaches support performance tracking; multi-stakeholder coordination is vital.

## 1.5 Formulation Process and Approach

The plan was prepared following a participatory bottom-up planning process that involved various stakeholders including communities at the grassroots level.

It is also linked to the Budget Framework Papers where different poverty dimensions, environment issues, gender concerns, the impact and effects of HIV/AIDS, population issues, disaster and emergency preparedness and management have been analyzed and recognized. The analysis was done at all levels of the participatory planning process, which has exposed explicitly the challenges facing Bundibugyo District.

### The District Development Plan Formulation Process

This plan was prepared using the Local Government Development Planning Guidelines (NPA, September 2020) that took into account the annual planning cycle. Development planning in local governments as stipulated in the LGA, 243(Amendment 2010), Sec 35-37 as well as sec 77 and schedule 2 is a legal requirement which follows a clearly stipulated process that makes functional linkages with the planning cycle.

The planning process in Bundibugyo District Started with a training that was organized by National Planning Authority at Regional level where data collection tools were disseminated to all Local Governments. The Tools included, Village proposal sheets for all sectors, Parish priority sheets for all departments, inventory sheets and scoring sheets

Lower local governments conducting village and parish meetings in which development priorities that could not be handled at these levels were forwarded to District for integration into the DDP. It is important to note before the District Council could approve the DDP, various discussions were conducted in DTPC, Senior management, and DEC meetings.

## Back ground to Planning / Steps

The district organized refresher training   for the Community Development officers as Focal Persons in charge of planning at those levels. They received a training on how to administer village and parish priority questionnaires, scoring forms and prioritization

The community development officers were sent to respective sub counties to facilitate the planning process. The Action Plan for each of these villages was produced emphasis was put on projects that had earlier been submitted for integration in DDP1V.

The Parish chiefs consolidated village action plans into parish action plans and this was done at the sub county level.

Approval of the village action plan was done by the LCI

Village action plans were consolidated at the parish level to form Parish plans which were sent to sub counties to come up with Sub county/ Town council development plans

Sub County/ Town council plans were made and approved by council and for project to be implemented by the district, were sent to the district for consideration and consolidation

Mentoring on Participatory Planning

Sub-county staff and heads of departments were invited for a three-days training on participatory planning at the district. The target group included the CDOs who are the focal persons for planning at LLGs levels; others were health assistants and Parish Chiefs. After the training the participants from the sub-county trained Parish Development Committee (PDC) members. These were 2 people (one female and one male) per village who were to facilitate the village planning process. During the PDC training, the district trainers (planners and SCDO) followed up the exercise to give back-up support. Thereafter, the PDCs facilitated the development of village plans with support from the district and LLGs staff. From the village plans priorities were discerned to be put in the Parish Development Plans (PDPs). LLGs assisted the PDCs in this process through follow up visits. It is from the community priority lists that respective LLGs development plans were developed. In the process, some projects were forwarded to next higher level for funding.

The DTPC appraised the Sub county/ Town council development plans and draft sectoral plans for further discussion before they were forwarded to the standing Committees of Council for further discussion and adjustments where necessary. Proposals made during the budget conference were also considered during the standing Committee meetings. NGOs were consulted so that their activities are captured in the overall District Development plan. All the above stages resulted into the production of the fourth five year development plan. Technical support was given by National Planning Authority, UNFPA funded the last hands on training held on 3rd- 4th December, 2025 at ESSELLA COUNTRY RESORT which attracted 85 LGs to finalize the Plan

Finally the Approved sectoral development plans were submitted to the district executive (DEC) for discussion. The Plans approved by DEC were merged into a district Comprehensive and integrated Development plan, which was submitted to the district council for further discussion and approval.

## 1.6 Structure of Plan

The Plan has eight chapters.

The First chapter talks about the Introduction which comprises of background of the district (it gives the summary of the performance of the previous plan, the planning involved in coming with the current plan and the stakeholders involved in the process) District profile (this gives key geographical information- soils, geographical features, land use patterns, focusing to extent of how the economic activities have affected the natural endowments). In chapter one Administrative structure is detailed giving the administrative units and lower local governments comprising the district.

It is also gives the demographic characteristics (population size and structures disaggregated   critical demographic ratios and population densities

Chapter two is about the District situation Analysis- Analysis of LG potentials, opportunities, constraints and challenges (POCC), Capture standard development indicators, review of sector development situations and previous plan performance by sector, analysis of the cross cutting issues, analysis of urban development issues, summary of the development issues informing the LGDP formulation and the status of ongoing projects and plans how they will be completed by the Local Government.

Chapter three highlights the LGDP strategic direction and plans. This looks at adoption of the National Goal, overall objectives and programs, key development results, development program interventions and out puts, summary of the LGDP programme, objectives/ outcomes, interventions/ outputs and summary of sectoral programmes/projects.

Chapter four covers the financing frame work and resources mobilization strategy. It gives the different sources of funding- Central Government, Development partners, local revenue and private sector contribution towards the implementation of the plan. It also gives details of Strategic Objectives and Interventions by program

Chapter five gives institutional arrangements for implementing the plan that gives details of Implementation Arrangement, Institutional Arrangements are, Role of Key Stakeholders, Coordination and Partnerships Framework, Prerequisites for Successful Implementation of the Plan and Conditions for successful implementation

Chapter six gives the   LGDP communication and feedback strategy. The Importance of an effective Communication and feedback strategy in the LGDP Framework

Chapter seven gives risks management and mitigation measures. Details of Type of risks, Category, causes of the risk mitigation and lead Agencies in the addressing the risk.

Chapter eight details the Monitoring, Evaluation and Learning that looks at Monitoring and Evaluation (M&E) Frameworks, M&E Roles and Responsibilities of Key Actors and Major Monitoring and Evaluation Events

CHAPTER 2: SITUATION ANALYSIS

## 2.1	Geographical Location, Land Area and Population

Bundibugyo District is located in the western region of Uganda. The District is bordered by the districts of Ntoroko in the North, Kabarole and Bunyangabu in the East and Southeast, Kasese to the Southwest, and the Democratic Republic of Congo (DRC) to the West on 0.66667 latitude and 30.05 longitude.

The size of Bundibugyo District is 849.9 square Kilometers. Therefore, the population density is 312 per square kilometer.  Settlement partners is basically rural with few upcoming linear settlements along Fort portal road, urban centers like Butoogo, Kikyo and Kanyamwirima trading while.

Rainfall

The District experiences a bimodal rainfall pattern. For most at the foot and slopes of the Rwenzori Mountains the rainfall is comparatively reliable; and so the majority of crops can be grown in both seasons. The less rainfall months are from January to February and June to July. However, Bundibugyo has experienced climate change; there has been rainfall throughout the year causing floods and landslides in the whole district.

Soil Erosion / Landslides

Bundibugyo mountainous terrain makes the area prone to immense soil erosion, which results in destructive landslides, loss of soil fertility, pollution and increased silting of rivers. Other contributing factors to soil erosion in Bundibugyo include poor agricultural practices like massive clearing of trees, bush burning, and absence of proper soil and water conservation structures like terraces and contour bands. The district has suffered disasters like cyclic occurrences of landslides every 2‐ 3 years and periodic flooding, but the trend of the recent years indicate increased indices. It is observed that every year especially during long rains of November – December landslides occur in various villages with varying magnitude. Landslides are reported to be associated with loss of crops and destruction of homes and conflicts among community members where gardens are washed into other people’s fields. The district needs to address the soil runoff challenge as part of priorities.1.2.4	Natural Resources Endowments

Tourism

Bundibugyo has great tourism potential. The main attractions are the rift valley, the forests and the Semuliki National park, Mountain Rwenzori National. These locations have a wide range of rare animal and bird life as well as many species of butterflies

The District is rich in flora and fauna, which are found in protected areas.  The largest part is located in the protected areas, which are as follows:

Semuliki National Park (220 sq. km),

Rwenzori National Park (250 sq. km),

Government forest reserve (50 sq. km),

Open water and swamps (883 sq. km)

Farmland (380 sq. km)

The National Parks and game reserve are under management of Uganda Wildlife Authority, while the 46 sq.km of forest reserves are under National Forest Authority (NFA) and 4 sq.km of the local forest reserve (calledNyakakindo Local Forest Reserve) is under management of Bundibugyo Local Government.

Hot Water Springs

The hot springs at Sempaya have a long and exciting history. For long the water from the springs are used as medicine and up to now it still attracts foreign and local visitors.

The Rift Valley

The scenic beauty of the Semuliki flats and the meandering river Semuliki are worth of tourist attract.

Wetlands and Lakes

Wetlands comprise of swamps and rivers. These resources can be exploited for fishing and sources of handcrafts materials.

Source of Fuel

Most people in Bundibugyo depend upon trees for their fuel needs, such as cooking, heating, curing cocoa and baking bricks the district has just been connected to the national hydroelectricity power grid. However, only 0.2% of the households have access to electricity leaving 98.8% dependent on firewood and charcoal as a source of household energy. There some households and organizations, which use thermal and solar power for running of various gadgets, like computers.  This over dependency on wood products has led to massive destruction of trees and bare hills are common in Bundibugyo, which facilitates soil and water run .

Demographic characteristics.

Basing on the recently concluded National Population and housing Census, 2024. The district total population is 264,778- Males 123,964 and Females 140,814

## Table 1     Population of selected age groups

| Age group | Number | Percentage |
| --- | --- | --- |
| 0-17 years ( children) | 136,560 |  |
| 18 years > ( Adult ) | 128,218 |  |
| – 15-24 years Youth | 57,441 |  |
| 18-30 years | 62,902 |  |
| 16- 64- working | 147,398 |  |
| 60+ Older persons | 12,320 |  |

Source: National Population Census 2024 Final Report

## Table 2:  Population by sub county/Town Council

| Sub County/Town Council | 2024 |  |  | Sex Ratio | Land Area (sq.Km) |
| --- | --- | --- | --- | --- | --- |
|  | Male | Female | Total |  |  |
| Bughendera | 47,519 | 52,531 | 100,050 |  |  |
| Bukonzo | 3,822 | 4,181 | 8,003 | 1.09 | 17,0 |
| Mbatya | 1,721 | 1,917 | 3,638 | 1.11 | 16,0 |
| Harugali | 4,181 | 4,709 | 8,890 | 1.12 | 40,0 |
| Ngite | 2,132 | 2,446 | 4,578 | 1.14 | 36,0 |
| Butama -Mitunda Town Council | 3,478 | 4,124 | 7,602 | 1.2 | 30,0 |
| Ndugutu | 2,176 | 2,361 | 4,537 | 1.08 | 33,0 |
| Ngamba | 4,416 | 4,913 | 9,329 | 1.11 | 35,0 |
| Ntotoro | 5,544 | 6,250 | 11,794 | 1.13 | 26,7 |
| Sindila | 3,888 | 4,293 | 8,181 | 1.10 | 9,2 |
| Kasitu | 2,396 | 2,404 | 4,800 | 1.00 | 49,0 |
| Mabere | 3,293 | 3,243 | 6,536 | 0.9 | 40,0 |
| Burondo | 3,775 | 4,139 | 7,914 | 1.14 | 36,5 |
| Kagugu | 1,836 | 2,056 | 3,892 | 1.11 | 8,0 |
| Ntandi Town Council | 4,861 | 5,495 | 10,356 | 1.13 | 41,5 |
| Bwamba | 76,445 | 88,283 | 164,728 |  |  |
| Busunga Town Council | 6,596 | 7,726 | 14,322 | 1.17 | 8,2 |
| Bubandi | 4,478 | 4,962 | 9,440 | 1.10 | 9,0 |
| Bubukwanga | 6,296 | 7,347 | 13,643 | 1.16 | 58,0 |
| Bundibugyo Town Council | 9,653 | 11,175 | 20,828 | 1.15 | 10,0 |
| Busaru | 8,259 | 9,394 | 17,653 | 1.13 | 27,4 |
| Bundingoma | 2,211 | 2,581 | 4,792 | 1.16 | 6,0 |
| Kirumya | 5,568 | 6,045 | 11,613 | 1.08 | 22,6 |
| Kisubba | 6,061 | 7,064 | 13,125 | 1.16 | 50,6 |
| Mirambi | 2,823 | 3,175 | 5,998 | 1.12 | 9,0 |
| Buganikere Town Council | 3,412 | 4,052 | 7,464 | 1.19 | 10,1 |
| Nyahuka Town Council | 9,041 | 10,872 | 19,913 | 1.2 | 13,2 |
| Tokwe | 7,649 | 8,842 | 16,491 | 1.15 | 54,5 |
| Kaghema Town Council* | 4,398 | 5,048 | 9,446 | 1.14 |  |
| District Total | 123,964 | 140,814 | 264,778 |  |  |

## Figure 1: Population pyramid

The District has a predominantly youthful population, with 39% under 18 years and over 70.1% in the working-age group (14–64 years). This demographic structure presents both opportunities and challenges: a potential labor force for development, but also a demand for education, jobs, and social services. High youth proportions signal the need for targeted investments in youth empowerment and skills development

2.1.3 Population density

The Population density of Bundibugyo District is 312 persons per sq.km. The Population is not fairly distributed since the part of the district is mountainous with sparsely populated and the Low lands are densely populated especially the urban centers.  Increase in population density implies increased pressure on natural resources like land, forests, and public utilities within the area.

2.1.4 Household Size

Bundibugyo district is comprised of twenty seven Lower Local Governments. According to the latest household demographic data, the district has total household population of   263,338 distributed across 58,755 households, with an average household size of 4.5 persons per household.

The overall average household size of 3.5 suggests moderate household density, balancing between urban and rural characteristics. Differences in household size across divisions highlight varying social and living arrangements, which could influence service delivery, housing policy, and infrastructure development.

### 2.1.5 Settlement Patterns

Settlement patterns in Bundibugyo district are shaped by infrastructure availability, economic activities, and the terrain:

- Linear settlements are common along main transport corridors, Burondo, Ntandi, Kirumya, Bubukwanga, Kanyamwirima, and Bundibugyo Town council. There more upcoming growth centres in the rural LLGs this is as result of the booming business in the sale of produce and cocoa.

- The mountainous part of Rwenzori sparsely populated due to the terrain, while in the lower settlement patterns is determined by availability of social services  .Scattered settlements dominate rural areas, with homesteads spread out on agricultural land in villages, reflective of customary land tenure and farming practices

### 2.1.6 Ethnic Groups

Bundibugyo district is predominantly inhabited by the Bamba, Babwisi, Bakonjo and Bavanoma. There are other tribes that have migrated to the district due to the cocoa booming business- These include the Bakiga, Batooro, Banyankole and Buganda.

### 2.1.7 Cultural Diversity

Bundibugyo district is under Obudhingiya Cultural institution headed by the Omudhingiya. However, there some pockets of the Bakonja who still pay allegiance to Obusinga Bwa Rwenzuru   and they are basically in the Rwenzori Mountains

### 2.1.8 Languages

Lubwisi, Rwamba and Lukonzo are the dominant language spoken in Bundibugyo Disstrict widely used in homes, markets, and community gatherings. Due to inter-District interactions and media influence, Rutooro and Luganda are also occasionally heard. English remains the official language used in schools, administration.

### 2.1.9 Population Issues

Bundibugyo presents several key population-related challenges and opportunities. The infant mortality rate in the District is estimated at 10 deaths per 1,000 live births, which is below the national average of 34. Similarly, under-five mortality remains a concern at 15 deaths per 1,000 live births, compared to the national rate of 46. The maternal mortality rate stands at 45 per 100,000 live births, which is also lower than the national figure of 207 indicating an improvement in health care services across the District though there still exist underlying challenges.

The total fertility rate in Bundibugyo is 4.7, which is higher than the national average of 4.5 the District’s literacy rate is estimated at 81%, , which is above the national average of 78.9%. The proportion of the population in the potential labour force is 66,377 estimated at 11.4%, lower than the national average (14.2%), suggesting a youthful population that will require expanded opportunities for education, skilling, and employment.

### 2.1.10 Life Standards Indicators and Statistics

### Average Life Expectancy:

The average life expectancy in Bundibugyo district is estimated at 63.3 years, slightly lower than the national average of 68.2 years. This suggests a need for targeted health interventions to improve overall population longevity.

2.1.11 Literacy Rate:

The literacy rate in Bundibugyo stands at 73.3%, which is somewhat lower than the national average of 74%, indicating that there is need to improve on education access..

### 2.1.12 Political and Administrative Issues

All administrative units within Bundibugyo District, including all sub counties, town councils and parishes, are operational, though they differ markedly in terms of size and access to infrastructure and services. Areas closer to the central business area have better access to essential services and economic opportunities, while more remote areas experience service delivery challenges.

### 2.2 Socio-Economic Situation

### 2.2.1 Poverty Situation in Bundibugyo district.

Poverty Trends

Bundibugyo District continues to face rural poverty challenges, with poverty levels estimated at around 20%, which is above the national average of 16.9%.

Inequalities as drivers of poverty and growth reduction explain Bundibugyo growing of inequality of outcomes. Differences in endowments (assets) and opportunities (economic climate, created by infrastructure investment) - whose evolution caused spatial inequality needs to be done to bring up incomes of the poor households. The location of households has also contributed to poverty levels in the district. The most affected being located in the mountain zones. They entirely depend on food crops that is grown on subsistence while in the low lands most households are engaged in Cocoa growing than earns more than the food crops.

While access to primary education and health facilities across is relatively equal in the district, still there are schools especially in rural areas where classes are in semi- permanent structure. Other factors that have determined poverty trends in the district include connection to electricity (main grid). All the sub counties in Bughendera are not connected to the power main grid. This affected the institution of cottages industries like welding workshops, milk coolers, etc. that would improve on household incomes. Thus urban areas poverty levels are lower than rural areas.

### 2.2.2 Unemployment Situation in Bundibugyo District.

Unemployment rate in Bundibugyo was reported as 11% among people aged 14-64, according to data from the Uganda Bureau of Statistics' (UBOS) 2024 National Population and Housing Census as compared national projection of around 3.35% to 6.10 which is absolutely higher

2.3 Potentials, Opportunities, Constraints and Challenges (POCC) Analysis

### 2.3.1 Agro- Industrialization

Agriculture is the backbone of Bundibugyo District economy, engaging over 80% of the population and serving as the primary source of livelihoods through crop cultivation and few households engaged in livestock and aquaculture.

Bundibugyo district is endowed with Good climate and fertile soils which favors agricultural production in livestock crop and Fisheries. It also Support agricultural activities in the district especially cocoa growing which is the back bone of this districts economy. There is need to attract investors to construct cocoa processing factory in order to increase household incomes. The district also has a District Agricultural strategic plan which is based on a vision arising from the National Agriculture Policy, which is to have “A Competitive, Profitable and Sustainable Agricultural Sector, Cross boarder agricultural market at Busunga border, Presence of coffee hullers at Ntandi Town council and Harugali for Value addition facilities newly established, Availability of both government and non-government programmes that support agricultural activities.

However, the district has the constraints; High losses due to pests, vectors and diseases; insufficient supply of raw materials, poor infrastructure and high costs of energy, uncertain land rights, landslides and floods leading to low investment in Agriculture production.

The Challenges include; High proportion of subsistence level farmers, Low levels of productivity across most enterprises; Low yields demonstrated by the wide gap in yields between research stations and farmer fields. Support services such as extension services, entrepreneurial training, R&D, innovations, regulation of agricultural inputs and weather information, to mention but a few, are still inadequate, Limited access by farmers to financial services such as credit and insurance. Shortage of standard and modern storage facilities and Limited access to markets and low competitiveness of local products in domestic, regional, international markets attributed to low value addition and the struggle to meet minimum product quality standards.

### 2.3.2 TOURISM

Bundibugyo has great tourism potential. The main attractions are the rift valley. The scenic beauty of the Semliki flats ,the meandering river Semliki, Nyahuka and Ngitte are worth of tourist attraction.

There are forests, the Semliki National park, Mountain Rwenzori National park, the hot springs at Sempaya have a long and exciting history. For long the water from the springs are used as medicine and up to now it still attracts foreign and local visitors. These National parks and forest reserves have a wide range of rare animal and bird life as well as many species of butterflies. The District is rich in flora and fauna, which are found in protected areas.

The National Parks and game reserves are under management of Uganda Wildlife Authority, while the 46 sq.km of forest reserves are under National Forest Authority (NFA) and 4 sq.km of the local forest reserve (called Nyakakindo Local Forest Reserve) is under management of Bundibugyo Local Government.

The opportunities under tourism in the district include existence of UWA which manages the two national parks in the district, rich cultural heritage through (OBB) Obudingiya bwa Bwamba. The existence of good road network- Fort portal – Bundibugyo Lamia road and the existing good governance has provided conducive environment for tourism activities . However, the current condition of Fort Portal- Bundibugyo Lamia road, Poor road network to the tourism site especially in the mountains, Some Hotels and restaurants in the district are not well developed to attract tourists. They end up travelling back to fort portal with better facilities and Unreliable power district has affected preservation of food stuffs in hotels

### 2.3.3 SCIENCE AND TECHNOLOGY

Bundibugyo district is well connected to various Telecom companies like Airtel and 
MTN., this has improved communication and access to information. ICT enhances efficiency and productivity across all sectors, has enabled the district to capitalize on emerging technologies, and enhances competitiveness. Digital tools and platforms facilitate better service delivery, increase transparency, and reduce transaction costs & lead time for acquisition of goods & services. In addition, ICT fosters innovation and entrepreneurship, creating new businesses and job opportunities. It also enables micro, small and medium enterprises (MSMEs) to access new markets and financial services. However, there is poor network as a result of masks in DRC which tamper with communication in the neighboring LLGs – Busunga TC, Bundingoma, Burondo, Sindila and Bubandi has caused network failures in the bordering communities.

## 2.3	Economic Infrastructure and services

## Urbanization

The urbanization process in the district is characterized by uncoordinated planning and developments leading to unrestricted widespread of rural growth centres (RGC).  Some of these centers are witnessing a growing number of inhabitants, mushrooming residential and business buildings and infrastructural developments like roads.

Urbanization has not been matched with a corresponding increase in provision of services and infrastructural facilities like roads, housing, education, health, sewage and sanitation including waste management facilities and landfills. Over 95% of the Rural Growth Centers are occupied by informal settlements. There are inadequate urban services and few amenities in most of the rural growth centers. There exist limited or none waste disposal facilities of landfills, incinerators, and lagoons. The district has no sewage systems in all urban areas in all the Town councils. Waste sorting for proper management and disposals is none-existent at urban areas posing serious health threats to the urban dwellers.

Physical planning

Bundibugyo Town council has a physical plan that needs updating while Nyahuka and Busunga Town Councils are in the process of preparing their physical plans and the remaining have not yet started on the process. These physical plans are expected to aid proper development by providing a clear land use plan for the centers. However, the physical planning section is understaffed with only a physical planner. There is no staff surveyor and land officer. The physical planning committees in the sub-counties are also nonfunctional. Hence, effective coordination of urban development issues has become a challenge as majority of the population are not aware of its importance. Bundibugyo district Local Government as mandated by law has prioritized physical planning through

- identification of its up-coming trading centers;

- allocating budgets to plan them and

- Preparing their development plans.

- More of the trading centers will be prioritized for physical planning and surveying.

- Recruitment of physical planners for all the 7 town councils to guide development of urban areas in the district.

Water for Production

Bundibugyo district entirely depends of rain fed agriculture. The mountainous terrain and the favorable climate has favored crop production without irrigation. Water for production project has been implemented in Burondo which experiences dry spell. With support from World Bank, micro-scale irrigation has been introduced in the communities to enhance production of vegetables and other cash crops like Cocoa and Coffee throughout the year.

# FINANCIAL SERVICES

The district has a number of financial institutions that are supporting the economic livelihoods in the district. We have two commercial banks- Stanbic bank and Centenary. There are two Micro Finance institutions – HOFOKAM and Post Bank, while there are several micro – financial institutions like BRAC, ASA UMOJA, and Kihondo SACCO.

Through the introduction of EMYOOGA, UWEP, GROW, YLP and PDM,the district has a number of Cooperatives where members can access loans to support their families in payment of school fees and livelihood that has boosted household incomes. To date we have 130 PDM SACCOs,

Road Net work

Bundibugyo district is connected with good road network- Tarmac from Kampala to Lamia Border with good community road network that is connected to schools, health facilities and cocoa producing communities. This has improved access to the market for the agricultural produce and to the social services like schools, health facilities and markets. However, due to the increase in traffic especially cargo trailers, Fort portal- Bundibugyo Lamia road has deteriorated and it is going to affect the transportation of goods outside Bundibugyo. Inadequate funding has also affected construction of community access roads and urban roads.

Energy

The district is connected to the power main grid- 33KVA which has been extended to the upcoming urban centers and some mini cocoa processing facilities in the district. Electricity is now being extended to most urban centers and rural growth centers which will improve on economic and social transformation in the district. This will improve on industrialization as well as value addition. The LLG that have so far reached are basically in the Lower lands. This has been due to the favorable terrain though some valleys have made it difficult for the service providers to reach the whole district. The areas that have not yet been covered include the mountainous areas of the Bughendera which are bordering with Mount Rwenzori National Park.

Energy plays a central role in the economy. It is the engine for economic growth and triggers sustainable development and enhances poverty reduction efforts. It affects all aspects of development, social, economic and environmental including livelihoods.  In Bundibugyo district there are mainly three major sources of energy that are being used namely; fuel wood, electricity, petroleum products and solar. Over 95% of the households’, in the district get energy from biomass mainly in the form of fire wood and charcoal yet it is used inefficiently. According to UBOS final Census report over 96% of the rural populations utilize firewood and while 70% of the urban population use charcoal as their main source of energy for cooking. The use of other improved sources of energy such as electricity, and gas is insignificant.

The other sources of energy are petroleum products. In Bundibugyo petroleum related products like kerosene, diesel and petrol are the major energy sources mostly used for transportation. However, about 65% of the households in the district also depend on kerosene for lighting..

There are 17,826 households in Bundibugyo that are solar as a source energy which is got from private providers like Solar now.

2.5 Social infrastructure and services

This section presents a situational analysis of Human and Social Development. These include; Health, Education, Water and Sanitation; Community Development and Social Protection in Bundibugyo district.

Education

There are 107 primary schools in the district of these 80% are government owned while 20% are private schools.

## Table 3: List of Primary schools

| S/NO | NAME OF SCHOOL | SUB-COUNTY | PARISH | ENROLMENT |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | BOYS | GIRLS | TOTAL |
| 1 | BUMBWENDE PRIMARY SCHOOL | MABERE | BUMBWENDE | 397 | 390 | 787 |
| 2 | KABANGO PRIMARY SCHOOL | MABERE | KABANGO | 343 | 305 | 648 |
| 3 | MABERE PRIMARY SCHOOL | MABERE | MABERE | 227 | 234 | 461 |
| 4 | BUPOMBOLI PRIMARY SCHOOL | HARUGALE | BUPOMBOLI | 105 | 108 | 213 |
| 5 | KIHOKO PRIMARY SCHOOL | HARUGALE | KIHOKO | 386 | 311 | 697 |
| 6 | IZAHURA PRIMARY SCHOOL | HARUGALE | BUPOMBOLI | 489 | 553 | 1042 |
| 7 | KARANGISTYO PRIMARY SCHOOL | HARUGALE | KARANGITSYO | 237 | 231 | 468 |
| 8 | KITSOLIMA PRIMARY SCHOOL | HARUGALE | KITSOLIMA | 234 | 217 | 451 |
| 9 | KASULENGE PRIMARY SCHOOL | HARUGALE | KASULENGE | 256 | 281 | 532 |
| 10 | MASULE PRIMARY SCHOOL | NGITE | NGITE | 234 | 239 | 473 |
| 11 | KANYANGOMA PRIMARY SCHOOL | NGITE | KANYANGOMA | 147 | 187 | 334 |
| 12 | KALEYALEYA PRIMARY SCHOOL | NGITE | KALEYALEYA | 246 | 251 | 497 |
| 13 | BUDENGE SDA PRIMARY SCHOOL | NGITE | NGITE | 205 | 248 | 453 |
| 14 | KISONKO PRIMARY SCHOOL | NDUGUTO | KISONKO | 299 | 314 | 613 |
| 15 | KIBAGHARA PRIMARY SCHOOL | NDUGUTO | KIBAGHALA | 179 | 227 | 406 |
| 16 | GALIRAYA PRIMARY SCHOOL | NDUGUTO | GALIRAYA | 177 | 187 | 364 |
| 17 | KASANZI PRIMARY SCHOOL | NDUGUTO | KASANZI | 324 | 321 | 645 |
| 18 | BUMADU PRIMARY SCHOOL | BUNDIBUGYO T. C | BUMADU | 220 | 190 | 410 |
| 19 | BUMATE PRIMARY SCHOOL | BUNDIBUGYO T.C | BUMATE | 174 | 161 | 335 |
| 20 | BUNDIBUGYO DEMO PRIMARY SCHOOL | BUNDIBUGYO T. C | HAMUTITI | 300 | 478 | 778 |
| 21 | BUNDIBUGYO PARENTS SCHOOL | BUNDIBUGYO T. C | BUNDIBUGYO CEMTRAL | 391 | 407 | 798 |
| 22 | BUNDIBUGYO PRIMARY SCHOOL | BUNDIBUGYO T.C | KANYANSIMBI | 258 | 257 | 515 |
| 23 | BUNDIBUGYO PUBLIC PRIMARY SCHOOL | BUNDIBUGYO T. C | BIMARA | 183 | 162 | 345 |
| 24 | HAMUTOMA PRIMARY SCHOOL | BUNDIBUGYO T.C | BUMADU | 105 | 98 | 203 |
| 25 | BUNDIBUGYO MOSLEM PRIMARY SCHOOL | BUNDIBUGYO T. C | BIMARA | 170 | 144 | 314 |
| 26 | KIRUMYA MOSLEM PRIMARY SCHOOL | KIRUMYA S/C | KIRUMYA | 347 | 391 | 738 |
| 27 | BUNDIKEKI PRIMARY SCHOOL | KIRUMYA S/C | BUNDIKEKI | 310 | 303 | 613 |
| 28 | BUNDIBUTURO PRIMARY SCHOOL | KIRUMYA S/C | BUNDIBUTURO | 337 | 311 | 648 |
| 29 | BUTUKURU PRIMARY SCHOOL | KIRUMYA S/C | KATUMBA | 135 | 143 | 278 |
| 30 | BUNDIWERUME PRIMARY SCHOOL | KIRUMYA S/C | NYANKIRO | 57 | 56 | 113 |
| 31 | IRAMBURA PRIMARY SCHOOL | BUKONZO S/C | IRAMBURA | 280 | 331 | 611 |
| 32 | IGHOMERWA PRIMARY SCHOOL | BUKONZO S/C | KITSANGIRWA | 226 | 222 | 448 |
| 33 | BUHUNDU PRIMARY SCHOOL | BUKONZO S/C | HUMYA | 549 | 553 | 1102 |
| 34 | BUKANGAMA PRIMARY SCHOOL | BUKONZO S/C | BUKANGAMA | 185 | 216 | 401 |
| 35 | BULEMBA I PRIMARY SCHOOL | MBATYA S/C | BULEMBA | 173 | 169 | 342 |
| 36 | BULEMBA II PRIMARY SCHOOL | MBATYA S/C | BULEMBA | 135 | 127 | 262 |
| 37 | BUSAMBA | MBATYA S/C | BUSAMBA | 208 | 202 | 410 |
| 38 | BUNGUHA PRIMARY SCHOOL | MBATYA S/C | BUNGUHA | 105 | 108 | 213 |
| 39 | BUGOMBWA PRIMARY SCHOOL | BUSARU S/C | BUGOMBWA | 227 | 237 | 467 |
| 40 | BUSARU PRIMARY SCHOOL | BUSARU S/C | BUSARU | 377 | 391 | 768 |
| 41 | NAMUGONGO PRIMARY SCHOOL | BUSARU S/C | KIRINDI | 323 | 345 | 668 |
| 42 | BUSENGERWA PRIMARY SCHOOL | BUSARU S/C | KIRINDI | 184 | 115 | 338 |
| 43 | KINYANTE PRIMARY SCHOOL | BUSARU S/C | KINYANTE | 148 | 172 | 320 |
| 44 | BUNDIMWENDI PRIMARY SCHOOL | BUSARU S/C | BUNDIMWENDI | 164 | 150 | 314 |
| 45 | BUNDINYAMA PRIMARY SCHOOL | TOKWE S/C | BUNDINYAMA | 559 | 512 | 1071 |
| 46 | BUHANDA PRIMARY SCHOOL | TOKWE S/C | BUHANDA | 505 | 473 | 978 |
| 47 | HAKITENGYA PRIMARY SCHOOL | TOKWE S/C | HAKITENGYA | 503 | 504 | 1007 |
| 48 | MATAISA PRIMARY SCHOOL | TOKWE S/C | MATAISA | 214 | 236 | 450 |
| 49 | BUNYARUTA PRIMARY SCHOOL | TOKWE S/C | BUNYARUTA | 137 | 94 | 231 |
| 50 | MANTOROBA PRIMARY SCHOOL | NTOTORO S/C | MANTOROBA | 302 | 312 | 614 |
| 51 | NTOTORO PRIMARY SCHOOL | NTOTORO S/C | BUKISI | 140 | 165 | 305 |
| 52 | KABUGA PRIMARY SCHOOL | NTOTORO S/C | KABUGA | 393 | 317 | 710 |
| 53 | NTANDI PRIMARY SCHOOL | NTANDI T.C | NTANDI | 255 | 259 | 514 |
| 54 | BUNDIMASOLYA PRIMARY SCHOOL | NTANDI T.C | BUNDIMASOLI | 519 | 508 | 1037 |
| 55 | MUTSAHURA PRIMARY SCHOOL | NTANDI T.C | KIRAMBI | 281 | 251 | 532 |
| 56 | NGAMBA PRIMARY SCHOOL | NGAMBA S/C | NGAMBA | 219 | 227 | 446 |
| 57 | BURAMBAGIRA PRIMARY SCHOOL | NGAMBA S/C | BURAMBAGIRA | 921 | 975 | 1895 |
| 58 | BUTHOLYA PRIMARY SCHOOL | NGAMBA S/C | BUTHOLYA | 186 | 195 | 381 |
| 59 | MWIRIBONDO PRIMARY SCHOOL | NGAMBA S/C | MWIRIBONDO | 189 | 223 | 410 |
| 60 | BUGHONGA PRIMARY SCHOOL | NGAMBA S/C | BUGHONGA | 194 | 225 | 419 |
| 61 | KIKYO SDA PRIMARY SCHOOL | NGAMBA S/C | KIKYO | 366 | 336 | 702 |
| 62 | BUSENDWA PRIMARY SCHOOL | NGAMBA S/C | BUSENDWA | 238 | 166 | 404 |
| 63 | KAHUMBU PRIMARY SCHOOL | KASITU S/C | KATWAKALI | 379 | 363 | 742 |
| 64 | KAMBISI PRIMARY SCHOOL | KASITU S/C | KASITU | 242 | 243 | 485 |
| 65 | KAHEMBE PRIMARY SCHOOL | KASITU S/C | NDALIBANA | 70 | 119 | 189 |
| 66 | KYONDO PRIMARY SCHOOL | KASITU S/C | NDALIBANA | 168 | 147 | 316 |
| 67 | MUNGUNI PRIMARY SCHOOL | KASITU S/C | MUNGUNI | 247 | 235 | 482 |
| 68 | BURONDO PRIMARY SCHOOL | BURONDO S/C | BURONDO | 478 | 500 | 978 |
| 69 | KARAMBI PRIMARY SCHOOL | BURONDOD S/C | KARAMBI | 319 | 314 | 633 |
| 70 | KAGUGU PRIMARY SCHOOL | KAGUGU S/C | BUNYAMWERA | 287 | 312 | 599 |
| 71 | BUNDIKAHONDO PRIMARY SCHOOL | KAGUGU S/C | NKURANGA | 201 | 203 | 404 |
| 72 | BUNDIMBUGA PRIMARY SCHOOL | BUTAMA-MITUNDA T.C | BUNDIMBUGA | 374 | 377 | 751 |
| 73 | IRANGO PRIMARY SCHOOL | BUTAMA-MITUNDA T.C | BUTAMA CENTRAL | 245 | 194 | 439 |
| 74 | BULIMBA PRIMARY SCHOOL | BUTAMA-MITUNDA T.C | BUTAMA CENTRAL | 294 | 324 | 618 |
| 75 | MITUNDA PRIMARY SCHOOL | BUTAMA-MITUNDA T.C | BUNDIMBUGA | 363 | 234 | 597 |
| 76 | MUTITI PRIMARY SCHOOL | SINDILA S/C | MUTITI | 257 | 219 | 476 |
| 77 | BUSANZA PRIMARY SCHOOL | SINDILA S/C | BUSANZA | 218 | 199 | 417 |
| 78 | KASAKA PRIMARY SCHOOL | SINDILA S/C | KASAKA | 242 | 231 | 473 |
| 79 | NYANKONDA PRIMARY SCHOOL | SINDILA S/C | NYANKONDA | 234 | 276 | 510 |
| 80 | BUNYANGULE PRIMARY SCHOOL | SINDILA S/C | BUNYANGULE | 260 | 218 | 478 |
| 81 | BUSUNGA PRIMARY SCHOOL | BUSUNGA T.C | BUSUNGA | 526 | 473 | 999 |
| 82 | LAMYA PRIMARY SCHOOL | BUSUNGA T.C | LAMYA | 249 | 251 | 540 |
| 83 | BUBANDI PRIMARY SCHOOL | BUSUNGA T.C | RUTOOBA | 565 | 513 | 1078 |
| 84 | BUNDINGOMA PRIMARY SCHOOL | BUNDINGOMA | BUNDINGOMA | 409 | 346 | 755 |
| 85 | BUSU PRIMARY SCHOOL | BUNDINGOMA | BUSU | 368 | 307 | 675 |
| 86 | NJUULE PRIMARY SCHOOL | BUBANDI S.C | NJUULE | 241 | 182 | 428 |
| 87 | TOMBWE PRIMARY SCHOOL | BUBANDI S.C | TOMBWE | 107 | 119 | 226 |
| 88 | NYAMBARO PRIMARY SCHOOL | BUBANDI S.C | NYAMBARO | 199 | 194 | 393 |
| 89 | BUNDIKAHUNGU PRIMARY SCHOOL | NYAHUKA T.C | BUNDIKAHUNGU | 253 | 239 | 492 |
| 90 | BUNDIMULINGA PRIMARY SCHOOL | NYAHUKA T.C | BUNDIMULINGA | 643 | 570 | 121 |
| 91 | KALERA PRIMARY SCHOOL | NYAHUKA T.C | KALERA | 335 | 307 | 642 |
| 92 | BUNDIKAKEMBA PRIMARY SCHOOL | NYAHUKA T.C | BUNDIKAKEMBA | 316 | 297 | 603 |
| 93 | BUNDIMBERE PRIMARY SCHOOL | NYAHUKA T.C | BUNDIMBERE | 103 | 79 | 182 |
| 94 | MIRAMBI PRIMARY SCHOOL | MIRAMBI S/C | MIRAMBI | 128 | 92 | 220 |
| 95 | NJANJA | MIRAMBI S/C | NJANJA | 733 | 724 | 1454 |
| 96 | KUKA PRIMARY SCHOOL | MIRAMBI S/C | KUKA | 268 | 274 | 542 |
| 97 | BUGANIKERE PRIMARY SCHOOL | BUGANIKERE T.C | BUGANIKERE | 370 | 316 | 686 |
| 98 | SIMBYA PRIMARY SCHOOL | BUGANIKERE T.C | SIMBYA | 268 | 248 | 511 |
| 99 | KANAMABALE PRIMARY SCHOOL | BUGANIKERE T.C | KANAMABALE | 28 | 37 | 65 |
| 100 | KISUBBA PRIMARY SCHOOL | KAGHEMA T. O | KISUBBA | 413 | 347 | 760 |
| 101 | BUNDIKUYALI PRIMARY SCHOOL | KAGHEMA T.C | BUBOMBOLI | 520 | 413 | 933 |
| 102 | HAKITARA PRIMARY SCHOOL | KISUBBA S/C | HAKITARA | 421 | 381 | 802 |
| 103 | BUTOOGO PRIMARY SCHOOL | KISUBBA S/C | BUTOOGO | 304 | 365 | 669 |
| 104 | BUSORU PRIMARY SCHOOL | KISUBBA S/C | BUSORU | 91 | 119 | 210 |
| 105 | BUBUKWANGA PRIMARY SCHOOL | BUBUKWANGA S/C | HUMYA | 257 | 263 | 520 |
| 106 | HAMUTITI PRIMARY SCHOOL | BUBUKWANGA S/C | BUBUKWANGA | 291 | 270 | 561 |
| 107 | BUNDIMAGWARA PRIMARY SCHOOL | BUBUKWANGA S/C | BUBUKWANGA | 309 | 305 | 614 |

Health and Nutrition;

This section presents situational analysis of the key aspects of public health in the Bundibugyo district. These include; accessibility to health services, available health facilities and staffing and selected health sector performance indicators.  According to office of the DHO, Seventy percent (70%) of the households are within a radius of 5kms of a health facility. Only 30 percent are in a radius of over 5kms. Out of the 27 LLGs, 9 have no health center 111s but they are served by existing Health center 11s which are about to be phased according to the new guidelines.  The catchment population for the health units for the whole district s stands at approximately at 70% this implies that health facilities are in easy reach by the residents and people have a choice as to where they can go for medical services.

## Table 4: Health infrastructure and ownership

| Category | Ownership |  | Total |
| --- | --- | --- | --- |
|  | Government | PNFP |  |
| Hospital | 1 | 0 | 1 |
| HC IV | 2 | 1 | 3 |
| HC III | 14 | 1 | 15 |
| HC II | 6 | 1 | 7 |
| Total | 24 | 3 | 27 |

## Table 5 Health Manpower

| Approved | Filled | Percentage filled | Vacant | Percentage vacant |
| --- | --- | --- | --- | --- |
| 1,415 | 471 | 33 | 944 | 67 |

WATER, SANITATION AND HYGIENE

The data from the Uganda Water Atlas shows steady progress in water access, with the population served increasing from 224,387 in 2013/2014 to 264.615 in 2023/2024 and overall access improving from 64% to 70%. Rural areas, however, remain underserved compared to urban areas, which have maintained higher access rates (73%-79%). Functionality of water systems fluctuated, with a decline to 62% in 2020/2021 but recovering to 87% in 2023/2024, indicating maintenance challenges. The persistent 0% functionality of WFP-managed systems highlights missed opportunities for leveraging resources. The Plan will address these gaps by prioritizing rural infrastructure development, ensuring sustainable system functionality, operationalizing unused systems, and strengthening monitoring frameworks to achieve equitable and sustainable water access for all by 2030.

Under sanitation, in Bundibugyo district, 76% of the total households have functional latrines/ toilets (that is any facility for excreta disposal with sub and super structure ? 44% of the households have access to a safely managed sanitation facility while 49% of households have improved latrines/ toilets ( Not shared with other Households , washable/cleanable). However, open defecation is still practiced by considerable part of the urban (26%) as well as the rural (26% ) of the population. In urban areas, households mainly access limited sanitation facilities shared with other households. in rural areas a large proportion of households make use of unimproved sanitation facilities

Social protection issues include among others orphans and vulnerable children, women who face gender-based violence and other domestic challenges. The probation and social sector is responsible for handling child related issues, domestic problems and to promote and protect children and women rights.

2.6 Environment Situation

The main wetland area in Bundibugyo district is associated with the

Semliki River and the adjacent Semliki Delta wetlands, which form a trans boundary wetland with the Democratic Republic of Congo. This area is characterized by riverine forest, swamp margins, floodplains, and is known for its high biodiversity, supporting species that have affinities with the Congo biome. However, it has also experienced significant wetland loss in recent decades.

2.7 Local Governance and Administration

Administration:

Administration is a key function for efficient and effective management of public service delivery. It entails the establishment of institutions, structures and systems, and the formulation and enforcement of policies, laws, ordnances, regulations, standards and procedures for effective coordination and management of public delivery systems. Both political and Management of the district ensure that public services are accessible by users in a timely and reliable manner, and they are affordable and of good quality. The sector is entrusted to provide support services, managerial and policy guidance to all sectors of Bundibugyo district with the objective of achieving effective and efficient service delivery to the populace in the district.

Governance:

Bundibugyo district is comprised of two counties- Bwamba and Bughendera with 27 LLGs of which 20 are sub counties and 7 Town councils. The Council is the highest political authority in the district with 52 members under the leadership of the District chairperson.

Council, Committees, Boards, and Commissions

The role of the district Executive Committee is to initiate and formulate policies for approval by the Council. It also oversees the implementation of policies made by the Council and the central Government.

Management and Technical team:

The District Council has got a technical team headed by the Chief Administrative officer, 13 sub sectors they act as the districts coordination mechanism, administration ensures that the district departments are well guided especially in strategic planning and policy direction, coordinated and regulated.

Administration strives to build capacity of departments for effective and efficient service delivery as well as ensuring that these departments conduct themselves in a manner that is accountable to the general public ensuring value for money. The department co-ordinates and supervises the provision of quality services by all key players in the district. Management and technical team comprise of Administration, Finance, Statutory Bodies, Production and marketing, Health, Education and sports Roads and Engineering, Water, Natural Resources, Community based Services, Planning, Internal Audit and Trade and Local Economic Development.

While the district council is committed to providing efficient and timely services to the entire community, the district, is constrained by a number of challenges which include among others; over dependency on grants from the central government due to limited local revenue base, inadequate qualified personnel to effectively deliver services to the people and carry out successful development projects, inadequate equipment to facilitate service monitoring.

2.8 Synthesis of development issues

- A large proportion of households,  is still stuck in the subsistence economy

- Limited production infrastructure e.g irrigation due to poor community perceptions and the mountainous  terrain

- Poor road network to the tourism site especially in the mountains

- The district is faced with frequent natural and manmade disasters such as flooding, landslides and wind storms. Environment degradation is common. Manmade disaster include wars in neighbouring DRC responsible for refuges influx.

- Encroachment on protected areas such Forest Reserves, public lands and riverbanks

- Farmer exploitation by the middle men.

- Limited entrepreneurial skills and business knowledge

- Landslides and mud slides have destroyed part of the road network, houses, water supply and crops

- Deterioration of the road network after every rainy season.

- Constant breakdown of equipment coupled with inadequate mechanical imprest

- Lack of appropriate knowledge, skills and attitude, poor population health and safety,

- Limited social protection and lack of institutionalize and integrated human resource planning and development

- Weak implementation planning and budgeting, weak M&E systems, limited financing,

- Weak coordination and weak systems for statistical development

- Over dependency on grants from the central government due to limited local revenue base including lack of a District revenue enhancement strategy

- Inadequate staffs to effectively deliver services to the people and carry out successful development projects.

- Inadequate infrastructure in terms of classrooms, latrines, staff houses,

- Inadequate furniture and fittings in public institutions

- Lack of transport means to inspectors of schools

- Refugee influx (some of these remain within the community) which brings in a hanging population.

# CHAPTER 3: LGDP STRATEGIC DIRECTION

3.1	LG Development Aspiration

## Vision

“A transformed community with improved Household incomes and livelihood by 2040”.

Mission Statement

To provide quality services to the community through an effective service delivery system with an emphasis on national and local priorities that promote a sustainable socio-economic development of the district.

Bundibugyo district local government seeks to promote the following Core Values:

- Honesty,

- Integrity,

- Accountability

- Innovation

- Dedication.

# 3.2	LGDP Strategic Direction

Theme:

“Sustainable Industrialization for Inclusive Growth, Employment, and Wealth Creation..”

Goal:

“Achieve higher household incomes, full monetization of the economy, and employment for sustainable socio-economic transformation”

“The Plan will be implemented through five Strategic Objectives;

- Sustainably increase production, productivity and value addition in agriculture, minerals, tourism, ICT, and financial services.

- Enhance human capital development along the entire life cycle;

- Support the private sector to drive growth and create jobs;

- Build and maintain strategic sustainable infrastructure in transport; and

- Strengthen good governance, security, and the role of the state in development

# 3.3	Alignment of LGDP direction with the NDPIV Programmes

Table 5: Alignment of LGDP Objectives and Strategies with the NDPIV

| Strategic Objectives (a) | Strategies (b) | NDP IV PROGRAMMES |
| --- | --- | --- |
| Objective 1: Sustainably increase production, productivity and value addition in agriculture and tourism | 1.1 Produce, multiply and distribute quality seed and inputs 1.2 Strategically invest in the fisheries sub-sector and aquaculture development 1.3 Increase access to and use of water for agricultural production 1.4 Strengthen farmer organizations and cooperatives ecosystems 1.5 Provide appropriate harvest, post-harvest handling and storage technologies 1.6 Establish and maintain appropriate market infrastructure 1.7 Promote affordable agricultural financing mechanisms 1.8 Strengthen planning, coordination, monitoring and evaluation Develop Tourism Recreational Zones 1.9 Market and promote Uganda’s tourist attractions. | Agro- Industrialisation Tourism Development Private Sector |
| Objective 2: Enhance human capital development along the entire life cycle | 2.1 Improve access and equity to pre-primary education 2.2 Promote optimal maternal, infant ,Young child, Adolescent and Elderly Nutrition Practices 2.3 Increase access to immunization against child illnesses 2.3 Improve adolescent and youth health 2.4 Strengthen the family unit to reduce domestic violence, child deprivation, abuse and child labour 2.5 Equip all lagging schools to meet BRMS 2.6 Enhance proficiency in literacy and numeracy through early Grade Reading (EGR) and Early Grade mathematics and remedial learning 2.7 Improve inclusivity in teaching and learning environments 2.8 Strengthen support services (guidance and counselling, child protection, school health, nutrition services) to enable retention and completion at all 2.9 Enforce the regulatory and quality assurance system of primary and secondary schools 2.10 Promote go to school, back to school and stay in school initiatives 2.11 Increased community ownership, access and utilization of health promotion, environmental health and community health services 2.12 Reduce the burden of communicable diseases with focus on high burden diseases (Malaria, HIV/AIDS, TB, Neglected Tropical diseases, Hepatitis), epidemic prone diseases across all age groups emphasizing Primary Health Care Approach groups emphasising primary health care approach 2.13 Improve maternal, neonatal , child and adolescent health services at all levels of care 21.4 Access to sexual and reproductive health information and services increased 2.15 Improve curative , palliative, rehabilitative and geriatric care services 2.16 Increase investment in water supply and sanitation infrastructure to increase service in underserved communities 2.17 Increase rehabilitation and expansion of existing WASH infrastructure. 2.18 Strengthen nutrition and partnership for WASH health 2.19 Promote gender equality and equity responsive planning, budgeting and implementation 2.20 Undertake monitoring, evaluation, and reporting of progress for HCD programme during plan implementation 2.21 Promote and strengthen sustainable water resources management 2.22 Integrate cross- cutting issues in the program 2.23 Strengthen regulation and enforcement against water pollution and degradation 2.24 Promote continuous mainstreaming of Climate Change and disaster risk screening in projects, programme investments, planning, implementation, management, and reporting | HUMAN CAPITAL DEVELOPMENT CLIMATE CHANGE AND NATURAL RESOURCES MANAGEMENT, WATER AND LAND MANAGEMENT |
| Objective 3: Support the private sector to drive growth and create jobs; | 3.1 Support financial inclusion pillar of PDM Implementation of the financial literacy programs 3.2 Increase access to short term fiancé | Private sector transformation |
| Objective 4: Build and maintain strategic sustainable infrastructure in transport | 4.1 Construct and upgrade strategic transport infrastructure 4.2 Rehabilitate and maintain transport infrastructure 4.3 Strengthen mechanical and engineering services | Transport and Infrastructure Development |
| Objective 5: Strengthen good governance, security, and the role of the state in development | 5.1 Fact track council business and plenary at committee level 5.2 Strengthen citizen participation in legislative process Strengthen the capacity of district councils to scrutinize and approve budgets and work plans 5.3 Strengthen mechanism for district council oversight function 5.4 Strengthen engagements between local and council and citizens 5.5 Develop a system to monitor budget implementation compliance 5.6 Build capacity in development planning and budget formulation at all levels of governance 5.7 Generate and use statistical data to inform decision making at all levels Strengthen local government revenue mobilization 5.8 Strengthen reporting and accountability 5.9 Strengthen M/E function across - Enhance local Economic Development 5.11 Improve international relations and diplomacy | Development plan implementation Public sector transformation Governance and security Legislation, Oversight and representation Regional Development |

  - Key LG Development Plan Results and Targets

Table 6: LG Development Plan Results and Targets

| Level | Key result areas | Indicators | Baseline | LGDP Targets |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2024/25 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |
| Goal: Increase household incomes and improve Quality of life | Household incomes | % of population below the poverty line | 20 | 20 | 19 | 18 | 16 | 15 |
|  |  | % of population employed less subsistence | 46.8% | 42.0% |  | 39.0% |  | 36.0% |
|  | Quality of life | Population growth rate | 5% | 5% | 4.9 | 4.8 | 4.6 | 4.5 |
| Objectives |  |  |  |  |  |  |  |  |
| Support production, productivity, and value addition in agriculture, tourism, and financial services; | Agro-industrialization | Post-harvest handling losses for priority agricultural commodities | 16.0% | 14.5% | 12.0% | 10.2% | 9.5% | 8.4% |
|  |  | Percentage of farmers adopting recommended post-harvest handling practices | 35% | 35% | 37% | 39% | 42% | 45% |
|  |  | Percentage of households dependent on subsistence Agriculture as the main source of livelihood | 46.8% | 42.0% |  | 39.0% |  | 36.0% |
|  |  | Number of water for production projects undertaken in the District | 0 | 3 | 5 | 7 | 9 | 10 |
|  |  | Number of agricultural processing plants | 30 | 32 | 34 | 37 | 39 | 40 |
|  | Tourism | Number of tourism sites identified in the District | 10 | 10 | 15 | 20 | 25 | 30 |
|  | Private sector Foundation | Proportion of farmers with access to agricultural finance | 11.3% | 13.0% | 16.0% | 18.0% | 22.0% | 25.0% |
|  | Land | Percentage of District land titled | 51 | 53 | 55 | 59 | 61 | 64 |
| Support the private sector to drive growth and create jobs/Local Economic Development | Private sector growth | Number of functional SACCOs in the District | 166 | 166 | 176 | 186 | 196 | 200 |
|  |  | %age of youth unemployed | 49.8 | 49.8 | 48 | 47 | 46 | 45 |
| Build and maintain road/urban infrastructure | Energy | Number of households with access to electricity | 20 | 20 | 40 | 50 | 60 | 70 |
|  | Roads | Outcome Indicator 1: Average Travel time min/km (District Roads) | 2.4 | 2.4 | 2.4 | 2.2 | 2.2 | 2.2 |
|  |  | Average Unit cost of rehabilitation of transport infrastructure Ugx Bn/Km (Paved District roads) | 0.150 | 0.150 | 0.130 | 0.120 | 0.110 | 0.100 |
|  |  | Average Unit cost of rehabilitation of transport infrastructure Ugx Bn (Community access roads) | 0.100 | 0.900 | 0.800 | 0.800 | 0.700 | 0.700 |
|  |  | % of DUCAR in fair to good condition | 9% | 13% | 15% | 17% | 20% | 20% |
| Enhance human capital development along the entire life cycle; | Water | % of population with access to safe water | 71 | 73 | 75 | 77 | 79 | 81 |
|  |  | % of population with access to improved sanitation | 70 | 72 | 74 | 76 | 78 | 80 |
|  |  | % of the population with access to basic hygiene services (Hand washing facilities with soap and water) | 50 | 51 | 52 | 53 | 54 | 55 |
|  |  | of the rural population with access to safe water | 71 | 72 | 73 | 74 | 75 | 76 |
|  |  | of villages with access to at least one safe water source | 57 | 59 | 61 | 63 | 65 | 67 |
|  | Education | Average years of schooling | 6.1 | 7 | 8 | 9 | 10 | 11 |
|  |  | Gross Enrolment Rate at Primary | 61.8 | 62 | 63 | 65 | 67 | 70 |
|  |  | Net Enrolment Rate at Primary | 80 | 82 | 87 | 90 | 91 | 93 |
|  |  | Percentage increase in enrolment in Early Childhood Care and Education (ECCE) | 56 | 58 | 60 | 62 | 64 | 66 |
|  |  | Literacy rate (%) | 81 | 81 | 82 | 83 | 84 | 85 |
|  | Health | Life expectancy at birth (years) | 63.3 | 63.3 | 64 | 65 | 66 | 67 |
|  |  | Infant mortality rate per 1000 | 36 | 36 | 35 | 34 | 35 | 36 |
|  |  | Maternal mortality rate/ 100,000 | 45 | 45 | 44 | 43 | 42 | 41 |
|  |  | U5 mortality rate/per 1,000 | 15 | 15 | 14 | 13 | 12 | 11 |
|  | Social protection coverage | Reduced vulnerabilities, inequity and gender inequality | 500 | 600 | 700 | 800 | 900 | 1000 |
|  |  | Youth, Women, Older Persons, PWDs, indigenous ethnic minorities and refugees livelihood and empowerment programmes implemented | 5 | 5 | 5 | 5 | 5 | 5 |
| Strengthen good local governance and accountability | Public sector transformation | Proportion of the population accessing public services by sector | 52% | 60% | 65% | 70% | 75% | 85% |
|  | Development plan implementation | % increase in the local revenue allocated to community development projects | 2% | 10% | 15% | 18% | 20% | 22% |

### 3.4	LGDP Development Results and Targets

Strategic Objective 1: Sustainably increase production, productivity and value addition in agriculture

The program aims to increase value addition to agricultural products. The key focus areas are: development and operationalization of value addition infrastructure; strengthening harvest and post-harvest handling; enhancing production and competitiveness of agricultural products for domestic, regional and international markets; strengthening specialized extension services; strengthening the adoption and integration of STI in agriculture; strengthening farmers field schools and cooperatives; de-risking agro-industry; eliminating counterfeits & low quality agro-inputs; and strengthening coordination, legal, and institutional framework for agro- industry.

### Programme 1: Agro-industrialization

### Table 7: Agro- Industrialization Development Results and Targets

| Program | Outcome | Indicator | Target 2024/25 | Target 2025/26 | Target 2026/27 | Target 2027/28 | Target 2028/29 | Target 202930 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Sustainably increase production and productivity in agriculture |  |  |  |  |  |  |  |  |  |
|  | Outcome 1.1: increased yield of priority agricultural commodities | Percentage change in yield of priority agricultural commodities | 3.4% | 3.5% | 3.7% | 3.9% | 4.3% | 5.1% | Annual Agricultural Survey |
|  | Intermediate Outcome 1.1.7 Increase farmer resilience to climate change | Production volumes of coffee (thousands 60-kg bag) | 8.1 | 10.2 | 13.5 | 16.7 | 18.2 | 20 | UCDA Annual Report |
|  | Out put | Indicator | Time Frame and Output Target |  |  |  |  |  | ACTORS |
|  |  |  | 2024/2025 | 2025/2026 | 2026/2027 | 2027/2028 | 2028/2029 | 2029/2030 |  |
| Strategic Intervention 1: Increase the uptake of fertilizers | 1.1.1.1: Fertilizer access and application increased | Number of bags of clean coffee produced per year |  | 112,500 | 112,500 | 112,500 | 112,500 | 112,500 |  |
|  |  | Number of farmer groups linked to credit services |  | 5 | 10 | 12 | 15 | 15 |  |
|  |  | Number of fertilizer dealers and premises registered |  | 2 | 4 |  | 7 | 7 |  |
| Strategic Intervention 2: Produce, multiply and distribute quality seed and inputs | Output 1.1.2.1: Agricultural inputs on the market quality assured | Number of crop compliance certificates issued (agro-chemicals dealers, premises) |  | 2 | 4 |  | 7 | 7 |  |
|  |  | Number of farmer groups provided with small scale irrigation equipment |  | 5 | 12 | 15 | 15 | 20 |  |
|  |  | Number of livestock compliance certificates issued |  | 1 | 2 | 3 | 4 | 5 |  |
| Strategic Intervention 3: Strategically invest in the fisheries sub-sector and aquaculture development | Output 1.1.3.1: Aquaculture production promoted | Number of community fish ponds established |  | 150 | 157 | 200 | 220 | 300 |  |
|  |  | Number of community groups supported with starter inputs packages |  | 150 | 157 | 200 | 220 | 300 |  |
|  |  | Number of domestic feed processors supported to produce quality fish feed |  |  | 2 |  | 4 |  |  |
|  |  | Number of extension Staff trained |  | 40 | 45 | 50 | 55 | 55 |  |
|  |  | Number of farmer groups formed |  | 2700 | 2700 | 3000 | 40000 | 4500 |  |
|  |  | Number of farmer groups supported |  | 2700 | 2700 | 3000 | 40000 | 4500 |  |
|  |  | Number of fingerings acquired (thousands fingerlings) |  | 200,000 | 300,000 | 400,000 | 420,000 | 450000 |  |
|  |  | Number of hatcheries certified |  |  | 1 |  | 2 |  |  |
|  |  | Number of surveillance and certification actions of fish processors made |  | 27 | 27 | 27 | 27 | 27 |  |
| Strategic Intervention 4: Support to large scale commercial farming entities | Output 1.1.5.1: Production capacity of large scale commercial farmers expanded | Number of government farms on which water infrastructure is renovated |  | 5 | 27 | 54 | 81 | 100 |  |
|  |  | No. of solar powered small scale water for production systems for demonstration established |  |  | 1 |  |  |  |  |
|  |  | No. of valley dams constructed |  |  |  |  | 2 |  |  |
|  |  | Number of communal dams constructed |  |  |  | 2 |  |  |  |
|  |  | Number of Individual valley tanks constructed |  |  | 2 |  | 4 |  |  |
|  |  | Number of micro-irrigation systems established |  |  |  | 2 |  | 4 |  |
|  |  | Number of solar powered small-scale irrigation systems constructed |  |  | 2 |  | 4 |  |  |
| Strategic Intervention 4: Support to large scale commercial farming entities | Output 1.1.2.3: Sustainable management mechanisms for water infrastructure established and maintained | Number of sustainable management mechanisms for water infrastructure established and maintained |  |  |  | 2 |  | 2 |  |
| Strategic Intervention 8: Strengthen farmer organizations and cooperatives ecosystems | Output 1.1.4.1: Functionality and sustainability of farmer groups, MSMEs and cooperatives improved | No. of farmer groups, MSME, Cooperatives trained |  | 15 | 20 |  | 24 |  |  |
|  |  | Number of farmer groups registered |  | 2700 | 2700 | 3000 | 40000 | 4500 |  |
|  |  | No. of farmer groups, MSME, Cooperatives supported with inputs |  | 2700 | 2700 | 3000 | 40000 | 4500 |  |
| Strategic Intervention 9: Strengthen pest, vector, disease management and control | Output 1.1.3.3: Antimicrobial resistance and disease surveillance enhanced | Number of surveillance and outbreak investigations undertaken |  | 100 | 100 | 100 | 100 | 100 |  |
|  |  | Quarterly antimicrobial surveys undertaken |  | 4 | 4 | 4 | 4 | 4 |  |
|  |  | Laboratory turnaround time for diagnostic samples submitted (hrs) |  | 4 | 4 | 4 | 4 | 4 |  |
| Strategic Intervention 10: Strengthen the agricultural extension system | Output 1.1.6.2: Capacity of extension workers enhanced | Number of demonstration gardens set-up |  | 130 | 130 | 130 | 130 | 130 |  |
|  |  | No of extension workers TOTs conducted |  | 4 | 4 | 4 | 4 | 4 |  |
|  |  | Number of Agricultural extension staff trained |  | 40 | 45 | 50 | 55 | 55 |  |
|  |  | Number of farmer groups trained |  | 2700 | 2700 | 3000 | 40000 | 4500 |  |
|  |  | No. of Agricultural extension staff equipped and facilitated |  | 40 | 45 | 50 | 55 | 55 |  |
|  |  | No.of skills and knowledge transfer centres established |  |  | 1 | 1 | 2 | 2 |  |
|  |  | Number of Extension Staff recruited |  | 5 | 5 | 5 | 5 | 5 |  |
|  | Output 1.1.6.3: Capacity of value chain actors enhanced | Number of value chain stakeholders trained on quality standards and compliance |  | 27 | 27 | 54 | 54 | 54 |  |
|  | Output 1.1.6.3: Farmers mobilized, sensitized and trained | Number of value chain stakeholders trained on quality standards and compliance |  | 5 | 10 | 10 | 15 | 16 |  |
|  |  | Number of farmers supported through the nucleus farms |  |  |  |  |  |  |  |
|  |  | Number of hectares acquired |  |  |  |  |  |  |  |
| Strategic Intervention 11: Promote climate adaptation and mitigation practices | Output 1.1.6.1: Climate smart agricultural practices undertaken | Kilograms of cover crop seeds distributed |  | TBD | TB | TB | TB | TB |  |
|  |  | No. of trees planted |  | TBD | TB | TB | TB | TB |  |
|  |  | No. of farms and ranches fully demarcated |  | 2 | 4 | 5 | 5 | 5 |  |
|  |  | Number dairy farmers trained |  | 27 | 27 | 54 | 54 | 54 |  |
|  |  | Number of Environment Social Impact Assessments, Audits and compliance enforcements. |  | TBD | TB | TB | TB | TB |  |
|  |  | Carbon farming strategy and guidelines in place |  |  | 1 | 1 | 1 | 1 |  |
|  |  | Number of youth groups engaged in commercial fodder production and conservation |  | 27 | 27 | 27 | 27 | 27 |  |
| Programme Objective 2: Improve harvesting, post-harvest handling and storage |  |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 2.1.1 Increase adoption of recommended post-harvest handling practices | Percentage of farmers adopting recommended post-harvest handling practices | 35% | 35% | 37% | 39% | 42% | 45% | Departmental quarterly reports |
| Strategic Intervention 2.1: Provide appropriate harvest, post-harvest handling and storage technologies | Output 2.1.1.1: Harvest, post-harvest handling and storage technologies developed and promoted | Number of farmers and other actors supported with appropriate post -harvest handling technologies |  | 27 | 27 | 54 | 54 | 54 |  |
|  |  | Number of post-harvest and storage facilities certified or licensed |  | 14 | 15 | 16 | 18 | 20 |  |
| Strategic Intervention 2.2: Ensure compliance to standards at harvesting, post-harvest handling and storage | Output 2.1.1.1: Harvest, post-harvest handling and storage standards developed and enforced | Number of farmer groups and other actors supported with appropriate agro-processing and value addition technologies |  | 27 | 27 | 54 | 54 | 54 |  |
| Strategic Intervention 2.3: Invest in appropriate agro-processing and value addition technologies | Output 2.2.1.2: Agro-processing and value addition technologies promoted |  |  |  |  |  |  |  |  |
| Programme Objective 3: Develop, operationalize and optimize value addition infrastructure |  |  |  |  |  |  |  |  |  |
|  | intermediate Outcome 3.1.1 Functional value addition infrastructure in place | Percentage of processed agricultural products | 5% | 7% | 10% | 12% | 15% | 17% | Annual District Agricultural statistics reports |
| Strategic Intervention 3.1: Establish appropriate value addition infrastructure | Output 3.1.1.1: Value addition infrastructure established | Completion status of the Cocoa processing factory |  | TBD |  |  |  |  |  |
| Programme Objective 4: Increase market access and competitiveness of agricultural products in domestic and international markets |  |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 4.1.1 Reduce subsistence farming | Percentage of households dependent on subsistence Agriculture as the main source of livelihood | 46.8% | 42.0% |  | 39.0% |  | 36.0% | Departmental annual reports |
| Strategic Intervention 4.1: Establish and maintain appropriate market infrastructure | Output 4.1.1.1: Marketing infrastructure established and maintained | Number of Livestock markets constructed |  |  | 1 |  | 2 | 2 |  |
|  |  | Number of slaughter facilities constructed |  |  | 27 | 27 | 27 | 27 |  |
|  |  | Kms of agricultural access roads constructed |  | TBD |  |  |  |  |  |
| Strategic Intervention 4.3: Promote market penetration for agro-based products |  |  |  |  |  |  |  |  |  |
|  |  | Production | 12 | 13.1 | 15.3 | 17.3 | 19.6 | 21.0 | Departmental annual agricultural statistics reports/surveys |
|  |  | volumes of cocoa (MT) |  |  |  |  |  |  |  |
|  |  | Production volumes of oil palm (MT) | 1790 | 1930 | 2074 | 2260 | 2380 | 2500 | MAAIF Statistical Abstract |
|  |  | Production volumes of beef (MT) |  |  |  |  |  |  |  |
| Programme Objective 2: Improve harvesting, post-harvest handling and storage |  |  |  |  |  |  |  |  |  |
|  | Output 1.1.6.3: Capacity of value chain actors enhanced | Post-harvest handling losses for priority agricultural commodities | 16.0% | 14.5% | 12.0% | 10.2% | 9.5% | 8.4% | APHLIS |
|  | Intermediate Outcome 2.1.1 Increase adoption of recommended post-harvest handling practices | Percentage of farmers adopting recommended post-harvest handling practices | 35% | 35% | 37% | 39% | 42% | 45% | Departmental quarterly reports |
| Programme Objective 5: Increase access to agricultural finance and insurance |  |  |  |  |  |  |  |  |  |
|  | intermediate Outcome 3.1.1 Functional value addition infrastructure in place | Percentage of processed agricultural products | 5% | 7% | 10% | 12% | 15% | 17% | Annual District Agricultural statistics reports |
| Programme Objective 4: Increase market access and competitiveness of agricultural products in domestic and international markets |  |  |  |  |  |  |  |  |  |
|  | Prog. Outcome 4.1: Increase income from agricultural enterprises | Median monthly nominal wages for paid employees in agriculture, forestry and fisheries as the main occupation (UGX) | 120,000 | 140,000 |  | 180,000 |  | 200,000 | Departmental annual reports |
|  | Intermediate Outcome 4.1.1 Reduce subsistence farming | Percentage of households dependent on subsistence Agriculture as the main source of livelihood | 46.8% | 42.0% |  | 39.0% |  | 36.0% | Departmental annual reports |
| Programme Objective 5: Increase access to agricultural finance and insurance |  |  |  |  |  |  |  |  |  |
|  | Prog. Outcome 5.1: Increase private and Government investment in agriculture |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 5.1.1 Increase access to agricultural financing | Proportion of farmers with access to agricultural finance | 11.3% | 13.0% | 16.0% | 18.0% | 22.0% | 25.0% | Departmental reports |

| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  | ACTORS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 1: Increase the uptake of fertilizers | Output 1.1.1.1: Fertilizer access and application increased | Number of bags of clean coffee produced per year | 112,500 | 112,500 | 112,500 | 112,500 | 112,500 | Quarterly performance reports |
|  |  | Number of farmer groups linked to credit services | 5 | 10 | 12 | 15 | 15 | Quarterly performance reports |
|  |  | Number of fertilizer dealers and premises registered | 2 | 4 |  | 7 | 7 | Quartery performance reports |
| Strategic Intervention 2: Produce, multiply and distribute quality seed and inputs | Output 1.1.2.1: Agricultural inputs on the market quality assured | Number of crop compliance certificates issued (agro-chemicals dealers, premises) | 2 | 4 |  | 7 | 7 | Quartery performance reports |
|  |  | Number of farmer groups provided with small scale irrigation equipment | 5 | 12 | 15 | 15 | 20 | Quarterly performance reports |
|  |  | Number of livestock compliance certificates issued | 1 | 2 | 3 | 4 | 5 | Quartery performance reports |
| Strategic Intervention 3: Strategically invest in the fisheries sub-sector and aquaculture development | Output 1.1.3.1: Aquaculture production promoted | Number of community fish ponds established | 150 | 157 | 200 | 220 | 300 | Quartery performance reports |
|  |  | Number of community groups supported with starter inputs packages | 150 | 157 | 200 | 220 | 300 | Quartery performance reports |
|  |  | Number of domestic feed processors supported to produce quality fish feed |  | 2 |  | 4 |  | Quartery performance reports |
|  |  | Number of extension Staff trained | 40 | 45 | 50 | 55 | 55 | Quartery performance reports |
|  |  | Number of farmer groups formed | 2700 | 2700 | 3000 | 40000 | 4500 | Quarterly performance reports |
|  |  | Number of farmer groups supported | 2700 | 2700 | 3000 | 40000 | 4500 | Quartery performance reports |
|  |  | Number of fingerings acquired (thousands fingerlings) | 200,000 | 300,000 | 400,000 | 420,000 | 450000 | Quartery performance reports |
|  |  | Number of hatcheries certified |  | 1 |  | 2 |  | Quartery performance reports |
|  |  | Number of surveillance and certification actions of fish processors made | 27 | 27 | 27 | 27 | 27 | Quartery performance reports |
| Strategic Intervention 4: Support to large scale commercial farming entities | Output 1.1.5.1: Production capacity of large scale commercial farmers expanded | Number of solar powered irrigation demonstrations established | 27 | 27 | 27 | 27 | 27 | Quartery performance reports |
|  |  | Number of tractors with assorted implements acquired | 2 | 2 | 5 | 6 | 5 | Quartery performance reports |
|  |  | No. of medium & large-scale commercial farms supported | 4 | 6 | 9 | 10 | 10 | Quartery performance reports |
|  |  | Number of large land owners supported to plant coffee | 2 | 4 | 4 | 5 | 5 | Quartery performance reports |
|  |  | Number of large scale commercial farmers supported | 2 | 4 | 4 | 5 | 5 | Quartery performance reports |
| Strategic Intervention 5: Increase access to and use of water for agricultural production | Output 1.1.2.1: Facilities, equipment and machinery managed and maintained | Number of government farms on which water infrastructure is renovated | 1 |  | 1 | 1 | 1 | Quartery performance reports |
|  | Output 1.1.2.2: On-farm water for production infrastructure established | No. of solar powered small scale water for production systems for demonstration established | 5 | 27 | 54 | 81 | 100 | Quartery performance reports |
|  |  | No. of valley dams constructed |  | 1 |  |  |  |  |
|  |  | Number of communal dams constructed |  |  |  | 2 |  |  |
|  |  | Number of Individual valley tanks constructed |  |  | 2 |  |  |  |
|  |  | Number of micro-irrigation systems established |  | 2 |  | 4 |  |  |
|  |  | Number of solar powered small-scale irrigation systems constructed |  |  | 2 |  | 4 |  |
|  | Output 1.1.2.3: Sustainable management mechanisms for water infrastructure established and maintained | Number of sustainable management mechanisms for water infrastructure established and maintained |  |  | 2 |  | 2 |  |
| Strategic Intervention 8: Strengthen farmer organizations and cooperatives ecosystems | Output 1.1.4.1: Functionality and sustainability of farmer groups, MSMEs and cooperatives improved | No. of farmer groups, MSME, Cooperatives trained | 15 | 20 |  | 24 |  |  |
|  |  | Number of farmer groups registered | 2700 | 2700 | 3000 | 40000 | 4500 | Quartery performance reports |
|  |  | No. of farmer groups, MSME, Cooperatives supported with inputs | 2700 | 2700 | 3000 | 40000 | 4500 | Quartery performance reports |
| Strategic Intervention 9: Strengthen pest, vector, disease management and control | Output 1.1.3.3: Antimicrobial resistance and disease surveillance enhanced | Number of surveillance and outbreak investigations undertaken | 100 | 100 | 100 | 100 | 100 | Quartery performance reports |
|  |  | Quarterly antimicrobial surveys undertaken | 4 | 4 | 4 | 4 | 4 | Quartery performance reports |
|  |  | Laboratory turnaround time for diagnostic samples submitted (hrs) | 4 | 4 | 4 | 4 | 4 | Quartery performance reports |
| Strategic Intervention 10: Strengthen the agricultural extension system | Output 1.1.6.2: Capacity of extension workers enhanced | Number of demonstration gardens set-up | 130 | 130 | 130 | 130 | 130 | Quartery performance reports |
|  |  | No of extension workers TOTs conducted | 4 | 4 | 4 | 4 | 4 | Quartery performance reports |
|  |  | Number of Agricultural extension staff trained | 40 | 45 | 50 | 55 | 55 | Quartery performance reports |
|  |  | Number of farmer groups trained | 2700 | 2700 | 3000 | 40000 | 4500 | Quartery performance reports |
|  |  | No. of Agricultural extension staff equipped and facilitated | 40 | 45 | 50 | 55 | 55 | Quartery performance reports |
|  |  | No.of skills and knowledge transfer centres established |  | 1 | 1 | 2 | 2 | Annual performance reports |
|  |  | Number of Extension Staff recruited | 5 | 5 | 5 | 5 | 5 | Annual performance reports |
|  | Output 1.1.6.3: Capacity of value chain actors enhanced | Number of value chain stakeholders trained on quality standards and compliance | 27 | 27 | 54 | 54 | 54 | Annual performance reports |
|  | Output 1.1.6.3: Farmers mobilized, sensitized and trained | Number of farmers supported through the nucleus farms | 5 | 10 | 10 | 15 | 16 | Annual performance reports |
|  |  | Number of hectares acquired |  |  |  |  |  |  |
|  | Intermediate Outcome 1.1.7 Increase farmer resilience to climate change | Proportion of farmers adopting sustainable land management/climate smart practices | 3% | 5% | 10% | 15% | 20% | Annual performance reports |
| Strategic Intervention 11: Promote climate adaptation and mitigation practices | Output 1.1.6.1: Climate smart agricultural practices undertaken | Kilograms of cover crop seeds distributed | TBD | TB | TB | TB | TB | Annual performance reports |
|  |  | No. of trees planted | TBD | TB | TB | TB | TB | Annual performance reports |
|  |  | No. of farms and ranches fully demarcated | 2 | 4 | 5 | 5 | 5 | Annual performance reports |
|  |  | Number dairy farmers trained | 27 | 27 | 54 | 54 | 54 | Annual performance reports |
|  |  | Number of Environment Social Impact Assessments, Audits and compliance enforcements. | TBD | TB | TB | TB | TB | Annual performance reports |
|  |  | Carbon farming strategy and guidelines in place |  | 1 | 1 | 1 | 1 | Quartery performance reports |
|  |  | Number of youth groups engaged in commercial fodder production and conservation |  | 27 | 27 | 27 | 27 | Quartery performance reports |
| Strategic Intervention 2.1: Provide appropriate harvest, post-harvest handling and storage technologies | Output 2.1.1.1: Harvest, post-harvest handling and storage technologies developed and promoted | Number of farmers and other actors supported with appropriate post -harvest handling technologies | 2700 | 2700 | 3000 | 40000 | 4500 | Quartery performance reports |
|  |  | Number of postharvest handling, processing and storage technologies developed | TBD | TB | TB | TB | TB | Quartery performance reports |
| Strategic Intervention 2.2: Ensure compliance to standards at harvesting, post-harvest handling and storage | Output 2.1.1.1: Harvest, post-harvest handling and storage standards developed and enforced | Number of value chain actors trained in Harvest, post-harvest handling and storage, quality control and compliance standard | 27 | 27 | 54 | 54 | 54 | Quartery performance reports |
|  |  | Number of post-harvest and storage facilities certified or licensed | 14 | 15 | 16 | 18 | 20 | Quartery performance reports |
| Strategic Intervention 2.3: Invest in appropriate agro-processing and value addition technologies | Output 2.2.1.2: Agro-processing and value addition technologies promoted | Number of farmer groups and other actors supported with appropriate agro-processing and value addition technologies | 27 | 27 | 54 | 54 | 54 | Quartery performance reports |
| Strategic Intervention 3.1: Establish appropriate value addition infrastructure | Output 3.1.1.1: Value addition infrastructure established | Completion status of the Cocoa processing factory | TBD |  |  |  |  |  |
| Strategic Intervention 4.1: Establish and maintain appropriate market infrastructure | Output 4.1.1.1: Marketing infrastructure established and maintained | Number of Livestock markets constructed |  | 1 |  | 2 | 2 | Annual performance reports |
|  |  | Number of slaughter facilities constructed |  | 27 | 27 | 27 | 27 | Quartery performance reports |
|  |  | Kms of agricultural access roads constructed | TBD |  |  |  |  |  |
| Strategic Intervention 4.3: Promote market penetration for agro-based products | Number of enterprises profiled |  |  | 1 | 2 | 2 | 2 | Annual performance reports |

Program 2: Tourism Development Programme Results and Targets

The Tourism Development Programme: aims to position the district as a preferred tourist destination. The key focus areas are: increasing tourism-related research and uptake; development, improvement, and diversification of tourism products; improving tourism infrastructure (transport, trails, electricity, ICT, accommodation and MICE); reducing the tourism skills gaps; strengthening and harmonizing marketing & promotion of Uganda as a preferred destination; strengthening enforcement of tourism standards and regulations; and strengthening conservation and protection of natural resources.

Program Goal: To Position Uganda as a preferred tourism destination.

Table 8: Tourism Development Programme Results and Targets

| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 3: Conserve, Develop, improve and diversify tourism products | Outcome 3.1: Improved Natural and Cultural Heritage Conservation | 3.1.3: Proportion of cultural sites with conservation efforts | 15.00% | 20% | 25% | 30% | 35% | 40% | Annual Tourism development Programme performance Report |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 3.1.1: Improved Wildlife Ecosystems | 3.1.1.5: Number of visitors to Museums and cultural sites | 1,250 | 1,259 | 1,245 | 1,400 | 1,450 | 125,404 | Administrative data collected by MM |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 3.2: Prioritize investments in the Country’s major tourism products in a sustainable way. | Output 1: Private sector players empowered to develop and manage tourism sites and facilities stopover point | Number of compliant stopover points along tourist routes | 0 | 3 | 3 | 3 | 5 | 7 | TILED |
|  | Output 2: Cultural tourism circuits developed. | Number of cultural tourism circuits developed | 0 | 0 | 1 | 1 | 1 | 1 | TILED |
|  | Output 4: Agro- tourism developed | No of agro tourism enterprises enlisted | 0 | 5 | 5 | 5 | 7 | 10 | TILED |
|  | Output 5: Culinary tourism products developed and promoted. | No of culinary tourism events held | 1 | 2 | 2 | 2 | 2 | 2 | TILED |
| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Objective 4: Develop skilled personnel along the tourism value chain | Outcome 4.1: Increased employment/ jobs created along the tourism value chain | 4.1.1: Contribution of tourism to total employment (%) | 5.7 | 7.10% | 7.60% | 8.20% | 8.70% | 9.20% | UBOS (Manpower Survey), Tourism Satellite Account |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 4.1.1: Personnel trained | 4.1.1.1: Number of people directly employed along the tourism value chain | 500 | 600 | 650 | 700 | 750 | 800 | UBOS (Manpower Survey), Tourism Satellite Account |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 4.1: Address skills and capacity gaps in the tourism and hospitality industry | Output: Tourism in-service personnel trained | No of tourism in-service personnel trained. | 0 | 10 | 12 | 12 | 12 | 17 | TILED |

| Intervention | Key Output | Indicator (f) | ANNUAL TARGETS |  |  |  |  | Actors |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention 1.1 Undertake district wide awareness and campaigns on cultural heritage conservation and importance of cultural heritage | Cultural museum developed and equipped | Number of cultural museums developed and equipped. | 1 | 1 | 1 | 1 | 1 | OBB, CCFU, DCDO, UWA, DLG |
|  |  | Number of community sensitization conducted | 4 | 4 | 4 | 4 | 4 | OBB, CCFU, DCDO, UWA, DLG |
| Intervention 1.2 Conduct community engagements | Historical and new sites sites/ of significance preserved | Number of community engagement meetings conducted | 4 | 4 | 4 | 4 | 4 | OBB, CCFU, DCDO, UWA, DLG |
| Intervention 1.3 Conduct conditional surveys and assessments on the performance of tourist sites |  | Number of functional community sites | 1 | 2 | 2 | 2 | 2 | OBB, CCFU, DCDO, UWA, DLG |
| 1.4 Develop plans and undertake feasibility studies for water-based tourism falls- Ngitte and Nyahuka, and Sempaya hot springs. | Output 5: Cultural tourism circuits developed. | Number of water-based tourism sites developed (cumulative) | 1 | 1 | 1 | 1 | 1 | UWA, DLG , TOURISM DEPT LLGS |

### 3.5.5 Natural Resources, Environment, Climate Change, Land, and Water Management

Goal: Sustainable management and utilization of Land, Water, environment and natural resources and effective response to climate change and other disasters.

The program aims to ensure sustainable management and utilization of land, environment & natural resources and effective response to climate change and other disasters. The key focus areas are: strengthening land administration and management; restoration of wetlands & forest cover; reducing the districts vulnerability to climate change; reduction of air and water pollution levels; value addition to forests & other natural resources; and strengthening institutional coordination, enforcement & implementation of policies & laws.

Table 9: Natural Resources, Environment, Climate Change, Land, and Water Management Programme Results and Targets.

| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 3: Protect, restore and add value to forests and wetlands | Outcome 3.1: Increased forest and wetland cover for socio-economic and ecological benefits | Percentage of land area covered by forests | 15 | 17 | 19 | 20 | 21 | 22 | Annual Performance Reports, Forest Management plans, Forestry Inventory reports |
|  |  | Percentage of land area covered by wetlands | 2.3 | 2.4 | 3.7 | 3.9 | 4 | 5 | Annual Performance Reports |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 3.1:1 Reduced area of degraded forests and landscapes | Area (ha) of degraded forest and degraded landscapes restored | 40 | 45 | 50 | 55 | 60 | 70 | Annual Performance Reports, Forest Management plans, Forestry Inventory reports |
|  | Intermediate Outcome 2.2:1.1: Reduced area of degraded wetlands | Percentage reduction in area of degraded wetland | 0.46 | 0.05 | 0.05 | 0.06 | 0.06 | 0.06 | Annual Programme Performance Report, Management plans |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 3.1: Increased forest and wetland cover for socio-economic and ecological benefits | Output 3.1.1: Central Forest reserves restored and protected | Area (ha) of CFRs protected from illegal activities | 70 | 65 | 60 | 55 | 50 | 45 | Natural Resources Department |
|  | Output 3.1.2: Degraded landscapes restored | Area (ha) of degraded landscapes restored | 30 | 35 | 40 | 45 | 50 | 55 | Natural Resources Department |
| Strategic Intervention 3.2: Upscale commercial forestry including bamboo and exploit opportunities along its entire value chain so as to leverage on its economic benefits and to increase resilience to climatic changes; | Output 3.2.1: Support establishment and maintenance of commercial forest plantations including bamboo within central forest reserves and private land. | Area (ha) of commercial plantations (above 10ha) established | 15 | 20 | 25 | 30 | 35 | 40 | Natural Resources Department |
|  |  | Area (ha) of commercial woodlots established | 20 | 25 | 30 | 35 | 40 | 45 | Natural Resources Department |
| Strategic Intervention 2.2.1: Protect and increase the wetland cover | Output 2.2.1.1: Gender responsive wetlands management plans and District/city wetland action plans developed and implemented | Area (ha) of wetlands under management plans | 70 | 75 | 80 | 85 | 90 | 95 | Natural Resources Department |
|  | Output 2.2.1.2: Wetland alternative livelihood options promoted and supported | Number of households supported with alternative livelihood options | 100 | 95 | 90 | 85 | 80 | 75 | Natural Resources Department |
|  | Output 2.2.1.3: Wetland boundaries surveyed and demarcated | Length (Km) of wetlands boundaries demarcated. | 6 | 6.5 | 7 | 7.5 | 8.0 | 8.5 | Natural Resources Department |
|  | Output 2.2.1.4: Degraded wetlands restored | Area (Ha) of wetlands restored | 40 | 60 | 65 | 70 | 75 | 80 | Natural Resources Department |
|  | Output 2.2.1.5: Wetland resources knowledge and information products produced | Number of wetland resources knowledge and information products | 3 | 3 | 4 | 3 | 4 | 4 | Natural Resources Department |
| Strategic Intervention 2.2.3: Strengthen regulation and enforcement against environmental pollution and degradation | Output 2.2.3.2: Interventions to halt degradation of wetland resources established and implemented | Number of compliance and enforcement actions undertaken | 80 | 100 | 100 | 120 | 150 | 200 | Natural Resources Department |
| Strategic Intervention 2.2.4: Promote biodiversity conservation | Output 2.2.4.2: Wetland biodiversity-based Ecotourism sites promoted | Number of wetlands biodiversity based ecotourism sites developed and promoted | 0 | 5 | 10 | 15 | 20 | 25 | Natural Resources Department |
| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Objective 4: To ensure a clean, healthy and productive environment | Outcome 1.1: Improved well-being, a sustainable and productive environment | Number of green jobs | 0 | 2 | 4 | 6 | 8 | 10 | National State of Environment Reports |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Increased environmentally sustainable technologies and practices for social economic transformation | Percentage area of fragile ecosystems (Hilly and mountainous areas, rangelands, riverbanks and lakeshores) restored | 15.00% | 20.00% | 25.00% | 30.00% | 35.00% | 40.00% | Annual Programme |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 4.1: Promote circular economy | Output 4.1.3: Initiatives that improve waste management undertaken | Proportion of solid waste recycled in urban areas | 10% | 15% | 20% | 25% | 30% | 35% | Natural Resources Department |
| Strategic Intervention 4.2: Strengthen regulation and enforcement against environmental pollution and degradation | Output 4.2.1: Measures to control environmental pollution established and implemented | Number of environment assessment reports (ToRs, ESIAs and SEAs) reviewed | 5 | 10 | 15 | 20 | 25 | 30 | Natural Resources Department |
|  |  | Number of environmental enforcement operations conducted by EPF | 10 | 15 | 20 | 25 | 30 | 35 | Natural Resources Department |
| Strategic Intervention 4.3: Promote sustainable biodiversity management in within and outside protected areas | Output 4.3.1: Fragile ecosystems restored and protected (Rangelands, hilly and mountainous areas, riverbanks and lakeshores) | Area (Ha) of fragile ecosystems restored/ protected | 60 | 65 | 70 | 75 | 80 | 85 | Natural Resources Department |
|  | Output 4.3.2: Threatened ecosystems mpleme as special conservation areas | Number of ecosystems mpleme as special conservation areas | 1 | 2 | 4 | 6 | 8 | 12 | Natural Resources Department |

Private Sector Development Programme: aims to increase survival and transition of private enterprises. The key focus areas are: reducing the cost of doing business; ensuring market access and competitiveness of goods and services; strengthening the capacity of local firms to tap into public investment opportunities; enhancing survival and growth of private enterprises; and strengthening the private sector organizational and institutional capacity.

Table 10: Private Sector Development Programme Results and Targets

| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Sustainably lower the cost of financing | Strategic Output: 1.1.1.2.3. Women and PWDs benefited from Government financial products | Increased number of women-led enterprises | 1000 | 1200 | 2400 | 3200 | 3450 | 4000 | TILED |
| Intervention: 1.1.2.1. Increase access to short term finance | Strategic output: 1.1.2.1.1. Emyooga SACCOs and other client institutions offered credit and grant financing | Value of financing (credit and grant) to women, youth and PWDs | 180M | 120M | 120M | 120M | 120M | 120M | TILED |
| Intervention 1.1.2.2. Implement financial literacy programs |  | Number of Emyooga SACCOs offered grant financing | 36 | 36 | 36 | 36 | 36 | 36 | TILED |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention 3.1.1.1. Roll out business development services (BDS) to support MSMEs. | Strategic output: 3.1.1.1.1. Compliance to Good corporate Governance best practices improved | Number of Annual Returns filed with URSB | 100 | 120 | 110 | 100 | 100 | 100 | TILED |
|  | Strategic output: 3.1.1.1.2. National BDS Framework Operationalized | Number of Entrepreneurs/MSMEs on government programs trained and supported | 75 | 78 | 80 | 86 | 87 | 100 | TILED |
|  |  | % Increase in MSMEs accessing bank financing after accessing BDS | 5% | 5% | 5% | 5% | 5% | 5% | TILED |
|  |  | Number of enterprises provided with BDS in RHS | 20 | 20 | 20 | 30 | 25 | 27 | TILED |
| Intervention 3.1.2.3. 3.1.3.1. Promote implementation and business registration | Strategic output3.1.3.1.1. Uptake of business registration enhanced | Number of businesses registered (New Company + Business names) | 15 | 25 | 26 | 35 | 59 | 70 | TILED |

Human Capital Development Programme:

This program aims to achieve a healthy, knowledgeable, skilled, ethical and productive population. The key focus areas are: strengthening the foundation for human capital; reducing knowledge and skills gaps; strengthening talent development and nurturing; developing and maintaining supportive infrastructure and facilities for the creative industry, sports, health, and education; increasing adoption of preventive health measures; reducing child labor, child marriages, and teenage pregnancies; improving food and nutrition security; increasing access and coverage of WASH; increasing coverage of social protection; reduce gender inequality and inequities; increasing participation in government programmes and wealth creation initiatives; institutionalizing and integrating human resource planning and development; reducing the cost of provision and access to health and education services, and ensuring decent and productive work environment for all.

Goal: The goal of this programme is a healthy, knowledgeable, skilled, ethical, and productive population.

Table 11: Human Capital Development Programme Results and Targets

| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: To improve the foundation of human capital development | Outcome 1.1: Improved access and quality of basic education | Average years of schooling | 6 | 6 | 6 | 6 | 6 | 6 | MoES |
|  |  | Learning adjusted years of schooling | 6 | 6 | 6 | 6 | 6 | 6 | MoES |
|  |  | Gross Enrolment Rate at Primary | 61.8 | 61.8 | 62 | 63 | 65 | 67 | School data/ EMIS |
|  |  | Net Enrolment Rate at Primary | 80 | 82 | 87 | 90 | 91 | 92 | EMIS |
|  |  | Percentage of children who are developmentally on track in at least three of the four domains of development (Numeracy, physical, socio-emotional, and learning) disaggregated by nationality, refugee status and disability. | 85 | 85 | 85 | 85 | 85 | 85 | school data/ Emis |
|  |  | Completion Rate at P.7 | 62 | 62 | 70 | 70 | 80 | 80 | EMIS / Education Dept data |
|  |  | Transition rate from primary to lower secondary education | 85 | 85 | 89 | 89 | 90 | 90 | department data |
|  | Outcome 1.2: Improved child wellbeing and development | Percentage of children who are developmentally on track in at least three of the four domains of development (Numeracy, physical, socio-emotional, and learning) by nationality, refugee status and disability. | 20% | 30% | 35% | 38% | 50% | 50% | Dept enrolment |
|  |  | Percentage of children who are attending early childhood development programs, disaggregated by nationality, refugee status and disability. | 20% | 30% | 35% | 38% | 50% | 50% | Dept enrolment |
|  |  | Percentage of children (aged 1-14) who experienced any form of violent discipline aggregated by nationality, refugee status and disability. | 25% | 25% | 25% | 20% | 20% | 20% | CBS data |
|  |  | Percentage of children age 15-17 who have ever experienced sexual violence aggregated by nationality and refugee status | 6% | 5% | 4% | 3% | 2% | 1% | CBS data |
|  | Outcome 1.3: Improved Pupil/Student Learning Outcomes | Proportion of students achieving proficiency in Literacy | 97.2 | 97.2 | 97.2 | 97.2 | 97.2 | 97.2 | NAPE 2023 |
|  |  | Proportion of students achieving proficiency in Numeracy | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | 95.5 | NAPE 2023 |
|  |  | Completion Rate for Primary Education [SDG Indicator 4.1.2] | 62 | 62 | 70 | 70 | 80 | 80 | Emis/ Educ Dept data |
|  |  | Survival Rate (Primary 7) | 62 | 62 | 70 | 70 | 80 | 80 | EMIS / educ Dept |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1.1: Increased access to quality and inclusive pre-primary education | Percentage increase in enrolment in Early Childhood Care and Education (ECCE) | 50 | 50 | 60 | 62 | 64 | 66 | education dept. |
|  | Intermediate Outcome 1.2.1: Enhanced compliance of duty bearers (families, parents and caregivers) to parenting standards (what are the parameter for measuring compliance? Define family) | Proportion of duty bearers (families, parents and caregivers) complying to the parenting standards | 25% | 25% | 28% | 30% | 35% | 40% | Police reports, SAUTI 116 Helpline, Reports from Community Services Departments in the DLGs, Juvenile court records |
|  | Intermediate Outcome 1.2.2: Improved child health and wellbeing | Reduced stunting | 44 | 44 | 45 | 46 | 47 | 48 | WHM |
|  |  | Reduced wasting | 30 | 30 | 50 | 60 | 65 | 70 | WHM |
|  | Intermediate Outcome 1.3.1: Improved learning, instruction, assessment and learning environments at basic education | Pupil Teacher Ratio | 1;70 | 1;70 | 1;70 | 1;70 | 1;70 | 1;70 | EMIS |
|  |  | Student teacher ratio | 25 | 24 | 22 | 21 | 20 | 19 | MoES |
|  |  | Student-to-Classroom ratio | 1;55 | 1;55 | 1;55 | 1;55 | 1;55 | 1;50 | EMIS |
|  |  | Proportion of primary teachers with the minimum required qualifications | 78% | 78% | 78% | 78% | 78% | 78% | EMIS |
|  |  | Pupil Desk Ratio | 1:5 | 1:5 | 1:5 | 1:5 | 1:5 | 1:5 | EMIS |
|  |  | Percentage of children age 15-17 who have ever experienced sexual violence aggregated by nationality and refugee status | 10% | 10% | 10% | 10% | 10% | 10% | EMIS |
|  |  | Percentage of children (aged 1-14) who experienced any form of violent discipline aggregated by nationality, refugee status and disability. | 10% | 10% | 10% | 10% | 10% | 10% | EMIS |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 2: Institutionalize Pre-primary teacher training at public teacher training institutions | Strategic Output 1.1.1.2: Improved Teacher Qualification and Training for quality provision of ECCE | Number of Pre-primary teachers trained in-service through CPDs | 26 | 26 | 26 | 26 | 26 | 26 | Education Department |
|  |  | Number of ECCE centres monitored, support supervised and inspected at least once per term | 15 | 15 | 15 | 15 | 15 | 15 | Education Department |
| Strategic Intervention 4: Improve Physical and Cognitive development of children below 8 years | Output 1.2.1.1: Prevention and response strategies to abuse, exploitation and violence against children, 0-8 years and their caregivers reviewed and rolled out | Number of D/CDOs trained on effective parenting of children | 26 | 26 | 26 | 26 | 26 | 26 | Community based Department |
|  |  | Number of caregivers/parents trained on effective parenting of children | 0 | 20 | 30 | 50 | 50 | 60 | Education Department |
|  |  | Number of LLGs implementing the strategies for preventing and responding to abuse, exploitation and violence against children, 0-8 years and their caregivers. | 0 | 2 | 3 | 5 | 7 | 8 | Education Department |
|  | Output 1.2.1.2: Compliance to the delivery of Early Childhood Development services strengthened | Proportion of ECD Centres compliant to the National Early Childhood Development standards | 0 | 0.35 | 0.55 | 0.65 | 0.8 | 0.85 | Education Department |
| Strategic Intervention 5:Promote optimal Maternal, Infant, Young child, Adolescent and Elderly Nutrition Practices | Strategic Output 1.2.2.1: Enabling environment for scaling up nutrition at all levels strengthened | Number of Nutrition regulations, guidelines and SOPs developed |  | 1 | 2 | 1 | 1 | 1 | Education Department |
|  |  | % of Schools providing feeding to children | 0 | 20 | 30 | 40 | 50 | 60 | Education Department |
|  |  | % of Health facilities designated as mother-baby friendly (Hospitals, HC Ivs and IIIs) |  |  |  |  |  |  | Health Department |
|  | Strategic Output 1.2.2.2: Promote consumption of fortified foods especially in schools with focus on beans, sweat potatoes, cooking oil and maize. | No. of school management committees sensitized on consumption of fortified foods in schools | 70 | 10 | 10 | 10 |  |  | Education Department |
| Strategic Intervention 6: Increase access to immunization against childhood diseases | Strategic Output 1.2.2.7: Increase access to immunization against childhood diseases | % of under 5 children dewormed in last 6 months | 311% | 319% | 319% | 319% | 319% | 319% | Health Department |
|  |  | Measles-Rubella 2nd dose Coverage | 412% | 136% | 136% | 136% | 136% | 136% | Health Department |
|  |  | % of Children under one year fully immunized | 261% | 131% | 131% | 131% | 131% | 131% | Health Department |
|  |  | % of children under 24 months immunized against malaria (malaria 4th dose coverage) | 0 | 12% | 12% | 12% | 12% | 12% | Health Department |
| Strategic Intervention 8: Strengthen the family Unit to reduce domestic violence, child deprivation, abuse and child labor | Output 1.2.2.10: Family institution strengthened to care and protect children against abuse | Proportion of incidences of Violence Against Children cases | 0 | 20 | 24 | 27 | 33 | 44 | Community based Department |
|  |  | No. of families accessing Counselling services | 98 | 110 | 150 | 170 | 220 | 250 | Community based Department |
|  |  | No. of family support groups established | No data | 3 | 4 | 6 | 7 | 9 | Community based Department |
|  |  | No. of Community Outreach programmes conducted | 4 | 8 | 6 | 7 | 8 | 8 | Community based Department |
|  |  | No of training programmes for family support practitioners /Para Social Workers conducted | 0 | 4 | 3 | 5 | 4 | 6 | Community based Department |
| Strategic Intervention 9: Equip all lagging schools to meet BRMS | Strategic Output 1.3.1.1: Lagging Public primary schools constructed, renovated, equipped with required infrastructure and staffed | Number of schools constructed in each of the parishes | 4 | 1 | 2 | 1 | 0 | 2 | Education Department |
|  |  | Number of existing public primary schools rehabilitated. | 2,656 | 60 | 102 | 102 | 102 | 102 | Education Department |
|  |  | Number of existing public primary schools renovated | 508 | 56 | 74 | 86 | 94 | 74 | Education Department |
|  |  | Number of classroom furniture (desks/tables/chairs/stools) provided in primary schools |  | 100 | 150 | 150 | 100 | 100 | MoES |
|  |  | Number of teachers houses constructed in rural public primary schools |  | 2 | 1 | 1 | 1 | 1 | Annual Reports |
|  | Latrines constructed at primary schools | Number of latrines constructed | 2 | 2 | 1 | 1 | 1 | 1 | Quarterly performance reports |
|  | Staff houses constructed at primary schools | Number of staff houses constructed | 1 | 2 | 6 | 6 | 5 | 5 | Quarterly performance reports |
|  | Classroom blocks constructed/renovated/completed | Number of classroom blocks constructed/renovated/completed | 2 | 2 | 1 | 1 | 1 | 1 | Quarterly performance reports |
|  | Water tanks constructed at primary schools | Number of water tanks constructed | 0 | 2 | 2 | 2 | 2 | 2 | Quarterly performance reports |
|  | Desks procured for schools | Number of desks procured | 100 | 150 | 150 | 100 | 100 | 100 | Quarterly performance reports |
| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 2: To produce appropriate knowledgeable, skilled and ethical labour force (with strong emphasis on science and technology; STEI/STEM in education and TVET) | Outcome 2.1: Improved Alignment of Workforce Supply with Labor Market Demands | Percentage of employers satisfied with training provided by TVET |  |  |  |  |  |  | Graduate Tracer Studies |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 2.1.1: Strengthened workforce planning, management and development | Science teachers to pupil ratio (secondary) | 1:09 | 1:07 | 1:06 | 1:05 | 1:04 | 1:03 |  |
|  |  | Percentage of TVET institutions meeting the BRMS | 16% | 18% | 20% | 22% | 24% | 26% |  |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Data Source |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 5: Increase access to TVET training in skills scarce TVET programmes to reverse the currently inverted skills triangle | Output 2.2.1.3: Increased access to scarce skills programmes | Number of TVET Institutions | 2 | 2 | 2 | 2 | 2 | 2 | APR |
|  |  | Number of TVET trainers recruited | 1,861 | 775 | 465 | 1,405 | 775 | 785 | APR |
|  |  | Number of TVET Institutions Grant aided | 143 | 153 | 163 | 183 | 203 | 213 | Annual Reports |
| Strategic Intervention 7: Review curricula to make them competence-based at all levels and implement competence-based curricula at all levels. | Strategic Output 2.2.1.6: Competence-Based Curricula Developed and implemented | Competence-Based Curriculum for Primary Education developed, piloted and implemented | - | 1 | 1 | 1 | 1 | 1 | Annual Reports |
|  |  | Competence-Based Curriculum for Upper Secondary Education developed, piloted and implemented | - | 1 | 1 | 1 | 1 | 1 | Annual Reports |
|  |  | Number of instructors/teachers retooled on the revised curriculum | 240 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | Annual Reports |
|  |  | School curricular aligned to ESD policy | - | 1 | 1 | 1 | 1 | 1 | Annual Reports |
|  |  | Learning Materials and Resources aligned with Competence-Based Curricula | - | 50,000 | 50,000 | 50,000 | 50,000 | 50,000 | Annual Reports |
| Programme Objectives | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Objective 3: To improve population health, safety and management; Access to safe water sanitation and hygiene services. | Outcome 3.1: Improved Health and wellbeing of the population | % of Prevalence of stunting among children under 5 | 26% | 26% | 26% | 26% | 26% | 23% | UDHS |
|  |  | Under Five Mortality Rate (per 1,000 live births) | 45 | 45 | 45 | 45 | 45 | 45 | UDHS |
|  |  | % of population with access to safe water | 71 | 73 | 75 | 77 | 79 | 81 | APPR, WEIS |
|  |  | % of population with access to improved sanitation | 70 | 72 | 74 | 76 | 78 | 80 | APPR, WEIS |
|  |  | % of the population with access to basic hygiene services | 50 | 51 | 52 | 53 | 54 | 55 | APPR, WEIS |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 3.1.1: Improved utilization of health services | Per Capita OPD attendance | 0.99 | 0.98 | 0.97 | 0.91 | 0.85 | 0.8 | DHIS2 |
|  |  | Hospital (public & private) admission rate (per 1,000 population) | 77.6 | 75 | 73 | 72 | 69 | 67 | DHIS2 |
|  |  | Bed Occupancy Rate (%) | 62% | 65% | 69% | 73% | 77% | 81% | DHIS 2 |
|  |  | HIV Viral Load Suppression rate among PLHA | 96% | 97% | 97% | 98% | 98% | 99% | HMIS |
|  |  | TB case notification rate/100,0000 | 198 | 187 | 177 | 168 | 159 | 150 | DHIS2 |
|  |  | DPTHibHep 3rd dose coverage (%) | 95% | 95% | 95% | 96% | 96% | 97% | DHIS2 |
|  |  | ANC 4th Visit Coverage (%) | 54% | 56% | 58% | 60% | 62% | 64% | DHIS2 |
|  |  | Deliveries in health facilities (%) | 67% | 69% | 70% | 72% | 73% | 75% | DHIS2 |
|  |  | Service availability and readiness index (%) | 49% | 51% | 51% | 53% | 53% | 56% | HHFA |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention: Strategic Intervention 1: Increase community ownership, access and utilization of health promotion, environmental health and community health services | Strategic Output 3.1.1.1: Integrated community health services package rolled out in all villages | % of sick children who were managed by VHTs who recovered | 65% | 68% | 71% | 74% | 77% | 80% | Health Department |
|  |  | % of Villages with at least 2 VHTs offering integrated community health service package | 0% | 30% | 40% | 50% | 55% | 65% | Health Department |
|  | Strategic Output 3.1.1.2: Strengthen enforcement of health/WASH-related legislation | Mortality rate from unsafe WASH (Diarrhoea, Typhoid, Dysentery & Cholera), per 100,000 population | 28.1 | 28.1 | 26 | 26 | 26 | 24 | Health Department |
|  |  | % of Households using a hand washing facility with soap and water | 14% | 16% | 16% | 16% | 18% | 18% | Health Department |
|  |  | % of Households with access to an improved water source | 81% | 81% | 83 | 84 | 85 | 86 | water department Department |
|  |  | % Households with improved sanitation facilities | 31% | 31% | 31% | 31% | 35% | 35% | NSDS |
|  | Strategic Output 3.1.1.3: Climate resilient health system built | % of LGs with health staff oriented in climate adaptation and mitigation capacity (%) | 0 | 20% | 30% | 40% | 50% | 60% | Health Department |
|  |  | % of Health facilities with climate resilient infrastructure (Solar Energy, incinerators, WASH) | 15% | 30% | 33% | 35% | 37% | 40% | Health Department |
|  | Strategic Output 3.1.1.4: Health/Nutrition promotion and education interventions scaled up | % of Planned health/Nutrition promotion and disease prevention events held | 15% | 25% | 35% | 40% | 45% | 50% | Health Department |
|  |  | National Communication Strategy & calendar developed | 1 | 1 | 1 | 1 | 1 | 1 | Health Department |
|  |  | % of Health facilities (HC III and above) providing integrated management of acute malnutrition | 45% | 50% | 55% | 60% | 65% | 70% | Health Department |
|  |  | % of OPD clients who had the nutritional status assessed | 63% | 69% | 75% | 81% | 87% | 93% | Health Department |
| Strategic Intervention 2: Reduce the burden of communicable diseases with focus on high burden diseases (Malaria, HIV/AIDS, TB, Neglected Tropical diseases, Hepatitis), epidemic prone diseases across all age groups emphasizing Primary Health Care Approach | Strategic Output 3.1.1.5: Access to malaria prevention and treatment services improved | % of sick children seen by VHT and treated within 24 hours for fever | 70% | 74% | 79% | 84% | 89% | 95% | Health Department |
|  |  | % of Population who slept under an ITN the night before the survey | 62% | 62% | 62% | 62% | 65% | 65% | Health Department |
|  |  | Intermittent Presumptive Treatment for Malaria in Pregnancy 3rd dose coverage (%) | 55% | 56% | 59% | 61% | 63% | 66% | Health Department |
|  | Strategic Output 3.1.1.6: Access to HIV/AIDs prevention, control and treatment services improved | Number of HIV/AIDS Care and prevention strategies and guidelines developed (Number) |  | 1 | 0 | 1 | 0 | s | Health Department |
|  |  | % of Population who know 3 methods of HIV prevention | 91% | 91% | 91% | 91% | 93% | 93% | UDHS |
|  |  | ART Retention rate at 12 months (%) | 82% | 84% | 87% | 90% | 92% | 95% | Health Department |
|  |  | % of HIV positive Pregnant women initiated on ART | 95% | 96% | 97% | 98% | 99% | 100% | Health Department |
|  |  | % of HIV exposed infants with 2nd DNA/PCR within 9 months | 81% | 80% | 87% | 94% | 100% | 100% | Health Department |
|  |  | Number of Safe male circumcisions conducted |  |  |  |  |  |  | Health Department |
| Strategic Intervention 3: Prevent and control Non-Communicable diseases with specific focus on cancer, cardiovascular, genetic, renal, endocrine, mental, trauma and malnutrition across all age groups. | Strategic Output 3.1.1.11: Centres of excellence in provision of oncology, cardiovascular and trauma services at both National and Regional Levels and foster regional integration established | Population aged 15 – 49 years diagnosed with diabetes who are on treatment (%) | 31% | 31% | 31% | 35% | 35% | 35% | Health Department |
|  |  | Population aged 15 – 49 years diagnosed with heart/chronic disease who are on treatment (%) | 40% | 40% | 40% | 40% | 45% | 45% | Health Department |
|  |  | % of Women 25 – 49 years screened for cervical cancer | 23% | 28% | 28% | 28% | 33% | 33% | Health Department |
|  |  | % of Men 40+ years screened for prostate cancer | 19% | 20% | 21% | 22% | 24% | 25% | Health Department |
|  |  | HPV 2nd dose coverage for girls at 10 years | 75% | 78% | 81% | 84% | 87% | 90% | Health Department |
|  | Strategic Output 3.1.1.12: Strengthen multi-sectoral & health sector capacity in NCDs & injury prevention and control | Alcohol Abuse Rate (%) | 6.60% | 6.60% | 6% | 6% | 6% | 5.50% | Health Department |
|  |  | Total alcohol per capita (>15 years of age consumption) (litres of pure alcohol) | 12.2 | 12.2 | 12.2 | 10 | 10 | 10 | Health Department |
|  |  | Road traffic injury mortality rate (per 100,000 population) | 29.4 | 27.7 | 26.2 | 24.7 | 23.3 | 22 | Health Department |
|  |  | % of MDAs with NCD prevention and control workplace policies | NA | 3% | 10% | 15% | 20% | 25% | Health Department |
|  |  | Number of health workers trained in substance abuse management and rehabilitation |  | 20 | 20 | 25 | 30 | 30 | Health Department |
| Strategic Intervention 4: Improve maternal, neonatal, child and adolescent health services at all levels of care | Strategic Output 3.1.1.15: Investments in maternal and child health services at all levels of care increased | % of under 5 illnesses attributed to diarrheal diseases | 60% | 64% | 69% | 74% | 80% | 85% | Health Department |
|  |  | % of deliveries in health facilities | 65% | 69% | 70% | 72% | 73% | 75% | Health Department |
|  |  | Institutional/Facility Maternal Mortality Risk/ 100,000 deliveries | 83 | 78 | 73 | 68 | 64 | 60 | Health Department |
|  |  | % of HC Ivs that are fully functional (Offering blood Transfusion and Caesarean Section) | 60% | 64% | 69% | 74% | 80% | 85% | Health Department |
|  | Strategic Output 3.1.1.16: Invest in appropriate neonatal care services at all levels | Institutional perinatal mortality rate per 1,000 births | 17.8 | 16.5 | 15.2 | 14.1 | 13 | 12 | Health Department |
|  |  | % of perinatal deaths reviewed | 80% | 100% | 100% | 100% | 100% | 100% | Health Department |
|  | Strategic Output 3.1.1.17: High impact adolescent health interventions to reduce teenage pregnancies, with a special focus on hot spot Districts developed and implemented | Adolescent Birth Rate (per 1,000 women aged 15 – 19 years) | 106 | 106 | 103 | 103 | 96 | 96 | Health Department |
|  |  | Adolescent Health Services implementation plan 2025 – 2030 developed & disseminated to all LGs | 0 | 100% | 100% | 100% | 100% | 100% | Health Department |
|  |  | Number of health workers oriented on adolescent health guidelines | 0 | 300 | 300 | 300 | 300 | 300 | Health Department |
|  |  | Number of LGs with Adolescent health guidelines | 0 | 50% | 100% | 100% | 100% | 100% | Health Department |
|  |  | Number of Adolescent & Youth peer educators oriented on age appropriate reproductive health |  | 2,000 | 2,500 | 3,000 | 3,500 | 4,000 | Health Department |
| Strategic intervention 5. : Access to Sexual and Reproductive Health (SRH) information and services increased | Strategic Output 3.1.1.18: Increased demand and uptake of reproductive health services | Couple years of protection | 4,403,934 | 4,883,147 | 5,362,360 | 5,841,574 | 6,320,787 | 6,800,000 | Health Department |
|  |  | Prevalence of positive syphilis serology in pregnant women (%) | 1.80% | 1.80% | 1.70% | 1.70% | 1.60% | 1.60% | Health Department |
|  |  | Prevalence of anaemia in pregnancy (%) | 23% | 21% | 19% | 18% | 16% | 15% | Health Department |
|  |  | % of obstetric & gynecologic admissions due to abortion | 12% | 10% | 10% | 9% | 9% | 8% | Health Department |
|  |  | % of pregnant women attending ANC who test HIV positive | 2% | 2% | 2% | 2% | 1% | 1% | Health Department |
| Strategic Intervention 6: Improve curative, palliative, rehabilitative and geriatric care services | Strategic Output 3.1.1.19: Quality curative, palliative, rehabilitative and geriatric care services provided | Per Capita OPD attendance | 0.99 | 0.98 | 0.97 | 0.91 | 0.85 | 0.8 | DHIS2 |
|  |  | Bed Occupancy Rate (%) | 62% | 65% | 69% | 73% | 77% | 81% | Health Department |
|  |  | Malaria Case Fatality Rate (per 10,000) | 13.8 | 11.7 | 9.9 | 8.4 | 7.1 | 6 | Health Department |
|  |  | % of health facilities (public & private) in conformity with the IPC standards (WHO) | 0% | 9% | 15% | 26% | 46% | 80% | Health Department |
|  | Strategic Output 3.1.1.22: Nursing and midwifery practice strengthened | Number of quarterly supervision and mentorship visits |  | 4 | 4 | 4 | 4 | 4 | Health Department |
|  |  | Number of standards and guidelines developed |  | 1 | 0 | 1 | 0 | 1 | Health Department |
| Strategic Intervention 7: Improve the functionality of the health system to deliver quality and affordable preventive, promotive, curative and palliative healthcare services. | Strategic Output 3.1.2.1: Adequate and well-trained human resources for health at all levels in place | % of approved posts filled in public health facilities | 34% | 38% | 40% | 45% | 50% | 55% | Health Department |
|  |  | Human Resource for Health Development Plan 2025/26 – 2029/30 developed | 1 | 1 | 0 | MTR | 0 | 0 | Health Department |
|  |  | Number of health workers trained (in-service training) for all programs / services | 7,538 | 8,000 | 8,500 | 9,000 | 9,500 | 10,000 | Health Department |
|  | Strategic Output 3.1.2.2: Health Infrastructure improved ( | % of Health facilities with adequate clean energy (solar) source | 80% | 80% | 100% | 100% | 100% | 100% | Health Department |
|  | Heath facilities upgraded ( | Number of health facilities upgraded | 8 | 8 | 2 | 2 | 2 | 2 | Health Department |
|  | OPD blocks constructed/renovated | Number of OPD blocks constructed | 8 | 8 | 2 | 2 | 2 | 2 | Health Department |
|  | Staff houses constructed (Ruhooko Health Centre IV and Bundibugyo Health Centre IV) | Number of staff houses constructed | 2 | 1 | 0 | 2 | 2 | 3 | Health Department |
|  | Construction of Mortuary at Bundibugyo HCIV | Number of mortuary units completed | 0 | 0 | 1 | 0 | 1 | 0 | Health Department |
|  | Pit latrines constructed at (Ruhooko Health Centre IV and Bundibugyo Health Centre IV) | Number of pit latrines constructed | 4 | 4 | 2 | 1 | 1 | 1 | Health Department |
|  | Medical laboratory constructed (Ruhooko Health Centre IV and Bundibugyo Health Centre IV) | Number of medical labs constructed | 0 | 0 | 0 | 0 | 1 | 1 | Health Department |
|  | Medical and laboratory equipment procured (All health facilities) | Number of facilities provided with medical equipment | 24 HFs | 24 HFs | 24 HFs | 24 HFs | 24 HFs | 24 HFs | Health Department |
|  | Furniture procured (All health facilities) | Number of facilities provided with furniture | 24 HFs | 24 HFs | 24 HFs | 24 HFs | 24 HFs | 24 HFs | Health Department |
|  | Laptop, desktop computers and printer procured | Number of computers and printers procured | 0 | 2 | 0 | 3 | 0 | 0 | Health Department |
|  | Retaining walls constructed | Number of retaining walls constructed | 0 | 1 | 0 | 0 | 0 | 0 | Health Department |
|  | Strategic Output: 3.1.2.4: Expand geographical access | Number of HC I11s constructed | 0 | 0 | 1 | 0 | 1 | 0 | Health Department |
|  |  | Number of HC IIIs established | 0 | 0 | 1 | 1 | 1 | 1 | Health Department |
| Programme Objectives (Aligned to the LGDPIV Strategic Objective- LGDPIV Development Results) | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 4: To promote decent work and productive employment | Outcome 4.1: Improved productive employment and decent work for all | Labor rate | 42 | 40 | 38 | 36 | 34 | 32 | National LFS and Uganda National Household Survey |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 4.1.1: Employment opportunities, safety and Compliance to labour standards increased | Number of jobs created in formal and informal sector |  | 800 | 800 | 800 | 800 | 800 | National Human Resource Survey |
|  |  | Number of workplaces reporting Occupational injuries and diseases | 10 | 500 | 1,000 | 2,000 | 4,000 | 8,000 | OSH MIS |
|  |  | Number of inspected work places compliant with labour standards | 20000 | 500 | 600 | 800 | 900 | 1000 | OSH MIS |
|  |  | Proportion of children aged 5-17 years engaged in child Labour excluding household chores aggregated by nationality, refugee status and disability. | 40% | 39% | 38% | 37% | 36% | 35% | NLFS, UBOS (2021) |
|  |  | Percentage of youth neither in employment nor in education (NEETS) | 49.8 | 49.8 | 48 | 47 | 46 | 45 | FINAL CENSUS REPORT 2024 |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
|  |  | Number of workers, employers, training institutions and recruitment agencies on labour Policies, laws, regulations and guidelines aggregated by nationality and refugee status | 35 | 1 | 1 | 1 | 1 | 1 | Community Based Services |
| Strategic Intervention 4: Improving Occupational Safety and Health (OSH) management | Output 4.1.1.6: Mechanisms for reducing workplace injuries, accidents and occupational diseases implemented | Number of workplaces with OSH systems in place | 50 | 50 | 50 | 50 | 50 | 50 | Community Based Services |
|  |  | Number of workplaces reporting OSH injuries and diseases to MGLSD | 10 | 50 | 50 | 50 | 50 | 50 | Community Based Services |
| Programme Objectives (Aligned to the LGDPIV Strategic Objective- LGDPIV Development Results) | Outcomes (a) | Outcome Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 5: Reduce vulnerability, gender inequality and inequity along the lifecycle | Outcome 5.1: Reduced vulnerabilities, inequity and gender inequality | Average number of hours a week spent on un-paid care work by sex | 15 | 19 | 18 | 16 | 15 | 13 | Time Use survey |
|  |  | Percentage of the vulnerable and marginalized persons empowered | 22% | 30% | 30% | 30% | 38% | 38% | Administrative |
|  |  | Proportion of mplemen married below 18 years | 32.80% | 30% | 29% | 26% | 24% | 20% | UDHS, MGLSD reports |
|  | Intermediate Outcome (b) | Indicator | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 5.1.1:Vulnerable persons protected from deprivation and livelihood risks | Percentage of seats/positions held by special interest groups (women, Older Persons, Persons with Disabilities (PWDs), Children& Youth, Ethnic minorities) | 34% (Women) | 1% | 1% | 1% | 1% | 1% | office of clerk to council |
|  |  | Proportion of the eligible vulnerable persons with access to Direct income support | 0.14 | 0.16 | 0.16 | 0.16 | 0.24 | 0.24 | Community Based services |
|  |  | Percentage of children involved in child labour | 31 | 31 | 31 | 31 | 31 | 31 | Community Based services |
|  |  | Proportion of the population covered by social protection systems by sex, distinguishing children, youth, older persons, PWDs, work injury victims, the poor, vulnerable and refugees | 0.9% (Youth) | 5% | 7% | 8% | 9% | 10% | MGLSD reports, UboS |
|  | Intermediate Outcome 5.1.2: Improved Gender relations in development processes | Prevalence of physical Violence | 94 | 94 | 94 | 94 | 94 | 94 | A survey by Ourganda in 2022 |
|  |  | Prevalence of sexual Violence | 16.00% | 16.00% | 14.80% | 14.80% | 14.80% | 11.00% | PSEA Task Force |
|  |  | CSO data base List of Organization dealing with PCVET | 1 | 1 | 1 | 1 | 1 | 1 | Mercy Corps/ URI |
|  |  | Percentage reduction in child marriage (children married by age 18) | 56 | 56 | 40 | 35 | 30 | 30 | Department of CBS |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 1 : Expand scope and coverage of livelihood enhancement and economic empowerment programmes for Youth, Women, Older Persons, PWDs and ethnic minorities | Output 5.1.1.1: Youth, Women, Older Persons, PWDs, indigenous ethnic minorities and refugee’s livelihood and empowerment programmes implemented | Number of youths benefitting from livelihood and empowerment programmes aggregated by nationality, refugee status and disability. |  | 8640 | 8640 | 8640 | 8640 | 8640 | Community Based Services |
|  |  | Number of women in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 2,519 | 3000 | 3500 | 4000 | 4500 | 5000 | Community Based Services |
|  |  | Number of Older Persons Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 1,356 | 1,356 | 1,356 | 1,356 | 1,356 | 1,356 | Community Based Services |
|  |  | Number of PWDs Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 70 | 70 | 75 | 80 | 85 | 90 | Community Based Services |
| Strategic Intervention 2: Expand the scope and coverage of Social Security along the life cycle. | Output 5.1.1.2: Direct Income Support Programmes designed and implemented | Number of Direct Income Support Interventions developed and implemented |  | 8 | 9 | 10 | 10 | 10 | Community Based Services |
|  | Output 5.1.1.5: Social protection systems strengthened. | Functional social protection systems in place. |  | 3 | 5 | 8 | 8 | 8 | Community Based Services |
|  | Output 5.1.2 Dialogue and conflict prevention | Number of dialogue meetings conducted to Promote tolerance and facilitate dialogue in at risk communities to build communities which appreciate their differences and understand each other. | 0 | 1 | 1 | 1 | 1 | 1 | Community Based Services |
| Strategic Intervention 3 : Provide holistic social care and support (assistance) services to vulnerable groups | Output 5.1.1.7: Holistic Social Care and Support for the Poor and Vulnerable persons provided across the Lifecycle | Number of children accessing social care and support services in the Institutions (Rehabilitation Centre, Remand homes and Children’s homes) | 2,303 | 2,000 | 2,000 | 1,800 | 1,700 | 1,500 | Community Based Services |
|  |  | Number of eligible poor accessing social care and support aggregated by nationality, refugee status and disability |  | 10,000 | 10,000 | 10,000 | 10,000 | 10,000 | Community Based Services |

## .4.1 PUBLIC SECTOR TRANSFORMATION

Public sector transformation aims to improve public sector response to the needs of the citizens and the private sector. The key focus areas are: strengthening accountability mechanisms; strengthening human resource management in the public sector; enhancing adoption and usage of e-government services; streamlining government structures and institutions for efficient and effective service delivery; and deepening decentralization and local economic development.

Table 12: Public sector Development Programme Results and Targets

| Level | Key Results (Impacts for Goal and Outcomes for the objectives) | Indicators | Baseline | LGDP Targets |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2024/25 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |
|  | Improved Quality of Services Delivered | Proportion of the population satisfied with their last experience of public services | 63.50% | 65% | 70% | 75% | 80% | 85% |
| Objective 1: Strengthen accountability for results across local government | Outcome 1.1 Increased transparency and accountability in provision of public services | Proportion of the population satisfied with their last experience of public services | 55% | 60% | 65% | 70% | 75% | 85% |
|  | Outcome 1.2 Increased trust and uptake of public services | Proportion of the population accessing public services by sector | 52% | 60% | 65% | 70% | 75% | 85% |
| Objective 2: Streamline government structures for efficient and effective service delivery | Outcome 2.1 Improved efficiency of government institutions in service delivery | DLG with structures aligned to its mandate and the National Development Plan. | 70% | 75% | 80% | 85% | 90% | 95% |
|  | Outcome 2.2 Reduced duplication and overlaps in government structures | DLG with structures void of duplications and overlaps. | 70% | 75% | 80% | 85% | 90% | 95% |
| Objective 3: Strengthen human resource management for improved service delivery | Outcome 3.1 Improved quality of public service | Perception of Public to on performance of Civil Servants | 47% | 50% | 55% | 60% | 65% | 70% |
|  | Outcome 3.1 Improved staffing in DLG | Staffing levels in LG | 55% | 75% | 75% | 85% | 85% | 90% |
| Objective 4: Deepen Decentralization and Citizen Participation in Local Development | Outcome 4.1 Increased local participation in development |  |  |  |  |  |  |  |
|  |  | % increase in the local revenue allocated to community development projects | 2% | 10% | 15% | 18% | 20% | 22% |
|  |  | % of citizens/clients accessing services from the service centres | 0.1% | 2% | 10% | 15% | 20% | 25% |
|  |  | No. of entities implementing e-government systems | 0.1% | 2% | 10% | 15% | 20% | 25% |
| Objective 5: Re- Engineer the Public Service Delivery Processes/ System to improve access to quality services | Outcome 5.1: Increased utilization of government services | No. of citizens accessing government services online | 0.1% | 2% | 10% | 15% | 20% | 25% |
|  | Intermediate Outcome 5.1.1 Increased access to government services | Percentage of commonly sought for services accessed at the Service Uganda Centres | 0.1% | 2% | 10% | 15% | 20% | 25% |
|  | Intermediate Outcome 5.1.2: Increased integration of service delivery E-Systems | DLG integrated with the data sharing and integration platform (UGhub) | 0.1% | 2% | 10% | 15% | 20% | 25% |
| Objective 6:. Strengthen institutional coordination and enforcement of polices, laws and regulatory frameworks | Outcome 6.1 Enhanced programme efficiency and effectiveness |  |  |  |  |  |  |  |

3.4.1 INTEGRATED TRANSPORT AND INFRASTRUCTURE

The Integrated Transport Infrastructure and Services Programme: aims to have a seamless, safe, inclusive and sustainable multi-modal transport system. The key focus areas are: diversification of the transport infrastructure by fast-tracking maintenance of existing transport infrastructure;; cost effective ways of infrastructure development and maintenance of the existing community access and urban roads

Table 13: Integrated transport and Infrastructure Development Programme Results and Targets

| Programme (a): | Outcome (a) | Indicator (c) | FY2024/25 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (BL) |  |  |  |  |  |  |
|  | Outcome 1.1: Increased access to services | Outcome Indicator 1: Average Travel time min/km (District Roads) | 2.4 | 2.4 | 2.4 | 2.2 | 2.2 | 2.2 |  |
| Programme Objective 1: To develop an inter-modal and seamless transport infrastructure and services |  | Outcome Indicator 2: Average Travel time min/km (Urban Roads) | 2.4 | 2.20 | 2.00 | 1.80 | 1.60 | 1.40 |  |
|  | Outcome 1.2: Increased stock of transport infrastructure | Outcome Indicator 1: Road Density by Area (Paved DUCAR) (km/1000sq km) | 8.65 | 11.96 | 12.38 | 12.94 | 14.06 | 13.44 |  |
| Objective 2: To strengthen transport asset management | Outcome 1: Longer service life of transport infrastructure | Outcome Indicator 1: Average Service life of transport infrastructure (tarmac roads yrs) | 20 | 20 | 20 | 20 | 20 | 20 |  |
|  |  | Outcome Indicator 2: Average Service life of transport infrastructure (first class murrum roads yrs) | 2 | 2 | 2 | 2 | 2 | 2 |  |
|  | Intermediate Outcome 1.1 Improved condition of transport infrastructure | Outcome Indicator 1: % of DUCAR in fair to good condition | 9% | 13% | 15% | 17% | 20% | 20% |  |
| Objective 3: To reduce the cost of transport infrastructure development and maintenance. | Outcome 1: Reduced cost of transport infrastructure development and maintenance | Average Unit cost of rehabilitation of transport infrastructure Ugx Bn/Km (Paved District roads) | 0.150 | 0.150 | 0.130 | 0.120 | 0.110 | 0.100 |  |
|  |  | Average Unit cost of rehabilitation of transport infrastructure Ugx Bn/Km (Unpaved District roads) | 0.130 | 0.120 | 0.100 | 0.100 | 0.900 | 0.800 |  |
|  |  | Average Unit cost of rehabilitation of transport infrastructure Ugx Bn (Community access roads) | 0.100 | 0.900 | 0.800 | 0.800 | 0.700 | 0.700 |  |
| Objective 4: To strengthen governance and management of the Programme | Intermediate Outcome 1.1: Improved transport planning and implementation capacity | % programme outputs achieved within the designated time frame | 100% | 100% | 100% | 100% | 100% | 100% |  |
| Sub-programme (a): | Intermediate Outcome (b) | Indicator (c) | FY2024/25 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  |  |  | (BL) |  |  |  |  |  |  |
|  | Intermediate Outcome 1.1: Reduced travel time | Intermediate Outcome Indicator 1: Average Travel time min/km (District Roads) | 2.4 | 2.4 | 2.4 | 2.2 | 2.2 | 2.2 |  |
| Sub-programme 1: |  | Intermediate Outcome Indicator 2: Average Travel time min/km (Urban Roads) | 2.4 | 2.20 | 2.00 | 1.80 | 1.60 | 1.40 |  |
|  | Intermediate Outcome 1.2: Increased stock of transport infrastructure | Intermediate Outcome Indicator 1: Road Density by Area (Paved DUCAR) (km/1000sq km) | 8.65 | 11.96 | 12.38 | 12.94 | 14.06 | 13.44 |  |
|  | Intermediate Outcome 2.1 : Reduced fatalities | Intermediate Outcome Indicator 1: Serious injuries on road transport | 650 | 600 | 500 | 400 | 300 | 200 |  |
|  | Intermediate Outcome 3.1 : Improved Integration of environment protection measures in transport infrastructure design and construction | Intermediate Outcome Indicator 1: Percentage of Transport Projects with Approved Environmental Impact Assessments (EIAs). |  |  |  |  |  |  |  |
|  | Intermediate Outcome 1.1 Improved condition of transport infrastructure | Intermediate Outcome Indicator 1: % of DUCAR in fair to good condition | 12% | 13% | 15% | 17% | 20% | 20% |  |
|  | Intermediate Outcome 1.1: Reduced Cost variations in projects | Intermediate Outcome Indicator 1: Average Percentage cost variation (Rehabilitation projects) | 5.50% | 5.5% | 5% | 4.00% | 3.00% | 2.00% |  |
|  | Intermediate Outcome 1.1: Improved transport planning and implementation capacity | % programme outputs achieved within the designated time frame | 80% | 95% | 95% | 100% | 100% | 100% |  |

3.4.2 GOVERNANCE AND SECURITY

The Governance and Security Programme: aims to ensure a peaceful and secure district, adhering to the rule of law. The key focus areas are: strengthening the fight against corruption and enforce proper accountability of government funds for improved service delivery

Table 14: Governance Development Programme Results and Targets

| Programme (a) | Outcome (b) | Indicator (c) | FY2024/25 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Enhance transparency, accountability, and anti-corruption systems to ensure effective governance; | Adherence to accountability standards and legal frameworks increased | Outcome Indicator 1: Number of Responses to Treasury Memoranda prepared and submitted | 1 | 2 | 2 | 2 | 2 | 2 |  |
|  |  | Outcome Indicator 2: Number of inspection reports produced | 1 | 2 | 4 | 4 | 4 | 4 |  |
|  | Prepare quarterly Internal audit reports for the District and submit them on time. | Outcome Indicator 3: Number of quarterly internal audit reports prepared and submitted on time. | 4 | 4 | 4 | 4 | 4 | 4 |  |
|  | Undertake Procurement Audits and submit them to relevant offices. | Outcome Indicator 4: Number of procurement audits conducted and reports submitted | 1 | 2 | 2 | 2 | 2 | 2 |  |
|  | Improved District Governance and Accountability | Outcome Indicator 1: Number of district risk assessment and management reports compiled | 0 | 1 | 2 | 2 | 2 | 2 |  |
| Sub-programme 1: Compliance and Accountability | Intermediate Outcome 1.1: Inspection and audit of completed and ongoing development projects | Number of Projects inspected/audited and reports produced | 6 | 8 | 8 | 8 | 8 | 8 |  |
|  | Intermediate Outcome 1.2: Production and submission of quarterly audit reports by due date | Number of quarterly audit reports prepared & submitted by due date | 4 | 4 | 4 | 4 | 4 | 4 |  |
|  | Intermediate Outcome 1.3: Preparation and submission of verification and follow up reports for audit recommendations | Number of Follow up and verification reports prepared and submitted to the office of the Internal auditor general. | 2 | 4 | 4 | 4 | 4 | 4 |  |
|  | Intermediate Outcome 1.4: Attendance of audit committee and other meetings attended. | Number of Audit committee meetings and other meetings attended. | 18 | 18 | 18 | 18 | 18 | 18 |  |
|  | Intermediate Outcome 1.5: Payment of monthly staff wages and Salaries | Months Staff salaries and wages paid up to date. | 12 | 12 | 12 | 12 | 12 | 12 |  |

| Sub-programme (a): | Intermediate Outcome (b) | Indicator (c) | FY2024/25 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Actors |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Number of Primary schools, health facilities, Sub counties and departments audited in financial year |  |  | 20 Sub Counties, 107 Primary schools, 12Sec schools, 27 H/Facilities 27 Feeder roads, 12 departments | 40P/schools, 12 Secondary schools, 10 feeder roads 15 Health facilities and 12departments | 40P/schools, 12 Secondary schools, 10 feeder roads 15 Health facilities and 12departments | 40P/schools, 12 Secondary schools, 10 feeder roads 15 Health facilities and 12departments | 40P/schools, 12 Secondary schools, 10 feeder roads 15 Health facilities and 12departments | 40P/schools, 12 Secondary schools, 10 feeder roads 15 Health facilities and 12departments |  |
| -Number of Value for money audits conducted |  |  | 0 | 1 | 1 | 1 | 1 | 1 |  |
| -Approved copy of Work plan and budget for the next financial produced. |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |
| -Number of Office equipment maintained |  |  | 3 computers, and 1 motor cycle | 3 computers, and 1 motor cycle | 3 computers, and 1 motor cycle | 3 computers, and 1 motor cycle | 3 computers, and 1 motor cycle | 3 computers, and 1 motor cycle |  |
| -Number of Printers, stationery, and other small office equipment and computer consumables procured. |  |  | 3 tonners 20 reams of paper and office equipment as required | 3 tonners 20 reams of paper and office equipment as required | 3 tonners 20 reams of paper and office equipment as required | 3 tonners 20 reams of paper and office equipment as required | 3 tonners 20 reams of paper and office equipment as required | 3 tonners 20 reams of paper and office equipment as required |  |
| -Number of Accountabilities, pension files, residual forms for arrears, pay change report forms, responses to audit queries and other documents verified |  |  | All as submitted | All as submitted | All as submitted | All as submitted | All as submitted | All as submitted |  |
| Evidence for submission of Annual work plan to audit committee and internal auditor general |  |  | 1 annual work plan | 1 annual work plan | 1 annual work plan | 1 annual work plan | 1 annual work plan | 1 annual work plan |  |

    - THE LEGISLATION, OVERSIGHT AND REPRESENTATION PROGRAMME

The Legislation, Oversight and Representation Programme: aims to ensure efficient legislation, representation, and accountability for results. The key focus areas are: increasing effectiveness and efficiency in legislative processes; improving alignment of plans to the budgets; improving the quality of representation at all levels; and strengthening institutional capacity

Table 15: THE LEGISLATION, OVERSIGHT AND REPRESENTATION PROGRAMME Development targets

| Programme (a): |  | Outcome (a) | Indicator (c) | FY2024/25 (BL) | FY2025/26 |  | FY2026/27 | FY2027/28 |  |  | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: To increase effectiveness and efficiency in legislative processes Accountability |  | Outcome 1.1: Improved legal framework for supporting District development | Number of ordinances and policies enacted and implemented | 2 | 3 |  | 4 | 4 |  |  | 4 | 4 | COUNCIL minutes and Attorney General |
|  |  |  | Number of council resolutions passed and implemented | 6 | 6 |  | 6 | 6 |  |  | 7 | 8 | COUNCIL minutes and Attorney General |
|  |  | Outcome 1.2: Efficient and effecting allocation and utilization of public resources | Number of district council recommendations on the budget implemented | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | COUNCIL minutes and Attorney General |
|  |  |  | Proportion of budget that is aligned to DDP1V | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | COUNCIL minutes and Attorney General |
|  |  |  | Number of audited reports reviewed by public accounts committee and submitted to District council for action | 4 | 4 |  | 4 | 4 |  |  | 4 | 4 | COUNCIL minutes and Attorney General, DPAC |
| Sub-programme (a): |  | Intermediate Outcome (b) | Indicator (c) | FY2024/25 (BL) | FY2025/26 |  | FY2026/27 | FY2027/28 |  |  | FY2028/29 | FY2029/30 | Data Source |
| Sub-programme 1: |  | Intermediate Outcome 1.1: | Implementation and overseeing of lawful council decision by technical staff and political leaders respectively | 4 | 4 |  | 4 | 4 |  |  | 4 | 4 | COUNCIL minutes and Attorney General |
|  |  |  | Reduction of unnecessary litigations against the district council | 20% | 15% |  | 10% | 5% |  |  | 5% | 5% |  |
| Intervention | Key Output |  | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |
|  |  |  |  | FY2025/26 |  | FY2026/27 | FY2027/28 | FY2028/29 |  |  |  | FY2029/30 |  |
| Intervention 1.1 Fast track legislative business at plenary and committee level | Ordinance enacted within 45 days |  | Output Indicator Number of ordinances enacted | 4 |  | 0 | 1 | 1 |  |  | 1 | 1 | Clerk to council |
| Intervention 1.2 Strengthen citizen participation in legislative processes | Citizen participation in the legislative process strengthened |  | Number of CSO engaged in legislative processes annually | 3 |  | 3 | 3 | 3 |  |  | 3 | 3 | Clerk to council |
| Conduct Committee Meetings to consider and incorporate citizens views on the proposed legislation | Collaboration between legislative actors enhanced |  | Hold meetings/ consultations with actors on relevant legislative matters | 4 |  | 4 | 4 | 4 |  | 4 |  | 4 | Clerk to council |
| Capacity of District and Local Councils in budgeting process strengthened | Effective and efficient allocation and utilization of public resources. |  | Proportion of District recommendations on the Budget implemented | 80% |  | 90% | 100% | 100% |  |  |  | 100% | District council, MOFPED |
| Train staff of district in budget analysis |  |  | Proportion of the Budget that is compliant to gender and equity requirements (%) | 67 |  | 70 | 72 |  | 75 |  |  | 77 | District council, MOFPED |
| Sensitize district councillors on Gender and Equity budgeting and planning compliance assessment checklist |  |  | Proportion of the Budget that is aligned to the DDPIV | 60 |  | 62 | 65 |  | 68 |  |  | 70 | District council, |
| Strengthen mechanisms for local council oversight function | Strengthened mechanisms for local council oversight function |  | Proportion of the Committee Reports on oversight adopted | 80 |  | 88 | 90 |  | 92 |  |  | 95 | District council, |
| Hold council sittings |  |  | Number of council meetings conducted | 6 |  | 6 | 6 | 6 |  |  |  | 6 | District council, |
| Hold committee sittings |  |  | Number of committee sittings held | 6 |  | 6 | 6 | 6 |  |  |  | 6 | District council, |
| Conduct quarterly monitoring and Oversight Field visits |  |  | Number of quarterly monitoring conducted | 4 |  | 4 | 4 | 4 |  |  |  | 4 | District council, |

### 3.5.10 Development Plan Implementation Programme.

Objective 5: Strengthen good governance, security, and the role of the state in development

The program aim at increasing the performance of the District Development Plan. The key focus areas are: enhancing development planning capacity; increasing domestic revenue generation; strengthening fiscal discipline, strengthening M&E systems to track progress; strengthening coordination of implementation; and strengthening statistical systems for development planning.

Table 16: Development Implementation Development targets

| Programme Objectives (Aligned to the LGDPIV Strategic Objective- LGDPIV Development Results) | Outcomes (a) | Outcome Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Strengthen Capacity for Evidence Based Development Planning across Government | Intermediate Outcome 1.1.2: Improved alignment of Plans to NDP | Level of alignment of Decentralized Plans to NDP | 90.0 | 90 | 90 | 100 |  | 100 | 100 | NPA |
|  | Intermediate Outcome 1.1.4: Increased use of research and statistics for development policy and planning across government and key private sector players | Percentage of NDP IV results informed by official statistics at goal and objective level. | 70 | 95 | 100 | 100 |  | 100 | 100 | MTR report |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 1.1.1.2: Build capacity in development planning and project formulation at all levels of government. | Output 1.1.1.2: Gender and equity responsive plans | Proportion of Sectors with gender and equity responsive plans | 70 | 75.00 | 75 | 85 |  | 95 | 100 | All Department |
|  | Output 1.1.1.1: Aligned Development Plans to NDP | Proportion of Sectors plans aligned to NDP | 95 | 98 | 100 | 100 |  | 100 | 100 | Planning Department |
| Strategic Intervention 1.1.1.1: Generate and use statistical data to inform Development plans at all levels | Output 1.1.1.2: Updated Administrative data and Statistics | Proportion of sectors with updated NDP Administrative data | 80 | 80.00 | 80 | 85 |  | 85 | 90 | Planning Department |
|  | Output 1.1.1.1: Quality data and Statistics Produced from nontraditional data sources | Number of Indicators compiled from Non -tradition data sources. | 0 | 3.00 | 4 | 6 |  | 6 | 12 | Planning Department |
|  | Output 1.1.1.1:Plan for National Statistical Development (PNSDIV) | Proportion of functional statistical units sectors | 75 | 80.00 | 80 | 90 |  | 95 | 95 | Planning Department |
| Programme Objectives (Aligned to the LGDPIV Strategic Objective- LGDPIV Development Results) | Outcomes (a) | Outcome Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 2: Enhance Resource Mobilization to finance the National Development Plan | Intermediate Outcome 2.1.1: Increased domestic revenue performance and budget self sufficiency | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 |  |
| Interventions | Key Outputs ( e) |  |  |  |  |  |  |  |  | Actors |
| Strategic Intervention 2.1.1.1: Strengthen Local Government Revenue Mobilization | Output 2.1.1.1: Local Government own source revenue growth | Percentage increase in local revenues year-over-year | 5 | 5.00 | 5 | 6 |  | 6 | 7 | Finance department |
|  |  | Percentage increase in own source revenue | 5 | 5.00 | 5 | 5 |  | 6 | 7 | Finance department |
| Programme Objectives (Aligned to the LGDPIV Strategic Objective- LGDPIV Development Results) | Outcomes (a) | Outcome Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 3: Strengthen Budgeting and Accountability systems | Outcome 3.1: Budget Credibility and Fiscal Discipline | Budget transparency index | 90 | 95.00 | 95 | 100 |  | 100 | 100 | MoFPED |
|  | Intermediate Outcome (b) | Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 3.1.1: Increased alignment of budget to the National Development Plan | Level of Compliance of the national Budget to NDPIV | 90 | 95.00 | 95 | 100 |  | 100 | 100 | CoC by MoFPED |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 3.1.1.1: Strengthen alignment of MDALGs budgets to NDP priorities during budget preparation and execution | Output 3.1.1.1: Credible budget | Percentage of budget released against originally approved budget | 106 | 108 | 108 | 110 |  | 110 | 110 | Finance Department |
| Strategic Intervention 3.1.1.1: Strengthen budget execution across government | Output 3.1.1.1: Efficiency and compliance in Public Procurement | Proportion of contracts completed on time | 98 | 98.00 | 98 | 100 |  | 100 | 100 | Contracts Committee |
|  | Output 3.1.1.1: Budget support services (in Budget execution) | Percentage of funds absorbed against funds released | 100 | 100 | 100 | 100 |  | 100 | 100 | Budget desk |
| Programme Objectives | Outcomes (a) | Outcome Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 4: Strengthen Oversight, Coordination and M&E across Government | Outcome 4.1: Improved delivery of the Plan | Percentage of NDP IV results on target | 95 | 95.00 | 100 | 100 |  | 100 | 100 | APR |
|  | Intermediate Outcome (b) | Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 4.1.2: Strengthened oversight function for the delivery of the plan | Level of Oversight across Government | 90 | 95.0 | 100 | 100 |  | 100 | 100 | APR |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 4.2.1.1: Strengthen the oversight function across government | Output 4.2.1.1: High quality, Specialized and impact driven audits | Level of implementation of Audit recommendations | 95 | 95 | 100 |  | 100 | 100 | 100 | Administration Department |
| Strategic Intervention 4.2.1.1: Strengthen the M&E function across government. | Output 4.2.1.1: Mid Term Review of NDPIV, Vision 2040 and End term evaluations conducted | No. Mid Term Review reports of NDPIV in Place | 0 | 0 | 0 |  | 1 | 0 | 0 | Planning Department |

3.5.13: Regional Development

Objective 5: Strengthen good governance, security, and the role of the state in development

The programme aims to minimize regional imbalances & inequalities and deepening of decentralization which supports realization of results of the Plan. By deepening decentralization, the programme will provide necessary structures and systems for effective implementation of the wealth creation initiatives such as PDM and EMYOOGA. By fostering local economic development, the programme empowers local authorities to generate revenue through localized taxation and asset management.

The goal of this programme is improved delivery of decentralized services and balanced regional development.

Table 46: Regional Development Programme Results and Targets

|  |  | Indicator | Baseline 2024/25 | Target 2025/26 | Target 2026/27 | Target 2027/28 | Target 2028/29 | Target 2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Enhance and Sustain Local Economic Development |  |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 1.1.1: Improved Access to Business Development Services at LG level | Number of Local Businesses formalized with URSB | 45 | 12 | 15 | 30 | 35 | 25 | TILED |
|  |  | Percentage of Local Businesses accessing business services online | 0 | 2 | 5 | 8 | 10 | 20 | TILED |
| Strategic Intervention 1.1.1.1: Implement the National LED Strategy | Output 1.1.1.1.1: LED Strategies developed | Percentage of LG LED strategies developed | 0 | 0 | 1 | 0 | 0 | 1 | TILED |
|  |  | Percentage of LLGs trained on Local Business Assessment | 0 | 0 | 1 | 0 | 0 | 1 | TILED |
| Strategic Intervention 1.1.1.2: Develop lower level PDPs to operationalize the National Physical Development Plan | Output 1.1.1.2.1: Integrated District and Local Physical Development Plans implemented | Number of District with approved integrated Physical Development Plans | 1 | 1 | 1 | 1 | 1 | 1 | Physical Planner |
|  |  | Number of Town councils and Rural Growth centers with approved integrated Physical Development Plans | 7 | 1 | 2 | 2 | 1 | 1 | Natural Resources Department |
|  |  | Number of Town councils benefiting from the physical planning Conditional Grant for the day-to-day operations | 0 | 1 | 2 | 2 | 1 | 1 | Natural Resources Department |
| Strategic Intervention 1.1.1.3: Integrate Physical Planning with LED | Output 1.1.1.3.1: Integrated Regional, District and Local Physical Development Plans implemented | Number of Regional Physical Development Plans developed | 0 | 1 | 0 | 0 | 0 | 0 | Natural Resources Department |
|  |  | Number of District Physical Development Plans developed | 0 | 0 | 0 | 0 | 0 | 1 | Natural Resources Department |
| Strategic Intervention 1.1.1.5: Link Enterprises to Local, Regional and International markets | Output 1.1.1.5.1: Increased access to markets | Number of local markets established | 1 | 0 | 1 | 0 | 1 | 0 | TILED |
|  |  | Number of Local SMEs linked to Local markets | 10 | 12 | 15 | 20 | 25 | 30 | TILED |
|  |  | Number of KMs of Community Access Roads constructed/rehabilitated | 35 | 25 | 30 | 34 | 40 | 54 | Works Department |
|  |  | Number of Agro processing facilities constructed | 2 | 0 | 1 | 1 | 0 | 1 | Production Department |
|  | Intermediate outcome 1.1.2: Increased productivity of the PDM SACCOs | Percentage Change in PDM SACCO portfolio | 12 | 15 | 20 | 25 | 30 | 50 | Production Department/ TLED |
| Strategic Intervention 1.1.2.1: Strengthen implementation of PDM Pillars & EMYOOGA | Output 1.1.2.1.1: PDM implementation coordination strengthened | Percentage of PDM households accessing PRF | 39 | 40 | 50 | 60 | 70 | 80 | Production Department/ TLED |
|  |  | Percentage of Parishes with Parish Action Plans | 100 | 100 | 100 | 100 | 100 | 100 | Production Department/ TLED/ DPU |
|  | Output 1.1.2.1.2: Governance and management structures for sustainability of PDM strengthened | Number of subsistence households accessing credit facilities (percentage) | 56.6 | 60 | 70 | 75 | 80 | 85 | Production Department/ TLED |
|  | Programme Objective 2: Enhance Local Revenue |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 2.1.1: Enhanced Contribution of Local Revenue to Local Government budgets | Percentage of the Local revenue contribution to the LG budget | 2 | 10 | 30 | 35 | 40 | 50 | Finance Department |
| Strategic Intervention 2.1.1.1: Implementation of Local Government Revenue Mobilisation Strategy | Output 2.1.1.1.1: Local revenue mobilized and generated | Amount of Local Revenue collected(000) | 616,580 | 960,780 | 964,000 | 1,000,000 | 1,500,000 | 2,00,000 | Finance Department |
|  |  | Number of new Local Revenue tax payers registered | 250 | 300 | 350 | 400 | 500 | 600 | Finance Department |
|  | Intermediate Outcome 2.1.2: Increased discretionary funding for LGs | Percentage of discretionary funding to all LGs | 100 | 100 | 100 | 100 | 100 | 100 | Finance Department |
| Strategic Intervention 2.1.2.1: Strengthen the implementation of the legal frameworks for Local Government funding | Output 2.1.2.1.1: Improved utilization of discretionary funds to LGs | Number of Advocacy engagements held for discretionary funding | 4 | 4 | 4 | 4 | 4 | 4 | Finance Department |
|  |  | Number of LG work plans adhering to the DDEG guidelines | 27 | 27 | 27 | 27 | 27 | 27 | Planning Department |
| Programme Objective 3: Strengthen affirmative action in lagging regions and refugee hosting communities |  |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 3.1.1 Enhanced livelihood support to the targeted Sub regions | Percentage of LLGs benefitting from Affirmative Action interventions | 60 | 65 | 70 | 75 | 80 | 85 | Planning Department |
| Strategic Intervention 3.1.1.1: Implement Social Economic Programs to address sub regional specific needs, Local Potential and Opportunities |  |  |  |  |  |  |  |  |  |
|  | Output 3.1.1.1.2 Households benefiting from Government Programs in affirmative action areas | Percentage of households benefitting from government programs/projects in affirmative action areas | 60 | 65 | 70 | 75 | 80 | 85 | Planning Department |
|  | Output 3.1.1.1.3 Community Social and Economic Infrastructure Projects in Affirmative action areas implemented | Number of safe and clean water points constructed in the targeted areas | 4 | 6 | 4 | 6 | 8 | 10 | Water Department |
|  |  | Number of education infrastructure constructed/rehabilitated in the targeted areas | 7 | 6 | 7 | 6 | 5 | 7 | Works and Technical Services department |
|  |  | Number of community markets established/improved in the targeted areas | 1 | 1 | 2 | 1 | 1 | 2 | TILED/ Roads and Engineering |
|  |  | KMs of community roads opened/rehabilitated in the targeted areas | 35 | 25 | 30 | 34 | 40 | 54 | Works and Technical Services department |
|  |  | Number of health infrastructure constructed/rehabilitated in the targeted areas | 5 | 4 | 5 | 4 | 4 | 5 | Health Department |
|  |  | Number of cultural infrastructure established/rehabilitated | 0 | 1 | 0 | 0 | 1 | 0 | TILED |
| Programme Objective 4: Strengthen policy, legal, institutional coordination, and regulatory frameworks |  |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 4.1.1: Enhanced LG capacity for utilizing statistics | Percentage coverage of LGs accessing the Data Analytics Systems | 0 | 0 | 100 | 0 | 0 | 100 | Planning Department |
| Strategic Intervention 4.1.1.1: Build LG Capacity for Generation and use of statistical data to inform Planning in LGs | Output 4.1.1.1.1: Increased use of statistical data in LG planning | LG Data Analytics Systems developed | 0 | 0 | 1 | 0 | 0 | 1 | Planning Department |
|  |  | Percentage of LGs using Data Analytics for planning | 50 | 60 | 70 | 80 | 90 | 100 | Planning Department |
|  |  | Percentage of LG Planning Units that are fully functional | 1 | 1 | 1 | 1 | 1 | 1 | Planning Department |
|  |  | Number of LGs producing Annual Statistical Abstracts | 1 | 1 | 1 | 1 | 1 | 1 | Planning Department |
|  | Intermediate Outcome 4.1.2 Improved Institutional performance | Level of implementation of District Development Plan (%) | 35 | 35 | 40 | 45 | 48 | 50 | Planning Department |
|  |  | Percentage of LLGs with approved development plans that are aligned to the NDP IV | 40 | 50 | 100 | 100 | 100 | 100 | Planning Department |
|  |  | Percentage of awarded procurement contracts to vulnerable groups | 0 | 10 | 10 | 10 | 10 | 10 | PDU |
|  | Result | Indicator |  |  |  |  |  |  |  |
| Strategic Intervention 4.1.2.1: Strengthen the functionality of Local Government structures | Output 4.1.2.1.1: Capacity of Local Government Leaders built | Number of LG Elected Leaders inducted | 0 | 0 | 55 | 0 | 0 | 0 | Statutory Bodies Department |
|  |  | Number of LG technical leaders trained in performance management | 0 | 0 | 55 | 0 | 0 | 0 | Statutory Bodies Department |
|  |  | Percentage of LG Councils with functional Committees, Statutory bodies and lawful resolutions | 100 | 100 | 100 | 100 | 100 | 100 | Statutory Bodies Department |
|  |  | Percentage of LG Councils receiving and scrutinizing reports of Statutory Bodies | 100 | 100 | 100 | 100 | 100 | 100 | Statutory Bodies Department |
|  | Output 4.1.2.1.2: Statutory Bodies in Local Governments (Land Boards, LGPAC) strengthened | Percentage of fully constituted Council Committees | 100 | 100 | 100 | 100 | 100 | 100 | PPDU |
| Strategic Intervention 4.1.2.2: Strengthen Human Resource function in Local Governments | Output 4.1.2.2.1: Performance management improved in Local Governments | No. of LGs supported to develop performance improvement plans | 1 | 1 | 1 | 1 | 1 | 1 | Planning Department |
|  |  | No. of LLGs inspected for compliance to laws, regulations and guidelines | 27 | 27 | 27 | 27 | 27 | 27 | Planning Department |
|  | Output 4.1.2.2.2: Employee Productivity in Local Governments improved | Percentage of approved LG staff positions filled. | 57 | 60 | 65 | 70 | 75 | 80 | Administration Department |
|  |  | Percentage of LG staff meeting performance rating of at least 70 percent. | 80 | 85 | 88 | 90 | 90 | 94 | Administration Department |
|  |  | Percentage of technical LG staff benefitting from capacity building trainings/ mentorship that lasted at least one week | 2 | 5 | 10 | 15 | 18 | 20 | Administration Department |
|  | Result | Indicator |  |  |  |  |  |  |  |
| Strategic Intervention 4.1.2.3: Coordinate policy, planning, implementation and reporting | Output 4.1.2.3.1: Service delivery in Local Governments coordinated | Number of coordination engagements with key LG stakeholders held | 4 | 8 | 6 | 4 | 6 | 6 | Administration Department |
|  |  | Number of Policy and Legal Frameworks developed and reviewed | 0 | 2 | 2 | 2 | 2 | 2 | Administration Department |
|  |  | Number of LGs with functional HIV/AIDS committees | 1 | 1 | 1 | 1 | 1 | 1 | Health Department |
|  |  | Percentage of LGs with functional Nutrition Committees | 1 | 1 | 1 | 1 | 1 | 1 | Health Department |
|  | Output 4.1.2.3.2: Finance and Administration | Number of Internal Audit reports prepared and submitted to MoLG Management | 4 | 4 | 4 | 4 | 4 | 4 | Audit Department |
|  |  | Updated asset register | 1 | 1 | 1 | 1 | 1 | 1 | Finance Department |
|  |  | No. of financial reports prepared and submitted to relevant authorities | 2 | 2 | 2 | 2 | 2 | 2 | Finance Department |
|  |  | No. of Management meetings held | 4 | 4 | 4 | 4 | 4 | 4 | Audit Department |
|  | Output 4.1.2.3.3: MoLG and LG offices constructed and retooled | Number of Lower Local Government Administration Offices constructed | 0 | 3 | 1 | 1 | 1 | 1 | Administration Department |

CHAPTER FOUR: FINANCING FRAMEWORK AND RESOURCE MOBILISATION STRATEGY

Overview

Bundibugyo district has a number of revenue sources that finance its budget which includes Locally Raised Revenue, Other Government Transfers, Conditional Government Transfers, Donors, and some off-budget support.

4.1 Financing Framework

Bundibugyo district requires a total of Uganda Shillings 257,389,207,290 to implement its development plan over the period 2025/2026 -2029/2030. This figure among others includes routine operation costs like wages, recurrent non-wage, operation of statutory bodies and councils. The plan shall be financed through a combination of Central Government Transfers, locally raised revenues and other sources of funding like the Donors.

# Table: 17 Financing Framework

# The table shows different sources of funding for the next five years . it includes how much shall be contributed by the central government transfers, Local Revenue and Eternal Financing.

| Sources of Financing | Total Contributions |  |  |  |  | GRAND Contributions | (%) Share |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |  | by source of financing |
| 1) Central Government Contributions[1] | 49,623,436,000 | 49,623,436,000 | 49,623,436,000 | 49,623,436,000 | 49,623,436,000 | 248,117,180,000 | 96 |
| 2) Locally Raised Revenue (contributions Member LGs)[2] | 960,802,000 | 1,056,882,200 | 1,162,570,420 | 1,278,827,462 | 1,406,710,208 | 5,865,792,290 | 3 |
| 3) Development Partners / Donors | 681,247,000 | 681,247,000 | 681,247,000 | 681,247,000 | 681,247,000 | 3,406,235,000 | 1 |
| Total | 51,265,485,000 | 51,361,565,200 | 51,467,253,420 | 51,583,510,462 | 51,711,393,208 | 257,389,207,290 | 100 |

4.2 Costs of the Plan Period (2025/26-2029/30)

The total cost of the plan is UGX 257,389,207,290 and will be used to implement different interventions in realization of the plan goals and mission and Vision of Bundibugyo district. This table gives Resources allocation for the next Five years starting with the base year and finally for the whole of the development cycle. It has details of the interventions

Table: 18 Summary Costs of the Interventions under Agro- Industrialization Cost of the program

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 1: Sustainably increase production and productivity in agriculture |  |  |  |  |  |  |
| Intervention |  |  |  |  |  |  |
| 1.1 Increase the uptake of fertilizers | 486,190 | 80,000 | 88,000 | 96,800 | 105,680 | 115,710 |
| 1.2 Produce, multiply and distribute quality seed and inputs | 608,000 | 100,000 | 110,000 | 121,000 | 132,000 | 145,000 |
| 1.3 Strategically invest in the fisheries sub-sector and aquaculture development | 608,000 | 100,000 | 110,000 | 121,000 | 132,000 | 145,000 |
| 1.4 Support to large scale commercial farming entities | 608,000 | 100,000 | 110,000 | 121,000 | 132,000 | 145,000 |
| 1.5 Increase access to and use of water for agricultural production | 2,424,000 | 400,000 | 440,000 | 484,000 | 524,000 | 576,000 |
| 1.6 Strengthen farmer organizations and cooperatives ecosystems | 608,000 | 100,000 | 110,000 | 121,000 | 132,000 | 145,000 |
| 1.7 Strengthen pest, vector, disease management and control | 608,000 | 100,000 | 110,000 | 121,000 | 132,000 | 145,000 |
| 1.8 Strengthen the agricultural extension system | 9,952,823 | 1,630,247 | 1,793,272 | 1,972,699 | 2,169,859 | 2,386845 |
| 1.9 Promote climate adaptation and mitigation practices | 2,424,000 | 400,000 | 440,000 | 484,000 | 524,000 | 576,000 |
| Strategic Objective 2: Improve harvesting, post-harvest handling and storage |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 2.1 Provide appropriate harvest, post-harvest handling and storage technologies | 25,000,000 | 15,000,000 |  |  | 10,000,000 |  |
| 2.2 Ensure compliance to standards at harvesting, post-harvest handling and storage | 608,000 | 100,000 | 110,000 | 121,000 | 132,000 | 145,000 |
| Strategic Objective 3: Develop, operationalize and optimize value addition infrastructure |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 3.1 Establish appropriate value addition infrastructure ( ie, Cocoa processing factory) | 25,000,000 | 15,000,000 |  |  | 10,000,000 |  |
| Strategic Objective 4: Increase market access and competitiveness of agricultural products in domestic and international markets |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 4.1 Establish and maintain appropriate market infrastructure | 486,190 | 80,000 | 88,000 | 96,800 | 105,680 | 115,710 |
| Strategic Objective 5: Increase access to agricultural finance and insurance |  |  |  |  |  |  |
| PARISH DEVELOPMENT MODEL |  | 130,000,000 | 130,000,000 | 130,000,000 | 130,000,000 | 130,000,000 |

Table 19: Summary Costs of the Interventions of Tourism development programme.

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Promote Domestic and inbound Tourism |  |  |  |  |  |  |
| Strategic Intervention 1.1 Promote domestic and inbound tourism | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Objective 2: Increase the stock and quality of tourism infrastructure |  |  |  |  |  |  |
| Strategic Intervention 2.1: Increase the stock and quality of tourism infrastructure; | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Objective 3: Conserve, Develop, improve and diversify tourism products |  |  |  |  |  |  |
| Strategic Intervention 3.2: Develop, Conserve and diversify tourism products and services; | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Objective 4: Develop skilled personnel along the tourism value chain |  |  |  |  |  |  |
| Strategic Intervention 4.1: Address skills and capacity gaps in the tourism and hospitality industry | 5,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 |
| Objective 5: Enhance enforcement of regulation and coordination of the tourism industry | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Strategic Intervention 5.3: Sustain security and safety of tourists and tourist attractions | 6,000 | 1,500 | 1,500 | 1,500 | 1,500 | 1,500 |
| TOTAL | 51,000 | 10,500 | 10,500 | 10,500 | 10,500 | 10,500 |

Table 20 : Summary Costs of the Interventions of Natural resources, Environment, Climate change, Land and Water.

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 3: Protect, restore and add value to forests and wetlands |  |  |  |  |  |  |
| Conduct public awareness on environment/ wetlands, climate change, Disaster risk reduction, weather information dissemination, renewable energy through radio talk show, seminars and meetings | 107,500 | 21,500 | 21,500 | 21,500 | 21,500 | 21,500 |
| Strategic Intervention 3.2: Upscale commercial forestry including bamboo and exploit opportunities along its entire value chain so as to leverage on its economic benefits and to increase resilience to climatic changes; | 94,500 | 18,900 | 18,900 | 18,900 | 18,900 | 18,900 |
| Strategic Intervention 2.2.1: Protect and increase the wetland cover | 147,500 | 29,500 | 29,500 | 29,500 | 29,500 | 29,500 |
| Strategic Intervention 2.2.3: Strengthen regulation and enforcement against environmental pollution and degradation | 235,000 | 47,000 | 47,000 | 47,000 | 47,000 | 47,000 |
| Strategic Intervention 2.2.4: Promote biodiversity conservation | 75,000 | 15,000 | 15,000 | 15,000 | 15,000 | 15,000 |
| Strategic Intervention 4.3: Promote sustainable biodiversity management in within and outside protected areas | 35,000 | 7,000 | 7,000 | 7,000 | 7,000 | 7,000 |
| Strategic intervention 4.4 Land use planning and management strengthened- physical planning | 192,500 | 38,500 | 38,500 | 38,500 | 38,500 | 38,500 |
| TOTAL | 887,000 | 177,000 | 177,000 | 177,000 | 177,000 | 177,000 |

Table 21: Summary Costs of the Interventions of human capital development.

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1: To improve the foundation of human capital development |  |  |  |  |  |  |
| 1. Improve access and equity of pre-primary education | 5,581,980 | 1,116,396 | 1,116,396 | 1,116,396 | 1,116,396 | 1,116,396 |
| 2 Institutionalize Pre-primary teacher training at public teacher training institutions | 995,000 | 199,000 | 199,000 | 199,000 | 199,000 | 199,000 |
| 3 Enforce the regulatory and quality assurance system for provision of ECC |  | 42.648 | 42.648 | 42.648 | 42.648 | 42.648 |
| Strategic Intervention 4: Improve Physical and Cognitive development of children below 8 years |  | 12.177 | 3.885 | 12.1 | 12.943 | 13.587 |
| Strategic Intervention 5: Promote optimal Maternal, Infant, Young child, Adolescent and Elderly Nutrition Practices |  | 300 | 315 | 331 | 347 | 365 |
| Strategic Intervention 6: Increase access to immunization against childhood diseases |  | 113.316 | 119 | 125 | 131 | 138 |
| Strategic Intervention 8: Strengthen the family Unit to reduce domestic violence, child deprivation, abuse and child labor |  | 21.9 | 20.12 | 20.874 | 21.66 | 22.497 |
| 1.9 Equip all lagging schools to meet BRMS | 2,375,000 | 475,000 | 475,000 | 475,000 | 475,000 | 475,000 |
| 1.11 Improve the inclusivity in teaching and learning environments | 463.298 | 5.050 | 114.562 | 114.562 | 114.562 | 114.562 |
| 1.12 Strengthen support services (guidance and counselling, child protection, school health, nutrition services) to enable retention and completion at all | 122.790 | 24.558 | 24.558 | 24.558 | 24.558 | 24.558 |
| 1.14. Enforce the regulatory, assessment and quality assurance system of primary and secondary schools | 240,000 | 48,000 | 48,000 | 48,000 | 48,000 | 48,000 |
| Programme Objective 2: To produce appropriate knowledgeable, skilled and ethical labor force (with strong emphasis on science and technology; STEI/STEM in education and TVET) |  |  |  |  |  |  |
| 2.5 Increase access to TVET training in skills scarce TVET programmes to reverse the currently inverted skills triangle | 70,000 | 10,000 | 10,000 | 10,000 | 10,000 | 10,000 |
| Objective 3: To improve population health, safety and management; Access to safe water sanitation and hygiene services. |  |  |  |  |  |  |
| Strategic Intervention: Strategic Intervention 1: Increase community ownership, access and utilization of health promotion, environmental health and community health services | 53.757 | 9 | 10.47 | 11.028 | 11.346 | 11.913 |
| Strategic Intervention 3: Prevent and control Non-Communicable diseases with specific focus on cancer, cardiovascular, genetic, renal, endocrine, mental, trauma and malnutrition across all age groups. | 19.34 | 3.5 | 3.675 | 3.859 | 4.052 | 4.254 |
| Strategic Intervention 4: Improve maternal, neonatal, child and adolescent health services at all levels of care | 165.769 | 30 | 31.5 | 33.075 | 34.729 | 36.465 |
| Strategic intervention 5. : Access to Sexual and Reproductive Health (SRH) information and services increased | 16.35 | 3 | 3.15 | 3.08 | 3.473 | 3.647 |
| Strategic Intervention 6: Improve curative, palliative, rehabilitative and geriatric care services | 2.763 | 0.5 | 0.525 | 0.551 | 0.579 | 0.608 |
| Strategic Intervention 7: Improve the functionality of the health system to deliver quality and affordable preventive, promotive, curative and palliative healthcare services. | 24086.172 | 4358.99 | 4576.94 | 4805.786 | 5046.076 | 5298.380 |
| Objective 3: To improve population health, safety and management; Access to safe water sanitation and hygiene services. |  |  |  |  |  |  |
| Strategic Intervention 8a: Increase investment in water supply and sanitation infrastructure to increase service in underserved communities in urban, rural and refugee settlements | 6807.678 | 1240 | 1302 | 1367.1 | 1435.454 | 1463.124 |
| Strategic Intervention 8b: Increase rehabilitation and expansion of existing WASH infrastructure. | 3163.471 | 576.5 | 605.325 | 635.591 | 667.369 | 678.686 |
| Strategic Intervention 8c: Increase investment in water supply and sanitation infrastructure to increase service in underserved communities in rural, urban, and refugee settlements. | 924.037 | 165.6 | 182.88 | 182.573 | 191.701 | 201.283 |
| Strategic Intervention 9: Strengthen nutrition coordination and partnerships for WASH-Nutrition | 89.451 | 13 | 13.65 | 16.41 | 22.63 | 23.761 |
| Strategic Intervention 10: Increase investment in water supply and sanitation infrastructure to increase service in underserved communities in rural, urban, and refugee settlements. | 61.586 | 8.2 | 10.4 | 10.92 | 11.466 | 20.6 |
| Programme Objective 4: To promote decent work and productive employment |  |  |  |  |  |  |
| Strategic Intervention 1: Strengthen compliance with labor standards and rights | 60,000 | 10,000 | 11,000 | 12,000 | 13,000 | 14,000 |
| Programme Objective 5: Reduce vulnerability, gender inequality and inequity along the lifecycle | 25,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 |
| Strategic Intervention 1 : Expand scope and coverage of livelihood enhancement and economic empowerment programmes for Youth, Women, Older Persons, PWDs and ethnic minorities | 35,000 | 70,000 | 70,000 | 70,000 | 70,000 | 70,000 |
| Strategic Intervention 3 : Provide holistic social care and support (assistance) services to vulnerable groups | 15,000 | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 |
| Strategic Intervention 5: Promote gender equality and equity responsive planning, budgeting and implementation | 25,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 |
| TOTAL |  |  |  |  |  |  |

Table 22: Summary Costs of the Interventions of private sector development.

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Sustainably lower the cost of financing |  |  |  |  |  |  |
| Intervention 1.1.1.1: Inspecting businesses, conducting market surveillance and sensitizing business operators about existing regulatory frame work | 10,000 | 1,000 | 200 | 1,000 | 200 | 1,000 |
| 1.1.1.2 Profiling of MSMEs ( Micro small & medium enterprises in the district | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Formation and registration of farmers groups | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Intervention: 1.1.2.3 Promote the integration of environmental, social, and governance (ESG) criteria in financial services to support sustainable development goals | 50 | 0 | 15 | 20 | 5 | 10 |
| Intervention 1.1.2.4 Preparation of annual financial reports, annual work plans and budgets, annual and quarterly performance reports, reports, procurement plan and PFB | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Intervnetion:1.1.2.5 Strengthen the financial inclusion pillar of PDM | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Intervention 1.1.2.6 Profiling of MSMEs ( Micro small & medium enterprises in the district | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Intervention 1.1.4.1. Monitoring and support supervision of cooperatives societies | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Intervention: 2.1.1.1. Enforcement of weights and measures Act | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Objective 3: Support capacity development for private sector institutions and organizations. |  |  |  |  |  |  |
| Intervention 3.1.1.1. Profiling of MSMEs (Micro small & medium enterprises in the district. | 10,000 | 2,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| Intervention 3.1.2.3. 3.1.3.1. Promote formalization and business registration | 5,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 |
| TOTAL | 60,000 | 16,000 | 16,000 | 16,000 | 16,000 | 16,000 |

TABLE 23; Summary Costs of the Interventions of INTEGRATED TRANSPORT AND INFRASTRUCTURE

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 1: To develop an inter-modal and seamless transport infrastructure and service |  |  |  |  |  |  |
| Interventions: |  |  |  |  |  |  |
| 1.1: Construct and upgrade strategic transport infrastructure. | 2,526,595,635 | 413,850,000 | 455,235,000 | 500,758,500 | 550,834,350 | 605,917,785 |
| 1.2 Increase capacity of existing transport infrastructure and services; | 842,198,545 | 137,950,000 | 151,745,000 | 166,919,500 | 183,611,450 | 201,972,595 |
| 1.3 Enhance transport safety; | 421,099,273 | 68,975,000 | 75,872,500 | 83,459,750 | 91,805,725 | 100,986,298 |
| 1.4: To strengthen transport system resilience to climate change and natural disasters with compliance to environmental and social safeguards. | 168,439,709 | 27,590,000 | 30,349,000 | 33,383,900 | 36,722,290 | 40,394,519 |
| Strategic Objective 2: To strengthen transport asset management |  |  |  |  |  |  |
| The Interventions |  |  |  |  |  |  |
| 2.1 Rehabilitate and maintain transport infrastructure. | 1,010,638,254 | 165,540,000 | 182,094,000 | 200,303,400 | 220,333,740 | 242,367,114 |
| 2.2 Develop and maintain transport infrastructure and services management information systems. | 168,439,709 | 27,590,000 | 30,349,000 | 33,383,900 | 36,722,290 | 40,394,519 |
| 2.3 Strengthen mechanical engineering services. | 842,198,545 | 137,950,000 | 151,745,000 | 166,919,500 | 183,611,450 | 201,972,595 |
| Strategic Objective 3: To reduce the cost of transport infrastructure development and maintenance. |  |  |  |  |  |  |
| The Interventions | - |  | - | - | - | - |
| 3.1 Implement cost-efficient technologies for provision of transport infrastructure and services | 1,010,638,254 | 165,540,000 | 182,094,000 | 200,303,400 | 220,333,740 | 242,367,114 |
| 3.2 Strengthen local construction capacity | 421,099,273 | 68,975,000 | 75,872,500 | 83,459,750 | 91,805,725 | 100,986,298 |
| 3.3 Adopt new technologies and innovations in transport | 842,198,545 | 137,950,000 | 151,745,000 | 166,919,500 | 183,611,450 | 201,972,595 |
| Strategic Objective 4: To strengthen governance and management of the Programme |  |  |  |  |  |  |
| The Interventions |  |  |  |  |  |  |
| 4.1 Strengthen planning, supervision, monitoring, evaluation, coordination and human resource capacity of the Programme | 168,439,709 | 27,590,000 | 30,349,000 | 33,383,900 | 36,722,290 | 40,394,519 |

| PUBLIC SECTOR TRANSFORMATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| Strategic Objective 1: Achieve higher household incomes and employment for sustainable socio-economic transformation. |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 1.1 Enforce compliance to Laws, regulations, guidelines and processes | 150,0000 | 20,000 | 25,000 | 30,000 | 35,000 | 40,000 |
| 1.2 Strengthen public sector performance management initiatives | 157,077 | 20,000 | 25,000 | 30,000 | 35,000 | 40,000 |
| 1.3 Strengthen implementation of service delivery standards and feedback mechanisms | 30,000 | 5,000 | 5,500 | 6,000 | 6,500 | 7,000 |
| 1.4 Strengthen recruitment in DLG | 27,000 | 3,500 | 4,500 | 5,500 | 6,500 | 7,000 |
| Strategic Objective 2 Strengthen human resource management for improved service delivery |  |  |  |  |  |  |
| The Interventions |  |  |  |  |  |  |
| 2.2 Undertake nurturing of the Civil Service |  |  |  |  |  |  |
| 2.3 Implement pay reform across the District service | 86,443,397 | 17,148,679 | 17,248,679 | 17,348,679 | 17,348,679 | 17348679 |
| 2.4 Strengthen human resource management in government |  |  |  |  |  |  |
| 2.5 Operationalize Public Service Negotiating, Consultative and Disputes Settlement Machinery |  | 2000 |  |  |  |  |
| Strategic Objective 3: Deepen Decentralization and Citizen Participation in Local Development |  |  |  |  |  |  |
| The Interventions |  |  |  |  |  |  |
| 3.1 Build LG decentralization and self-reliance capacity | 30,000 | 5,000 | 5,500 | 6,000 | 6,500 | 7,000 |
| Strategic Objective 4: Strengthen Government Institutions in Records, Archives and Information Management |  |  |  |  |  |  |
| The Interventions |  |  |  |  |  |  |
| 4.1 Enforce adoption and implementation of e-government services | 30,000 | 5,000 | 5,500 | 6,000 | 6,500 | 7,000 |
| 4.2 Strengthen Government Institutions in Records, Archives and Information Management | 30,000 | 5,000 | 5,500 | 6,000 | 6,500 | 7,000 |
| 4.3 Improve access to timely, accurate and comprehensible public information | 30,000 | 5,000 | 5,500 | 6,000 | 6,500 | 7,000 |
| 4.4 Re – engineer and automate key government processes. | 30,000 | 5,000 | 5,500 | 6,000 | 6,500 | 7,000 |
| Strategic Objective 5: Strengthen institutional coordination and enforcement of polices, laws and regulatory frameworks |  |  |  |  |  |  |
| The Interventions |  |  |  |  |  |  |
| 5.1 Enhance Institutional Coordination and Administrative Efficiency | 157,744 | 28,044 | 30,300 | 30,600 | 30,600 | 34,200 |
| 5.2 |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

Table 25: Summary Costs of the Interventions Development plan implementation.

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 1: Strengthen Capacity for Evidence Based Development Planning across Government |  |  |  |  |  |  |
| Strategic Intervention 1.1.1.2: Build capacity in development planning and project formulation at all levels of government. | 40,000 | 8,000 | 8,000 | 8,000 | 8,000 | 8,000 |
| Strategic Intervention 1.1.1.1: Generate and use statistical data to inform Development plans at all levels | 35,000 | 7,000 | 7,000 | 7,000 | 7,000 | 7,000 |
| Programme Objective 3: Strengthen Budgeting and Accountability systems |  |  |  |  |  |  |
| Strategic Intervention 3.1.1.1: Strengthen alignment of MDALGs budgets to NDP priorities during budget preparation and execution | 70,000 | 14,000 | 14,000 | 14,000 | 14,000 | 14,000 |
| Strategic Intervention 3.1.1.1: Strengthen budget execution across government | 95,935 | 19,187, | 19,187, | 19,187, | 19,187, | 19,187, |
| Programme Objective 4: Strengthen Oversight, Coordination and M&E across Government |  |  |  |  |  |  |
| Strategic Intervention 4.2.1.1: Strengthen the oversight function across government | 119,860 | 23,972, | 23,972, | 23,972, | 23,972, | 23,972, |
| Strategic Intervention 4.2.1.1: Strengthen the M&E function across government. | 50,000 | 10,000 | 10,000 | 10,000 | 10,000 | 10,000 |
| TOTAL | 410,795 | 82,159 | 82,159 | 82,159 | 82,159 | 82,159 |

Table 26: Summary Costs of the Interventions Regional Development

|  | Total Cost (Millions) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Enhance and Sustain Local Economic Development |  |  |  |  |  |  |
| Strategic Intervention 1.1.1.1: Implement the National LED Strategy | 10 | 2 | 2 | 2 | 2 | 2 |
| Strategic Intervention 1.1.1.2: Develop lower level PDPs to operationalize the National Physical Development Plan | 5 | 1 | 1 | 1 | 1 | 1 |
| Strategic Intervention 1.1.1.3: Integrate Physical Planning with LED | 10 | 2 | 2 | 2 | 2 | 2 |
| Strategic Intervention 1.1.1.5: Link Enterprises to Local, Regional and International markets | 50 | 10 | 10 | 10 | 10 | 10 |
| Strategic Intervention 1.1.2.1: Strengthen implementation of PDM Pillars & EMYOOGA | 100 | 20 | 20 | 20 | 20 | 20 |
| Strategic Intervention 2.1.2.1: Strengthen the implementation of the legal frameworks for Local Government funding | 10 | 2 | 2 | 2 | 2 | 2 |
| Programme Objective 3: Strengthen affirmative action in lagging regions and refugee hosting communities |  |  |  |  |  |  |
| Strategic Intervention 3.1.1.1: Implement Social Economic Programs to address sub regional specific needs, Local Potential and Opportunities | 20 | 4 | 4 | 4 | 4 | 4 |
| Programme Objective 4: Strengthen policy, legal, institutional coordination, and regulatory frameworks |  |  |  |  |  |  |
| Strategic Intervention 4.1.1.1: Build LG Capacity for Generation and use of statistical data to inform Planning in LGs | 100 | 20 | 20 | 20 | 20 | 20 |
| Strategic Intervention 4.1.2.1: Strengthen the functionality of Local Government structures | 20 | 4 | 4 | 4 | 4 | 4 |
| Strategic Intervention 4.1.2.2: Strengthen Human Resource function in Local Governments | 5 | 1 | 1 | 1 | 1 | 1 |
| Strategic Intervention 4.1.2.3: Coordinate policy, planning, implementation and reporting | 10 | 2 | 2 | 2 | 2 | 2 |
| TOTAL | 345 | 70 | 70 | 70 | 70 | 70 |

Table 27: List of the projects under AGRO- INDUSTRIALISATION

| Projects | Total (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Project 1: Establishment of a cocoa factory | 25,000,000 | 15,000,000 |  |  | 10,000,000 |  |
| Project 2: Establishment and equipping of an integrated Agricultural Laboratory | 5,000,000 |  | 5,000,000 |  |  |  |
| Project 3: Establishment of 1 cattle holding ground | 21,000,000 |  | 1,000,000 |  | 1,000,000 |  |
| Project 4: Establishment of cattle crushes | 1,500,000 | 500,000 | 500,000 |  |  | 500,000 |
| Project 5: Establishment 1 multipurpose water dam | 1,900,000 |  | 900,000 |  |  | 1,000,000 |
| Project6: Establishment of Crop/livestock/fisheries demonstration sites | 2,500,000 | 500,000 | 500,000 | 500,000 | 500,000 | 500,000 |
| Project7: Establishment of on farm crop trials and multiplication centres | 2,500,000 | 500,000 | 500,000 | 500,000 | 500,000 | 500,000 |
| Project8: Rehabilitation of 15 Farm access road chokes | TBD |  |  |  |  |  |
| Project9s: Establishment of small scale and micro scale irrigation schemes | TBD |  |  |  |  |  |
| Project10 Establishment of Fish Hatchery | 1,500,000 |  | 700,000 |  | 800,000 |  |
| Project11: Provision of improved planting/stocking materials | 2,500,000 | 500,000 | 500,000 | 500,000 | 500,000 | 500,000 |
| Project12: Establishment value addition | 2,500,000 | 500,000 | 500,000 | 500,000 | 500,000 | 500,000 |
| Project13: SLM Activities | 2,500,000 | 500,000 | 500,000 | 500,000 | 500,000 | 500,000 |
| Project14: Establishment of horticultural nursery |  | 500,000 |  | 500,000 |  |  |
| Project 15: EXPANSION OF BUSUNGA BOARDER MARKET | 1,000,000 |  | 500,000,000 | 500,000,000 |  |  |
| Project 16; CONSTRUCTION OF BUNDIBUGYO MPANGA MARKET | 1,500,000 |  | 500,000,000 | 500,000,000 | 500,000 |  |
| Project 17: CONSTRUCTION OF NYAHUKA MARKET | 1,500,000 |  | 500,000,000 | 500,000,000 | 500,000 |  |
| Project 18: CONSTRUCTION OF NYABUGESERA MARKET | 1,500,000 |  | 500,000,000 | 500,000,000 | 500,000 |  |
| Project 19: CONSTRUCTION OF KIKYO MARKET | 1,500,000 |  | 500,000,000 | 500,000,000 | 500,000 |  |
| Project 20: CONSTRUCTION OF KANYAMWIRIMA MARKET | 1,500,000 |  | 500,000,000 | 500,000,000 | 500,000 |  |

Table 28 List of projects under NATURAL RESOURCES

| Projects | Total (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Project 1: Establish tree nurseries | 25.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 |
| Project 2: land titling | 52.000.0000 | 10.500.0000 | 10.500.0000 | 10.500.0000 | 10.500.0000 | 10.500.000 |
| Project 3: procure tree seedlings | UNHCR,WWF, | 1000 | 1000 | 1000 | 1000 | 10000 |
| Project 4: mark/demarcate wetlands | 25.000,000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 |
| Project 5: Restore degraded river banks and hills | 25.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 |
| Project 6: develop physical development plans for all Town Councils | 5.000.000 | 1.000.000 | 1.000.000 | 1.000.000 | 1.000.000 | 1.000.000 |
| TOTAL | 107.000.0000 | 21.500.000 |  | 16.500.000 | 16.500.000 | 16.500.000 |

HUMAN CAPITAL DEVELOPMENT

4.3 Costs of Projects

| Total Cost for the Plan Period (UGX in Million) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Projects | Total (000) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| Project 1:Completion of the Maternity ward Complex at Nyahuka HC IV ( 3 storey structure) plus equipping it | 3,200,000 | 1,000,0000,000 | 700,000,000 | 700,000,000 | 600,000,0000 | 200,000,000 |
| Project 2: Construction/establishment of a health centre III in Ntotoro sub-county(Completion-Phase II) | 700,000 | 700,000,000 |  |  |  |  |
| Project 3: Construction of staff house at the newly established HC III in Ntotoro Sub-County | 190,000 |  | 190,000,000 |  |  |  |
| Project 4: Equipping of the newly established HC III | 250,000 | 250,000,000 |  |  |  |  |
| Project 5:Re-Construction of Kayenje HC II with upgrade to HC III( Busengerwa) | 1,000,000 | 250,000,000 | 250,000,000 | 500,000,000 |  |  |
| Project 6: Renovation of Bundibugyo General Hospital | 3,000,000 | 500,000,000 | 500,000,000 | 1,000,000,000 | 1,000,000,000 |  |
| Project 7:Construction and equipping of In-Patient Wards at Butama HC III, Kisubba HC III and Kakuka HC III | 2,500,000 | 500,000,000 | 500,000,000 | 500,000,000 | 500,000,000 | 500,000,000 |
| Project 8: Establishment of HC III in 5 sub-counties without any HC ( Ndugutu, Buganikere, Mabere, Mbatya, Kagugu, ) | 6,000,000 |  |  |  |  |  |
| Project 9: Upgrading of HC IIs to HC III( Kasulenge, Bundingoma, Busoru, Bulyambwa, | 2,400,000 | 700,000,000 | 700,000,000 | 700,000,000 | 700,000,000 |  |
| Project 10: Construction of walkways ( with a shelter/shade )at all newly upgraded HC IIIs( Buhanda, Mirambi, Tombwe, Burondo, Bupomboli, Busunga, Bundimulagya | 80,000 | 10,000,000 | 20,000,000 | 20,000,000 | 20,000,000 | 10,000,000 |
| Project 11: Procurement of medical equipment | 150,000 | 30,000,000 | 30,000,000 | 30,000,000 | 30,000,000 | 30,000,000 |
| Project 12: Establishing laboratories at newly upgraded HC III( Buhanda, Kyondo, and Tombwe HC IIIs) | 90,000 | 15,000,000 | 50,000,000 | 25,000,000 |  |  |
| Project 13: Construction of OPD at Bupomboli HC III | 300,000 |  |  | 100,000,000 | 100,000,000 | 100,000,000 |
| Project 14: Construction of a permanent Isolation unit at Bundibugyo General Hospital | 1,000,000 |  |  |  |  |  |
| Project 15: Construction of incinerators and waste pits at 4 Health Centre IIIs | 120,000 |  |  |  |  |  |
| Project 16: Construction of ANC and immunisation shelters at 5 newly upgraded HCs | 250,000 |  | 50,000,000 | 50,000,000 | 50,000,000 | 100,000,000 |
| Project 17: Construction of and equipping mortuaries Bundibugyo Hospital, Nyahuka and Kikyo HC IVs | 400,000 |  | 100,000,000 | 100,000,000 | 100,000,000 | 100,000,000 |
| TOTAL |  |  |  |  |  |  |

EDUCATION

| Total Cost for the Plan Period (UGX in Million) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Projects | Total (000) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| Project 1: Construction of three classroom block at Mataisa Primary school , Two classroom block at KUKA Primary school, : Completion of Two classroom block with an office at Kasaka Primary school, three classroom block at KInyante, two classroom at Busengerwa , two classroom at Bughonga and two classroom , two classroom at Budenge and kanyangoma, two classroom block for ntotoro primary school | 2,015,872 | 440,872,000 | 380,000,000 | 450,000,000 | 560,000,000 | 185,000,000 |
| Project 2: Construction of three stance latrine at Buganikere Primary school, a three stance latrine at Kihoko Primary School, three stance latrine at Bundingoma Primary school | 375,000 | 75,000,000 | 75,000,000 | 75,000,000 | 75,000,000 | 75,000,000 |
| Project 3: Supply of furniture to the highly enrolled schools | 223,000 | 22,000,000 | 45,000,000 | 52,000,000 | 52,000,000 | 52,000,000 |
| Project 4: Rehabilitation of the following primary schools Mwiribondo , of Bundikeki, Masule, Njule , Bundikakemba, Bukangama, Bundibugyo primary school, Bumate, Izahura, Buganikere, Bumate, Kisonko, and Galilaya primary school | 876,413 | 302,413,000 | 184,000,000 | 139,000,000 | 251,000,000 |  |
| Project 4: Construction of staff quarters at Bundimasoli, and Bundimbere, Mutsahur and primary schools | 663,000 |  |  | 221,000,000 |  | 442,000,000 |
| TOTAL |  |  |  |  |  |  |

WATER

| Projects | Total (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Project 1: Construction of Kagugu gravity flow scheme phase 11 in kagugu sub county | 15,000,000,000 | 160,468,000 | 3,000,000,000 | 3,000,000,000 | 3,000,000,000 | 3,000,000,000 |
| Project 2: Rehabilitation of Nyaruru Gravity flow scheme phase Busaru Sub county (Source and Transmission) | 600,000,000 | 20,000,000 | 120,000,000 | 120,000,000 | 120,000,000 | 120,000,000 |
| Project 3: Rehabilitation, of four protected springs | 250,000,000 | 50,000,000 | 50,000,000 | 50,000,000 | 50,000,000 | 50,000,000 |
| Project 4 Design and construction of Rukoki Gravity flow scheme in Mbatya Sub county | 10,000,000 |  |  |  | 10,000,000,000 | 10,000,000,000 |
| Project 5: Rehabilitation and Upgrade of Kikyo Gravity Flow Scheme | 6,000,000 |  |  | 3,000,000,000 | 3,000,000 |  |
| Project 6: Rehabilitation of piped water systems in rural areas (2 per year) | 3,000,000,000 | 600,000,000 | 600,000,000 | 600,000,000 | 600,000,000 | 600,000,000 |
| Project 7: Rehabilitation of Protected Springs in rural areas (5 per year) | 125,000,000 | 25,000,000 | 25,000,000 | 25,000,000 | 25,000,000 | 25,000,000 |
| Project 8: Rehabilitation of boreholes in rural areas (5 per year) | 250,000,000 | 50,000,000 | 50,000,000 | 50,000,000 | 50,000,000 | 50,000,000 |
| Project 9: Rehabilitation of piped water systems in mall towns (1 per year) | 2,000,000,000 | 400,000,000 | 400,000,000 | 400,000,000 | 400,000,000 | 400,000,000 |
| Project 10: Rehabilitation of piped water systems in large towns (1 per year) | 1,500,000,000 | 300,000,000 | 300,000,000 | 300,000,000 | 300,000,000 | 300,000,000 |
| Project 11: Upgrading and expansion of point water sources (1 per year) | 1,500,000,000 | 300,000,000 | 300,000,000 | 300,000,000 | 300,000,000 | 300,000,000 |
| Project 12: Construction of Public Sanitation Facilities in Rural Areas (2 per year) | 400,000,000 | 80,000,000 | 80,000,000 | 80,000,000 | 80,000,000 | 80,000,000 |
| Project 13: Construction of Public Sanitation Facilities in Urban Areas (2 per year) | 500,000,000 | 100,000,000 | 100,000,000 | 100,000,000 | 100,000,000 | 100,000,000 |
| Project 14: Awareness campaigns in rural areas (10 per year) | 250,000,000 | 50,000,000 | 50,000,000 | 50,000,000 | 50,000,000 | 50,000,000 |
| Project 15: Awareness campaigns in urban areas (4 per year) | 100,000,000 | 20,000,000 | 20,000,000 | 20,000,000 | 20,000,000 | 20,000,000 |
| Project 16: Construction of inclusive sanitation facilities in Health Centres (2 per year) | 300,000,000 | 60,000,000 | 60,000,000 | 60,000,000 | 60,000,000 | 60,000,000 |
| Project 22: Hand washing facilities installed in institutions and public places in rural areas (10 per year) | 15,000,000 | 3,000,000 | 3,000,000 | 3,000,000 | 3,000,000 | 3,000,000 |
| Project 23: Hand washing facilities installed in institutions and public places in urban areas (10 per year) | 15,000,000 | 3,000,000 | 3,000,000 | 3,000,000 | 3,000,000 | 3,000,000 |
| Project 24: Construction of Rwabatwa Gravity Flow Scheme | 3,373,257 |  | 843,314,250 | 843,314,250 | 843,314,250 | 843,314,250 |
| TOTAL | 63,040,000,000 | 12,608,000,000 | 12,608,000,000 | 12,608,000,000 | 12,608,000,000 | 12,608,000,000 |

TRANSPORT AND INFRASTRUCTURE DEVELOPMENT

| 4.3 Costs of projects. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Total Cost for the Plan Period (UGX in Million) |  |  |  |  |  |  |
| Projects | Total (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| Project 1: Manual routine maintenance of 60km of the road network. | 549,459,000 | 90,000,000 | 99,000,000 | 108,900,000 | 119,790,000 | 131,769,000 |
| Project 2: Mechanized routine maintenance of 150km of the road net work | 3,663,060,000 | 600,000,000 | 660,000,000 | 726,000,000 | 798,600,000 | 878,460,000 |
| Project 3: Installation of 100 lines culvert across the road network for drainage improvement. | 610,510,000 | 100,000,000 | 110,000,000 | 121,000,000 | 133,100,000 | 146,410,000 |
| Project 4: Rehabilitation/completion of 2km of Burondo – Kinoni road. | 366,306,000 | 60,000,000 | 66,000,000 | 72,600,000 | 79,860,000 | 87,846,000 |
| Project 5: Opening of 39.5km of District roads (Ntandi – Kahumbu road 8km, Butama – Irango – Kidedeya road 8km, Bumate – Karangusio road 6km, Bundingoma – Bundimirambi – Lamia road 6km, Njule – Tombwe road 3km, Mitunda – Bundikahondo – Bunyangule road 6km, Burambagira – Buyaya – Ngamba mosque 2.5km). | 1,205,757,250 | 197,500,000 | 217,250,000 | 238,975,000 | 262,872,500 | 289,159,750 |
| Rehabilitation of Bubukwanga - Katumba road 7km. Sub counties: Bubukwanga S/C and Kirumya S/C. Parishes: Sarah, Bundikeki and Katumba Parishes. | 490,000 |  | 490,000,000 |  |  |  |
| Rehabilitation of Kahumbu - Kyondo - Kahembe - Kirambi road 18km, Kasitu Sub County. Parishes: Katwakali, Munguni, Ndalibana. | 1,260,000 |  | 315,000,000 | 315,000,000 | 315,000,000 | 315,000,000 |
| Rehabilitation of Bundikuyali - Hakitara road 3km, in Kaghema Town Council and Kisuba S/C. Parishes: Hakitara parish and Kisubba Ward | 1,010,000 |  | 252,500,000 | 252,500,000 | 252,500,000 | 252,500,000 |
| Rehabilitation of Hakitara Boarder - Buhanda road 2km, in Kisuba S/C. Parishes: Hakitara and Buhanda Parishes | 940,000 |  | 235,000,000 | 235,000,000 | 235,000,000 | 235,000,000 |
| Bumadu - Gabbata - ESCO - Bundibugyo Town Council road 4.7km, in Bundibugyo Town Council. Parishes: Bumadu Ward, Kanyansimbi ward. | 829,000 |  | 207,250,000 | 207,250,000 | 207,250,000 | 207,250,000 |
| Rehabilitation of Mampongya - Bundikiteganwa road 3km, in Bubukwanga S/C. Parishes: Bubukwanga Parish, Mampongya parish | 270,000 |  | 67,500,000 | 67,500,000 | 67,500,000 | 67,500,000 |
| Rehabilitation of Harugale - Buhundu road 3km, traversing through Harugale and Bukonzo Sub Counties. Parishes: Bupomboli, Bumate and Buhundu parishes. | 2,610,000,000 |  | 652,000,000 | 652,000,000 | 652,000,000 | 652,000,000 |
| Rehabilitation of Gone- Bundikahondo- Bunyangule in Sindila and Butaama- Mitunda and kagugu sub counties | 870,000 |  | 217,500,000 | 217,500,000 | 217,500,000 | 217,500,000 |
| Rehabilitation of Busunga- Nyankoda community access road | 150,000 |  |  |  | 150,000,000 |  |
| Rehabilitation of Tobwe HCIII - Njule road 2km, in Bubandi S/C. Parishes: Tombwe and Njule Parishes | 940,000 |  |  |  |  | 940,000,000 |
| Rehabilitation of Buganikere - Kayenje road 1.5km, in Buganikere Town Council and Busaru S/C.Parishes: Buganikere ward, Kyamaisi ward and Kirindi parish. | 905,000 |  |  | 452,000,000 | 452,000,000 |  |
| Construction of Buganikere Town Council Administrative Head Quarters in Buganikere Ward. | 400,000 |  |  | 400,000,000 |  |  |
| Construction of Mbatiya Sub County Administrative Head Quarters, in Busamba Parish | 400,000 |  | 400,000,000 |  |  |  |
| Construction of Nduguto sub county headquarters in Galiraya | 400,000 |  |  |  | 400,000,000 |  |
| Construction of Bundingoma Sub County Administrative Head Quarters, in Bundinamandi Parish | 400,000 |  |  |  |  | 400,000,000 |
| Project 6: Rehabilitation of Kiryambuzi road section along Bundikayanja – Kisendera – Butwaka road. | 73,261,200 | 12,000,000 | 13,200,000 | 14,520,000 | 15,972,000 | 17,569,200 |
| Project 7: Construction of six arch bridges across the road network | 1,221,020,000 | 200,000,000 | 220,000,000 | 242,000,000 | 266,200,000 | 292,820,000 |
| Project 8: Maintenance and repair of equipment and vehicles. | 732,612,000 | 120,000,000 | 132,000,000 | 145,200,000 | 159,720,000 | 175,692,000 |
| TOTAL | 8,421,985,450 | 1,379,500,000 | 1,517,450,000 | 1,669,195,000 | 1,836,114,500 | 2,019,725,950 |

SUSTAINABLE ENERGY DEVELOPMENT

| ## PROJECT | ## Total (000) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| ## Project 1 construction of Butholya solar mini grid, Ngamba S/C, Butholya Parish. | ## 450,000 |  | ## 450,000,000 |  |  |  |
| ## Project 2: construction of Kasaka solar mini grid, Sindila S/C, Kakuka parish | ## 450,000 |  |  | ## 450,000,000 |  |  |
| ## Project 3: construction of Kihoko mini solar grid, Harugale S/C, Bupomboli parish. | ## 450,000 |  |  |  | ## 450,000,000 |  |
| ## Project 4: construction of Kyondo mini solar grid, Kasitu S/C, Ndalibana parish. | ## 450,000 |  |  |  | ## 450,000,000 |  |
| ## Project 5: construction of kibaghara solar mini grid, Ndugutu S/C, Kasanzi parish. | ## 450,000 |  |  |  |  | ## 450,000,000 |
| ## Project 6: Construction of Kibiriri solar mini grip, Ndugutu S/C, Kasanzi parish. | ## 450,000 |  |  |  |  | ## 450,000,000 |
| ## GRAND TOTAL | ## 2,7000,000 |  | ## 450,000,000 | ## 450,000,000 | ## 900,000,000 | ## 900,000,000 |

## 4.3	Resource Mobilization Strategy

This section Provides objectives and strategies for resource mobilization. A resource mobilization strategy is a plan designed to acquire and manage resources (financial, human, material, etc.) needed for an organization to achieve its goals. It involves identifying, securing, and optimizing the use of both existing and new resources. This strategy is crucial for organizational sustainability and success, ensuring the organization has the means to implement its programs and initiatives effectively.

4.3.1 Strategies for resource mobilization

To generate increased resources for the implementation of the plan, the following key

Strategies will be implemented over the plan period;

- The District will formulate and implement a local revenue enhancement plan for the District. These may include engaging cocoa buying companies, Power Suppliers –Sindila power suppliers.

- Investment of the available revenue in revenue generating activities. The district plans to invest its revenue mainly in road construction especially in areas where revenue can be generated like cocoa and vanilla buying areas and markets.

- Valuation of properties and conducting a business census are one of the measures the district is undertaking to enhance its own source revenue base. Sensitisations and taxi education in the community has always been key in engaging taxi payers to understand their obligations.

- Updating of the business register through conducting a business census and making use of the IRAS

- Bundibugyo district will implement the developed Local Economic Development Strategy to increase locally generated revenue.

- Strengthening revenue inspection, supervision and monitoring at all levels to reduce spending from source.

- Proper prioritization of projects will contribute to the proper utilization and management of revenue where resource shall be directed to priority areas.

- Strengthen revenue management and accountability through mandatory notices and Community Baraza,

- Conducting mass awareness campaign through radio talk shows to mobilize the public and explain key priorities of the district, BFP, and annual budgets and work plans.

- Compliance to the existing laws and regulation to improve performance and also attract donor attention.

- Strengthening coordination with development partners to ensure that their interventions are aligned to priorities in the five-year development plan.

- Compliance with MoFPED budget and reporting requirement would guide the decision makers on the performance of the available revenue sources and which strategies should be applied in a case where the performance is poor.

- Accountability and transparency are yet another key aspect which would give a true picture of what has been realised and if it has been spent according to plan.

- Lobbying for more funding from the central government through local authority’s association   like DRDIP 11

# CHAPTER FIVE: INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTING THE PLAN

Institutional arrangements for local government typically involve a structure that outlines the roles, responsibilities, and relationships between different levels of government, as well as between government and other stakeholders. These arrangements are crucial for effective service delivery, democratic participation, and local development.

The Development plan shall be implemented in accordance to the Local Government standing orders and the according to the Planning Frame works which district councils, counties (which are administrative units without a council), sub-county councils, parish councils and village councils. Majorly, the implementations shall be

Through government investments in strategic areas and private sector market driven actions, will be pursued. The Private sector will remain the engine of growth and development, while the local Government, in addition to undertaking the facilitating role through the provision of a conducive policy, regulatory and institutional framework, will also actively promote and encourage Local Economic Development in the district and Public – private partnerships in a rational manner that is being promoted by the current government.

In order to bring together all district development stakeholders to achieve common goals and objectives, in line with the National Development Plan, a partnership approach” will be adopted in the implementation of the district Development Plan in order to improve service delivery at all levels of governance. In order to operationalize the aforementioned concept, several reforms will be implemented including: improving the public service delivery system and deepening and strengthening the consultative machinery between the public and private sectors, community involvement in development and mindset change.

# 5.1 Implementation arrangements

The implementation activities will mainly focus on mechanisms to be used and measures that will be taken to ensure the achievement and measurement of the Distric Development plan results.

The implementation of the plan is therefore not a separate exercise, but primarily operates through the actions of each sector and the annual budgetary exercise. The projects under consideration are those approved by council in that financial year, and the implementation for each Programme is spelt out in details.

The strategy will also assist in coordinating the monitoring and evaluation processes to ensure the generation of data and information needed to steer implementation towards the realization of the Local Government Vision, mission, objectives, and goals.

- Out of the strategy, key information including lessons learnt, best practices and areas for improvement will be captured so as to ensure, accountability, transparency, value for money wealth creation and gauging the impact of development interventions. The strategy will be the basis for providing the knowledge and evidence generation that will shape implementation and achievement of intended Results.

- Every sector will hold quarterly meetings to discuss the progress of implementation of the annual work plans that will have been obtained from the District Development Plan. These meetings will be held within the first month of the quarter and will be attended by all staff members within the sector. The  quarterly performance review attended by all stakeholders including the political wing

- The District will continue holding monthly Technical Planning Committee meetings as required by law. These meetings will be attended by all Heads of Department, Senior Assistant Chief Administrative officers (SACAOs) and Town Clerks. During the meetings, each all-sector heads representative will present a quarterly brief outlining the achievements made by that sector during the previous quarter using a format that will be acceptable by all members of TPC. While discussing the quarterly briefs, the District Technical Planning Committee will ensure that there is no duplication of interventions by the various players in the implementation of the District Development Plan IV.

- The District will continue holding quarterly standing committee meetings for consideration of integrated progress reports from departments. These reports will also indicate the cumulative progress by the department during the course of the Financial Year in line with the annual work plan.

- The DistrictCouncil will continue to sit at least once a quarter. During the Council sessions, the Chairpersons of the Standing Committees will present recommendations regarding improved implementation and coordination of the annual work plans derived from the District Development Plan IV.

- District council will continue to organize Annual Budget Consultative conferences targeting the District technical and Political Leadership, Area Members of Parliament, Lower Local Government representatives, representatives of the civil society organizations, private sector, and the cultural leaders. During these meetings, the stakeholders will be updated about the progress of implementation of the planned projects and agree on strategies and priorities for the subsequent Financial Year in line with the Local Government Development Plan.

5.2 Institutional Arrangement

Implementation of the District Development Plan for the period 2025/2026-2029/2030 will be through the established decentralized local government structures, institutions, systems, procedures and regulations. Bundibugyo district will adopt and strengthen both political and technical structures and committees as provided in the Local Governments Act 1997 as amended. The institutions or committees both at District and lower Local Governments such as local councils, executive committees and standing committees of the councils, these structures will be empowered with relevant laws and regulations that govern their operations to enable them perform their mandates effectively. The annual budgets and work plans will have to be aligned to the priorities in the DDPIV to ensure that they are implemented. The council will review departmental annual work plans and budgets to ensure that priorities in the plans are funded. Heads of departments will spearhead implementation of the planned priorities in the development plan in their respective departments under the overall stewardship of the Chief Administrative officer who is charged with the mandate of coordinating all development programmes in the District

### 5.2.1 Role of Key Stakeholders

| S/No. | Role and responsibility of LG Organ/ Committee/Institution/ |
| --- | --- |
| 1. | Council |
|  | The council and its sectoral standing committees shall undertake the following responsibilities; - Approve annual plans and budgets derived from the Development Plan - Authorize public expenditure and exercise general control over public revenues - Enacting ordinances and byelaws - Approve policies and bylaws that may be relevant in implementation - Departmental quarterly work plans and budgets reviews and approval - Discuss quarterly progress reports, including challenges and propose way forward - Monitor project implementation in the district and report accordingly - Report any deviation from approved work plans and budgets - Approval of work schedule and quarterly work plans for implementation - Review monthly revenues, expenditure returns, contracts and PAC reports |
| 2. | Executive Committee |
|  | The Executive Committee is composed of all the secretaries. The District chairperson chairs the committee and the CAO is the secretary. All heads of departments are co-opted members and the committee is expected to meet at least monthly. The DEC will play the following role in the implementation of the plan; - Oversee the implementation of the DDP including policy formulation and guidance - Monitor the implementation of council programmes and take action where necessary - Review the budget performance - Discuss monthly, quarterly and annual synthesis and progress reports, including challenges and propose way forward - Consider and evaluate performance of council against approved work plans and programmes - Initiate, encourage and support self-help projects and mobilize people, materials and technical assistance in relation to the self-help projects and lobbying for additional external resources - Monitor and supervise projects and other activities being implemented - Ensure political oversight in areas of implementation and evaluation of the District Development Plan |
| 3. | Standing Committees of Council |
|  | - Reporting to the council on status of implementation - Discussing quarterly and annual reports and making recommendations to District Council for improvement - Approval of work schedule and quarterly work plans for implementation - Departmental quarterly work plans and budgets reviews and approval |
| 4. | The Technical Planning Committee |
|  | - Provision of technical specifications and Terms of References, Bills of Quantities, Drawings and Designs to be submitted to Procurement and Disposal Unit and certification of works and services - Create awareness for the full understanding and appreciation of the plan - Ensure efficient allocation of resources through better coordination and budgeting - Initiate procurement and disposal requirements and forward to PDU (procurement plan) based on approved budget - Harmonize management, supervision, coordination and reporting arrangements for the DDP implementation. - Preparation of monthly, quarterly and annual progress reports including challenges and recommendations and way forward for future implementation - Supervision and inspection of projects and programs for compliance and standards in service delivery. - Resource mobilization and accountability for funds received and spent on quarterly bases to all stakeholders including the community beneficiaries - Project generation and appraisals for feasibility, viability and sustainability - Technical backstopping to Lower Local Governments and other relevant institutions - Advising councils on project implementations - Evaluation of projects and programs and document key lessons learnt for future designing and programming |
| 5. | The Budget Desk |
|  | Budget Desk Team shall be appointed by CAO to coordinate budgeting process. The Committee shall be chaired by Head of Finance and Planning staff as a Secretariat. The role and responsibility of budget desk include; - Ensuring that departmental plans and budgets are realistic - Ensuring that departmental work plans and budgets are aligned to the DDP - Coordinating the preparation of departmental annual work plans and budgets and ensuring that development partners’ resources are integrated - Ensuring that the local government budgeting cycle is followed and stakeholders are updated on the planning process |
| 6. | Contracts Committees |
|  | The DCC will carry out procurement of goods and services required using the PPDA Act and Regulation. The functions of the DCC and user departments are as follows; - Approve recommendations from adhoc evaluation committee and award contracts - Approval of Annual Procurement and Disposal Plans - Approval of evaluation reports and verifying asserts for disposal - Approval of negotiation team - Approval of bidding and contracts documents - Approval of members of evaluation committee - Ensuring compliance with the guidelines, the Act and regulations |
| 7. | Civil Society Organizations |
|  | - Participate in community mobilization and sensitization - Participate in resource mobilization - Lobbying and advocacy - Representation of the interest vulnerable communities - Engaging government on the plight of the vulnerable members of the community - Participate in monitoring and evaluation |
| 8. | Physical Planning Committee |
|  | - Establishment of physical planning committee - Their functions shall include and not limited to the following; - To cause to prepare local physical development plans, through each officer, agents or any qualified Physical Planner - To recommend to the board development applications for change of land use - To approve development applications relating to housing estates, industrial locations, schools, petrol stations, dumping sites or sewerage treatment which may have injurious impacts on the environment as well as applications in respect of land adjoining or within a reasonable vicinity of safeguarding areas - To hear appeals lodged by persons aggrieve by decisions made by the Physical Planner and Lower Local Physical Planning Committee under this act - To ensure the integration of Physical Planning into the Five Year integrated Development Plans - To exercise supervisory powers over all lower Physical Planning Committees - To ensure integration of social economic and environmental plans into the Physical Development Plans |
| 9. | Roads Committee |
|  | - Planning and management of road funds - Collection of revenues from utilization of roads - Investment of surplus funds - Determine levels of road traffic - Allocation and transfer of funds to designated agencies |
| 10. | Community Members |
|  | - Participate in planning and budgeting activities through the normal planning and budgeting cycle - Prioritize their needs for submission by the Local Council I chairperson and town agent. - Participate in implementation and monitoring of the project implementation - Providing project site security during implementation and report activities or acts that are detrimental to quality of the project - Participate when required or called upon for Evaluation of the projects |

## 5.2 Coordination and Partnership Framework

The development plan will integrate interventions from all stakeholders most especially interventions from lower local governments, departments and civil society organizations especially conducting annual budget stakeholder consultative conference, management committee meeting with implementing partners.  This will be done by sequencing programme interventions and projects in such way that there are clear linkages between projects that will require inputs, work in progress from other programmes or lower local governments.  The higher local governments will also take care of lower local governments’ projects that may have financial implications on the higher local governments.

The district intends to focus its attention on both service delivery and local economic development/wealth creation.   This will be achieved through engagement both public led approach and public private partnership. The district will ensure that joint monitoring with implanting partners, sharing our BFPs, work plans and annual budget with implementing partners as well as participatory planning meeting and interface meeting with community members.

Through integrity meetings issues related to service delivery will be shared in form of barazas and community meetings

5.3 Pre-Requisites for Successful DDP IV Implementation

5.3.1 Sustained funding from the Central Government

Over 96% of the Development plan will be financed by the central Government Transfers. The District will fulfill the Local Government obligations for accessing the central Government transfers for example timely reporting and accountability for the funds received, adherence to the conditions related to specific grants , UGIFT, DDEG, School maintenance non-wage component , sector non-wage conditional and development  School Facilities Grant and, timely procurement of goods, services and works

5.3.2 Strong Political will and commitment to transparency, accountability and results.

Strong political will and a commitment to transparency, accountability, and results are essential prerequisites for successful DDP IV implementation because they create an enabling environment in which policies, resources, and institutional efforts can be aligned toward achieving development outcomes. When national and local leaders prioritize openness, uphold clear reporting mechanisms, and demand measurable progress, it strengthens public trust and ensures efficient use of funds. This commitment also promotes timely decision-making, reduces corruption risks, and enhances coordination among government agencies, development partners, and communities. Ultimately, strong political backing combined with transparent and accountable systems ensures that DDP IV initiatives are implemented effectively, sustainably, and with tangible, traceable impact for citizens.

5.3.4 Behavior/mindset change amongst the communities.

Behavior and mindset change among communities is essential for the successful implementation of DDP IV because sustainable development relies not only on infrastructure and services but also on active community ownership and positive social practices. When communities embrace new ways of thinking such as supporting local development initiatives, adopting responsible resource use, participating in planning processes, and maintaining public infrastructure the effectiveness and longevity of DDP IV interventions are greatly enhanced. Shifting attitudes toward collaboration, accountability, and civic responsibility helps reduce resistance to change, strengthens local governance, and ensures that development gains are preserved and expanded over time.

5.3.5 Enhanced Local Revenue collection

The District intends to boost local collection through implementation of the Local Revenue Enhancement Plan for the period 2025/2026 to 2029/2030. Improved local revenue collection will enable the District implement the local needs that are neither funded by the Central Government nor the Development Partners. Strict follow up of the parish chiefs and town Agents will lead to improvement of the local revenue collected through IRAs. All stakeholders political and technical wing will make follow up and monitoring to ensure that all the local revenue is collected as planned

5.3.6 Partnership with other players

The District will continue to provide a conducive environment for other players like the Civil Society Organizations and the private sector in order to complement District efforts in the delivery of the District Development Plan aspirations. Their activities/ plans will be captured either off – Budgets or fully be planned for the district plan where cash will be received directly on the district accounts.

5.3.7 Team Work

The District will continue to promote team work among all players for example team work within the departments, team work between departments, team work between the technical and Political Leadership, team work between the District and Lower Local Governments, and team work between District and Civil Society organizations and Private Sector.

5.3.8 Continuous Capacity Building of staff

There is need for continuous capacity building of staff in order to match with the contemporary requirements for improved service delivery in the District. However, this will call for formulation of a comprehensive District capacity building Strategy for the medium term and preparation of annual Capacity Building Plans to operationalize it.

CHAPTER SIX: COMMUNICATION AND FEEDBACK STRATEGY

6.1 Communication strategy

A local government communication strategy builds trust and informs residents by creating a two-way dialogue, focusing on transparency, accessibility, and engagement across multiple platforms (digital, print, community) to share service info, manage crises, foster participation, and achieve strategic goals like better service delivery and community buy-in, using data to understand diverse audiences and consistently measuring impact

Communication plays a vital role in providing knowledge, and changing people’s attitudes and norms. It can play an important role in initiating or accelerating the changes that are already underway as well as in reinforcing and supporting change that has occurred. Effective communication can also result in supportive policies, positive legislature and increased resource allocation. To be effective, strategy must take three factors into account simultaneously and these include; your goals and objectives, Operational constraints and imperatives i.e., things you must do and things you cannot do and Pertinent conditions in the environment. The District will use the following strategies to inform the community

- Objectives: Inform, persuade, engage, build reputation, manage crises, and enhance service delivery

- Audiences: Residents (diverse demographics), businesses, media, community groups, other government levels

- Content: Service updates, project progress, emergency info, policy changes, budget details, success stories

- Crisis Management: Establish rapid response, consistent messaging, and multi-platform alerts (websites, social media, SMS) for emergencies like disasters or health protocols.

An effective Communication strategy is an essential element of the DDP implementation and monitoring and evaluation frameworks.   With regard to DDP implementation framework, it is crucial that all stakeholders in the DDP process are adequately informed and mobilized to understand and comply with the district vision, objectives, the targeted long-term outcomes and the strategic directions pursued in the DDP.  But an effective Communication strategy will also serve to actualize the required bottom-up influences presumed in the DDP conceptual framework where local government priorities are expected to inform the selection of national sector development priorities.

## 6.2 Communication Plan

Table 28 : Communication Plan

| Communication | Audience | Type / Communication Channel | Objectives | Content | Responsibility |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Primary | Others |
| LG Vision, Goals and Strategic objectives | Primary: District staff, citizens | Others: Development partners, NGOs Public meetings, brochures, website, radio | To Raise awareness and align stakeholders with the District’s development agenda | Vision statement, goals, objectives | CAO | District council |
| Role of OPM | Primary: District staff, OPM | Others: Local leaders, CSOs, Reports, Circulars, Workshops, memos | To clarify the oversight and coordination role of the Office of the Prime Minister | Detailed roles and responsibilities | CAO, OPM |  |
| Priority Investment Projects | Primary: Community members | Others: Development partners Radio, community dialogues, reports | To inform stakeholders about priority projects and gather community support | Project descriptions, timelines, benefits | District Planning Department |  |
| Dissemination of the Plan | All stakeholders | Public meetings, social media, website, barazas | To ensure widespread understanding and ownership of the plan | Full plan, annexes and summaries | CAO District planning department, RDCs office |  |
| Feedback Mechanisms | Citizens, community leaders | Suggestion boxes, hotlines, surveys | To encourage stakeholder feedback on the plan and its implementation | Contact details for feedback, survey forms | Communication Officer |  |
| Progress Updates | Stakeholders | Quarterly reports, radio, newsletters | To provide updates on implementation progress | Achievements, challenges, next steps | Sector Heads |  |

LG Stakeholders

Ministry of Finance, Planning and Economic Development, Ministry of Local Government, NPA, UBOS, District Administration, DEC, Council, Lower Local Governments, Civil Society Organizations, Faith Based Organizations, Community Based Organizations, Private Sector Organizations, Special Interest Groups, and Business Community representatives.

Information Dissemination Channels

A multimedia approach will be used to disseminate the information. The choice of the communication channel and message theme will be determined by the target audience and their role. The following communication channels will be used;

Briefs (weekly and monthly), Progress reports (quarterly, annual and midterm), Meetings (monthly, quarterly, annual and midterm), Interactive Radio programs, Workshops, Internet and email, Newspaper publications, Press conferences and briefs, Barazas, Television programs, Quarterly News Letters and Brochures.

### The Importance of an effective Communication and feedback strategy in the DDP framework

Effective communication is vital for organizations as it improves productivity, fosters teamwork, and builds employee engagement and trust. It reduces misunderstandings and conflicts, enables innovation and problem-solving, and helps align everyone with the districts goals and vision. Effective communication helps unleash the power of an organization. It helps to create a healthy working environment, fostering collaboration, and increasing productivity

Table 29: Levels and Target Institutions for Effective Communication and Feedback

| Institutions | Audiences (Agencies) |
| --- | --- |
| Central Government | All Ministries, Departments and Agencies |
| Local Government | All LLGs (Divisions) |
| Council | The district council will target key stakeholders such as Technical Planning Committee, DEC, and PAC so as to streamline the Program implementation process. |
| CSOs/NGOs | The CSOs operating in the District are involved in activities that contribute towards the achievement of the vision of the plan. Therefore, the communication strategy seeks to strengthen partnerships with CSOs in the entire. |
| Mass media | Both electronic and print media will be utilized in order to lead to dissemination of information regarding progress of implementation of the LGDP to the public and other stakeholders. The Local FM Stations like Voice of Bundibugyo- UBC and DFM radio stat. will be very instrumental disseminating information. |
| Cultural ( OBB) and religious institutions | These institutions have influence and reach the masses in large numbers. These will be targeted to disseminate and pass on key development messages during their services to foster development. |
| Communities | These are the primary beneficiaries of the interventions reflected in the Plan. A package of communication channels will be used to reach out to the community on regular basis to update them on the progress of the Plan implementation and the roles of the various stakeholders in the implementation, monitoring and evaluation of the plan. |

Table 30 : Institutions of Interest and Channel of Communication

| Audience | Common Interest | Key Message Concept | Channel |
| --- | --- | --- | --- |
| MoLG & NPA | -Generation of NDP & DDP -Vision 2040 | Guidance of government Planning and resource allocation | -Issuance of planning guidelines -Workshops and seminars -Website |
| MoFPED | Preparation of annual budgets and work plans | Guidance on Program-based budgeting approach to planning | -Issuance of planning guidelines -Workshops and seminars -Website |
| Other line ministries | Implementation of sector government Programs in the LG | Issuance of IPFs and guidance on sector conditional and development grants | -Workshops and seminars -Website |
| Office of the District chairperson and Council | Improved performance in gov’t Programs and projects | Provision of an oversight role, monitoring and evaluation of gov’t Programs | Reports and field visits |
| Office of the CAO and all Departments | Effective service delivery | Provision of efficiency and effectiveness of public resources | Budgets, Plans, audit and PAC reports |
| Mass Media | Awareness of public Programs | Publication of gov’t Programs | -Website, Live broadcast, print media |
| CSOs/NGOs | Signing of MOUs and sharing of Development partners work plans | Provision of development support to gov’t Programs | Donations, facilitation of off budget activities |
| General public | Access to effective and efficient public services | Embracing gov’t Programs and projects for development | Budget conferences, public Barraza meeting and dissemination of public information on public notice boards. |

### 6.3.1: Roles/Responsibilities of Stakeholders of LG in Communication and Provision of Feedback to Stakeholders

Table 31: Relevant Institutions with Corresponding Roles & Responsibilities for Communication and Feedback.

| Institution | Roles and responsibilities. |
| --- | --- |
| Office of the District chairperson | Receive quarterly reports from the Local Government Public Accounts Committee and provide synthesis reports to Council Lobbying and advocacy for improved funding from the central Government and Development Partners |
| CAOs office | Ensure efficient use of available funds, transparent and accountability |
| Heads of Departments. | Propose policies for improved revenue collection and management, Planning, and budgeting |
| Heads of Service Provision Institutions like Health units and schools. | Provision of social services to the communities |
| Management Committees of Service Provision Institutions like SMC, HUMCs, BMCs, Market management committees etc. | Post-project implementation management and maintenance |
| Project Management Committees. | Issue Policy Guidelines for use of conditional grants by the Local Government Provide other Government transfers to the Local Government Receive and review work plans and reports from the Districtity |
| LLG councils | Approve annual budgets and work plans Approve new sources of revenue Lobbying and advocacy for improved funding from the central Government and Development Partners |
| Parish Chiefs/Town Agents | Provide supervision and oversight at parish/ ward level |
| Community Development Officers | Mobilization of communities for government development activities Settling of community conflicts and disputes among families |

CHAPTER SEVEN: RISK MANAGEMENT AND MITIGATION MEASURES

7.1	Risks Management and Anticipated Impacts

Risk management in local governments is a crucial, systematic process of identifying, assessing, and controlling threats (like floods, , legal issues, or operational failures) to ensure service continuity, protect public assets, maintain public trust, and achieve objectives, involving strong governance, clear policies, mitigation strategies (insurance, plans, infrastructure), continuous monitoring, and communication for effective, balanced decision-making. It balances seizing opportunities with minimizing negative impacts, embedding risk awareness into the culture and structure of the district.

- Why it's Important for Local Governments

- Ensures Service Continuity: Protects essential public services from disruption.

- Safeguards Assets & Funds: Protects public buildings, data, and financial resources.

- Builds Public Trust: Demonstrates responsibility and competence in handling public interests.

- Supports Strategic Goals: Allows councils to pursue opportunities (like development) with confidence by managing associated risks.

Table 32: Anticipated Risks and Mitigation Measures

| No. | Type of risks | Category | Causes of the risks | Likelihood of occurrence | Impacts (1=low, 2- | Mitigation | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1= Low | 1= Low, |  |  |
|  |  |  |  | 2=Intermediate | 2=intermediate |  |  |
|  |  |  |  | 3= High | 3= High |  |  |
| 1. | Infrastructure Gaps and Maintenance | Operational/Preventive Risks | - Inadequate infrastructure - Wide road networks - Limited and poorly maintained structures at schools and health centres |  |  | - Budgeting for face lift and maintenance of infrastructures | Works department |
| 2. | Weak institutional capacities | Operational/Preventive Risks | - Under-staffing - Limited staff training - Corruption |  |  | - Recruit of staff to narrow the staffing gaps and organizing capacity building training | Administration |
| 3. | Climate Change and Environmental Degradation. | External Risks | - Unsustainable use of natural resources |  |  | - Environmental and climate change mainstreaming in all programs - Restoration of degraded fragile ecosystems. - Enforcement of laws and regulations to ensure environmental protection. | Natural Resources Department |
| 4 | Population explosion and associated pressures | Strategic Risks | - High population growth rate and development of rural growth centres. |  |  | - Sensitization of masses on family planning. - Provision of social services to rural areas | Health and community Based Services |
| 5 | Corruption and Financial Mismanagement. | Strategic Risks | - Delayed implementation of development activities leading to misallocation of funds. - Lack of transparency - Poor governance |  |  | - Auditing of all government projects and programmes - Short life cycle audits - Ensuring launching and commissioning of development projects - Proper planning and budgeting | Audit and Administration |
| 6 | Loss of reputation | Operational/Preventive Risks | - Misinformation and communication gaps |  |  | - Developing communication plans - Disciplinary action against involved officers | Administration |
| 7 | Theft of property | External Risks | - Limited security lights and security personnel |  |  | - Provision of security, installation of cameras and security lights - Regular update of the asset registers and engraving of all assets. | Administration |
| 8 | Improper record keeping | Operational/Preventive Risks | - Insufficient storage space - Lack of computers - Inaccurate and incomplete records - Unauthorized access and disclosure - Data loss |  |  | - Training staff - Procuring of filing cabins - Procuring of computers - Digitization of records and information | Administration |
| 9 | Procurement Delays | Operational/Preventive Risks | - Delayed and Non submission of Procurement documentations by procuring entities. |  |  | - Adherence to procurement timelines for submissions | Administration, PDU |
| 10 | Budgeting risk | Operational/Preventive Risks | - Unrealistic revenue projections - Inaccurate budgeting |  |  | - Reliable and accurate data collection - Regular Budget Desk Meetings - Revenue enhancement Plans | Finance and Planning |
| 11 | Expiry of drugs/medicine and supplies | External Risks | - Short expiry periods - Short shelf life - Overstocking - Push methods - Poor storage - Change of regiments |  |  | - Support supervision of District medical stores, stores focal persons - Formulate distribution policy (internal &external) - Improving Drug stores at Health facility - ¦Provision of tools e.g. stock cards, Expiry drugs register, thermometers - Fridge tags - Proper planning that is data-driven | Health, Production and NMS |
| 12 | Counter fake drugs | External Risks | - Unlicensed pharmacies/drug shops, clinics - Importation through porous boarders - Inadequate supervision/ monitoring of pharmacies, clinics & Drug shops |  |  | - Drugs inspection - Clinics inspection - Policies/guidelines in place - Registration of practitioners | NDA and UNBS |
| 13 | Incidences of diseases eg Covid, mpox, measles s, Merbug, Ebola, Yellow fever | Strategic Risks | - Environmental degradation - Porous boarders - Non-adherence to SOPS eg Screening, - Poor coordination - Delayed detection & reporting to management. - -Undependable reference forms |  |  | - Observe the point of entries and their functionality - Sensitization - Intensify cross meetings and surveillance | One Health Team |
| 14 | Poor academic performance in schools | Operational/Preventive Risks | - Inadequate education infrastructure and learning materials - Absenteeism of learners and teachers |  |  | - Avoiding absenteeism - Providing good learning environment | Education |
| 15 | Encroachment on government lands | External Risks | - Untitled government lands - Lands without clear boundaries |  |  | - Titling of government lands - Live fencing of government lands | Natural Resources |
| 16 | Inadequate tools to perform duties | Operational/Preventive Risks | - Limited means of transport, Computer accessories, cameras, GPS, Protective gears - Under funding |  |  | - Retooling and procurement of goods and supplies | Administration |
| 17 | Failure to Implement Audit recommendations | Operational/Preventive Risks | - Lack of management commitment, support and prioritization of audit recommendations - Limited follow up and monitoring |  |  | - Ensure monitoring and follow up - Integrate audit recommendations into strategic planning | Audit |
| 18 | Payroll errors and inaccuracies | Operational/Preventive Risks | - Non-compliance with regulations - Lack of transparency - Insufficient training and expertise |  |  | - Ensure adherence to regulations, circulars and guidelines - Conduct regular audits and reviews - Provide training and development | Administration |

CHAPTER EIGHT: MONITORING AND EVALUATION AND LEARNING

### 8.1 Monitoring and Evaluation (M&E) Frameworks

LGDP Monitoring and Evaluation Arrangements

Monitoring, Evaluation, and Learning (MEL) Frameworks are integrated systems guiding programs to track progress (Monitoring), assess effectiveness (Evaluation), and use insights for adaptation and improvement (Learning). They act as a project's navigation system, using tools like logical frameworks (logframes) to define goals, indicators, data collection, and responsibilities, ensuring accountability, evidence-based decisions, and continuous learning for better results in development, humanitarian, and other sectors.

Bundibugyo District Council implements its Monitoring and Evaluation through a structured institutional framework led by the District Planning Department which coordinates all data collection, performance tracking, and reporting across departments. The District Council provides overall oversight, while the Technical Planning Committee (TPC) consolidates sector reports and ensures alignment with the District Development Plan IV. Sector departments including Health, Education, Works, Production, and Community Services conduct routine monitoring of their activities, submit periodic reports, and track progress against sector indicators.

The District uses a combination of routine monitoring, quarterly and annual performance reporting, field inspections, community feedback mechanisms, and both mid-term and end-of-term evaluations. Reporting is standardized through national systems such as the Performance Budgeting System (PBS), ensuring consistency in data management and alignment with national frameworks like the National Development Plan (NDP IV). Participatory methods, such as community barazas and scorecards, strengthen accountability and allow beneficiaries to provide direct feedback on service delivery.

Monitoring and Evaluation (M&E) in Bundibugyo district  faces challenges like weak infrastructure (internet/power), funding gaps, limited data culture/stakeholder buy-in, poor capacity (skills, planning), data quality issues (bad data, focus), and institutional fragmentation, hindering evidence-based decisions, transparency, and effective resource allocation for development goals. Solutions involve digital tools, training, integrating M&E into budgets, fostering data use, and improving planning for better accountability and impact. However, opportunities exist through national reforms, the use of digital reporting systems, and strong community mobilization structures linked to programs like the Parish Development Model (PDM). Strengthening these systems would allow Bundibugyo district to more effectively track development outcomes, improve service delivery, and support evidence-based planning.

### 8.2 M&E Roles and Responsibilities of Key Actors

Table 33: Roles and Responsibilities of Key Actors

| Key Actors | Roles and Responsibilities. | M&E Output. |
| --- | --- | --- |
| Accounting officers/ Technical staff | - Strategic development planning for results, based on the District strategic direction and its priorities. - Prepare the results and reporting framework that includes target setting for the Plan. - Coordinates the review of the District performance indicators and targets. | A comprehensive framework for results and targets. Annual reviews of the district performance indicators. |
| District planning department | - Strategic development planning for results, based on the District strategic direction and its priorities. - Prepare the results and reporting framework that includes target setting for the Plan. - Coordinates the review of the district performance indicators and targets. - Conducts annual LGMSD performance assessment | Updated performance framework and target adjustments. LGMSD performance assessment reports |
| District Council | - Responsible for programme oversight. - Independent monitoring & evaluation of the budget to inform resource utilization for results. - Fosters good governance and consistency of the budget management to the DDP and guarantees effectiveness and value for money. - Conducts evaluations to assess the execution of the Budget as per district objectives and priorities. | Independent reports on budget utilization. Evaluation reports on the effectiveness of program execution. |
| Office of the District Chairperson. | - Provides oversight of the Plan implementation - Promotes of good governance practices. | Oversight reports on the implementation status. Governance improvement recommendations. |
| Implementing partners (NGOs, CSOs etc) | - Monitor and submit reports on the implementation of their projects and programs in line with the National and District objectives/priorities. - Assess and provide oversight reports on service delivery and implementation of planning in the district. | Project and program reports. Service delivery and program implementation assessments. |
| Ministry of Finance, Planning and Economic Development | - Conducts budget monitoring in line with the Plan - Coordination of programs by improving monitoring systems, better alignment of budgeting processes with national development priorities | Budget monitoring reports. Coordination assessments and recommendations for better alignment with national priorities. |

### 8.3 Major Monitoring and Evaluation Events

Table 34: Presenting the LGDP Main M&E Events

| Main M&E Events | Purpose and Description | Output | Lead Agency | Other Key Actors | Time frame |
| --- | --- | --- | --- | --- | --- |
| Programme/Sub-programme Quarterly Progress report | Document progress of implementation, the drivers of progress, challenges and recommendations | Quarterly Programme Progress report | LG Programme/Sub-programme Heads | Other LG Actors- NGOs and DPs | Quarterly |
| LGDP Annual Performance Review | Internal review of LGDP implementation (Programmes, interventions and projects) | Local Government Annual Performance Report | HLG | LG Stakeholders | Annually, September |
| Alignment of BFPs and budgets to the LGDP | Align BFP with the LGDP (Alignment) following communication of the 1st BCC to HODs and LLGs and | BFP | Accounting Officer, Planning Department | MFPED, NPA, TPC Members and other LG stakeholders | Annually, October- November |
| Budgeting and Financial Planning | Circulate 2nd Budget Call Circulars to commence the budget preparation process | Annual Budget Estimates Performance Contracts Annual Work Plan | Accounting Officer, Planning and Finance Department | MFPED, NPA, TPC Members and other LG stakeholders | Annual, March- May |
| Statistics Production and use in the NDP implementation | Basis for a before, midterm and end line assessment of the LGDP progress | Statistical abstracts and Quarterly Progress Reports | UBOS, MFPED | OPM, NPA, MFPED, other MDAs as well as LGs | Annually, Quarterly |
| LGDP Mid-Term Review | Assess mid-term progress of LGDP and projects and programmes to ensure consistency of implementation with overall focus and objectives | LGDP mid-term review reports | LG | NPA, MDAs, MFPED, OPM, LGs, private sector, CSOs | January-June 2028 |
| LGDP end Evaluation | Assess end-term evaluation of LGDP including projects and programmes | LGDP End evaluation reports | LG | MDAs, MFPED, OPM, LGs, private sector, CSOs | June 2030 |

# ANNEXES

# Annex 1: Project Profiles

| PROJECT SUMMARY |  |
| --- | --- |
| Project Title | Rehabilitation and upgrading of Community access and urban roads |
| NDP Program Description | Transport and infrastructure Development |
| Department | Roads and Engineering |
| Location | 20 Sub counties and 7 Town councils |
| Estimated Project Cost | 20,000,000,000 |
| Current stage of project implementation at commencement of LGDP | Most of the community access and Urban roads are maintained manually by use of hoes |
| Funding Secured | 8,421,985,450 |
| Total funding gap | 11,578,014,550 |
| Project Duration/Life span (Financial Years) | 2026 |
|  | 2030 |
| Officer Responsible | District Engineer |
| PROJECT INTRODUCTION |  |
| Problem Statement | Problem to be addressed Bundibugyo District, is experiencing rapid urban growth, increased traffic volumes, and expanding economic activities. However, its road infrastructure has not kept pace with development needs, resulting in major challenges that affect residents, businesses, and service delivery. The most common issues identified include; Poor Road Conditions, Inadequate Connectivity, Lack of Sustainable Road Maintenance, Increased, Road Accidents and Urban Growth Without Infrastructure Expansion, frequent floods that wash away bridges and constructed roads |
|  | Causes of the problem The challenges facing road infrastructure in Bundibugyo District stem from a combination of technical, financial, institutional, environmental, and demographic factors. These root causes contribute to the ongoing deterioration of roads and the lack of sufficient coverage across the District. These problems arise due to Inadequate Funding for Road Infrastructure both central government funding and Locally raised funding, Poor Planning and Urban Expansion, Weak Institutional Capacity, Lack of Routine and Preventive Maintenance and Poor Drainage and Erosion Control. |
| Situation Analysis | Bundibugyo district is connected with good road network- Tarmac from Kampala to Lamia Border with good community road network that is connected to schools, health facilities and cocoa producing communities. This has improved access to the market for the agricultural produce and to the social services like schools, health facilities and markets. However, due to the increase in traffic especially cargo trailers, Fort portal- Bundibugyo Lamia road has deteriorated and it is going to affect the transportation of goods outside Bundibugyo. Inadequate funding has also affected construction of community access roads and urban roads. |
|  | Construct, upgrade and climate proof strategic transport infrastructure (tourism and agriculture), Strengthen existing mechanisms to deal with negative social and environmental feeder and intra-District roads in good condition. |
|  | Challenges - Inadequate supervision vehicle (JMC). - Inadequate mechanical imprest for maintenance of new and old equipment. - Disaster that affects the road network and bridges beyond repair as a result of heavy rainfall. - Unfunded lower LGs and S/Cs under the road fund (Kaghema Town Council, Mbantia S/C and Ngite S/C). - Lack of a suitable equipment (tracked excavator) to handle road opening for the hilly/mountainous terrain – where a wheel loader is misused for this purpose. - Human Resource gap (inadequate operators and drivers for the road fleet). |
|  | Crosscutting aspects Gender Equality and Women’s Empowerment. Women and girls are often disproportionately affected by poor infrastructure (e.g. unsafe walking conditions, limited access to health or economic opportunities). Environment and Climate Change. Road construction can cause soil erosion, flooding, dust, deforestation, and water pollution. HIV/AIDS Prevention and Health. Road construction projects often involve mobile workers, which can increase the risk of HIV/AIDS transmission in host communities. Youth Empowerment. High youth unemployment in Bundibugyo limits economic opportunities. Disability Inclusion and Accessibility. Persons with disabilities (PWDs) often face barriers due to inaccessible road infrastructure. Human Rights and Social Inclusion. All citizens have a right to safe and reliable transport. |
| Relevance of the project idea | Alignment to NDP, SDPs and Agency plans The project is aligned to Uganda’s Vision 2040 and the Third National Development Plan (NDP III) prioritize infrastructure development as a key driver of socio-economic transformation. The District Development Plan (DDP) and District Physical Development Plan emphasize improving transport networks to promote urbanization and economic integration. Project contributes to achieving national development goals, SDGs, and District performance targets. |
| Stakeholders | Direct beneficiaries 1. Residents Living Along Project Roads 2. Landowners and Property Owners along the Road Corridor 3. Roadside Businesses and Market Vendors 4. Farmers Adjacent to Project Roads 5. Transport Operators Using Upgraded Roads |
|  | Indirect beneficiaries 1. General Residents of Bundibugyo District 2. Farmers and Agricultural Producers 3. Local Businesses and Traders 4. Transport Operators and Drivers 8. Tourists and Visitors 9. Financial Institutions |
|  | Likely project affected persons - Landowners - Tenants/Occupants - Business Owners and Traders - Residents and Households - Vulnerable Groups - Utility Service Providers |
| Project objectives/outcomes/outputs | Objectives - To construct new roads where there is no existing road infrastructure. - To rehabilitate and upgrade existing roads to withstand increasing traffic volumes and improve road safety. - To implement routine and periodic maintenance to ensure the long-term sustainability of the road network. - To improve access to economic hubs, markets, social services, and other essential facilities within the District. |
|  | Outcomes - Improved Road Connectivity: Enhanced accessibility between urban and rural areas, facilitating trade and economic activities. - Enhanced Economic Growth: Easier access to markets, improved logistics, and reduced transportation costs. - Improved Quality of Life: Better access to education, healthcare, and other essential services. - Employment Opportunities: Local employment opportunities during construction and maintenance phases. - Sustainability: Long-term durability of the road network through proper maintenance practices. |
|  | Outputs - New roads constructed Opening of 39.5km of District roads (Ntandi – Kahumbu road 8km, Butama – Irango – Kidedeya road 8km, Bumate – Karangusio road 6km, Bundingoma – Bundimirambi – Lamia road 6km, Njule – Tombwe road 3km, Mitunda – Bundikahondo – Bunyangule road 6km, Burambagira – Buyaya – Ngamba mosque 2.5km). - Rehabilitated existing roads (km of road, resurfacing, and pothole repairs). - Routine and periodic maintenance Rehabilitation of Kiryambuzi road section along Bundikayanja – Kisendera – Butwaka road. Manual routine maintenance of 60km of the road network, - Construction of six arch bridges across the road network - Local contractors and District staff trained in road construction and maintenance. - Improved road safety features (signage, pedestrian crossings). |
| Project inputs/activities/interventions | Inputs - Financial Resources: UGX 20 billion from government and donors - Human Resources: Project managers, engineers, contractors, labor force, trainers, and M&E staff. - Equipment and Machinery: Excavators, graders, trucks, rollers, pavers, and related construction vehicles. - Materials and Supplies:, gravel, concrete, drainage pipes, signage, and road safety materials. - Technology and Tools: Surveying instruments, project management software, M&E systems, and GIS tools. - Legal Resources: Permits, environmental assessments, and contracts. - Community Resources: Public consultations, awareness campaigns, and community support. - Environmental and Social Safeguard Resources: Mitigation measures, resettlement plans, and social monitoring. - Monitoring & Evaluation Resources: Data collection tools, baseline studies, and M&E frameworks. |
|  | Activities Road Construction (New Roads): - Feasibility studies and survey of new road routes. - Design and planning of new road sections. - Clearing and earthworks for new roads. - Installation of proper drainage systems. - Asphalt or gravel surfacing as per design specifications. - Road signage, marking, and installation of road safety features. Road Rehabilitation: - Detailed assessment of existing roads to identify critical areas of improvement. - Pothole repairs and resurfacing. - Reconstruction of weak road sections and embankments. - Drainage improvements to prevent road erosion. Routine and Periodic Maintenance: - Regular monitoring of road conditions. - Grading and patching of gravel roads. - Removal of debris, sediment, and obstructions from drainage systems. Capacity Building and Training: - Train local contractors in road construction and maintenance techniques. - Capacity building for District technical staff in road project management. |
| STRATEGIC OPTIONS |  |
| Strategic options (indicate the existing asset, non-asset, and new asset solution) | Alternative means of solving the problem stating the advantage and disadvantages of each Construction of Arch bridges: This a resistant to flash flood that frequently wah away the bridges during flash floods Disadvantage Its is expensive to construct as compared to the budget received by the district Community-Based Road Maintenance Programs. Empower local community groups (LCs, youth, and women’s groups) to maintain roads using locally available tools and materials. Advantages: Promotes community ownership and sustainability. Cost-effective and employment-generating. Disadvantages: Limited technical capacity for major works. Quality may vary. |
|  | Alternative means of financing stating the advantages and disadvantages of each Public-Private Partnerships (PPPs). Collaborations between government and private entities to finance, build, and/or maintain infrastructure (e.g., build-operate-transfer, lease-operate models). Advantages Mobilizes private capital and expertise. Risk-sharing between public and private sector. Improved efficiency and innovation. Disadvantages: Legal and regulatory complexity. |
|  | Comparison of the alternatives, indicate methodologies used in the assessment |
|  | Selected approach, highlight reasons for the superiority of the proposed approach/project Blended Financing Model After comparing all financing alternatives using multi-criteria assessment (cost-efficiency, sustainability, risk, feasibility, and stakeholder acceptability), the blended financing model has been selected as the most suitable and superior approach. |
| Coordination with government agencies | Indicate the roles of other stakeholders respecting legal and policy mandates, embrace integrated planning, define the roles of each agency in project implementation #### Ministry of Works and Transport #### Provides technical guidelines and standards for road construction. - Offers technical support through district engineers and regional offices. - Monitors compliance with national transport policies. #### Uganda Road Fund #### - Provides funding for road maintenance and minor rehabilitation. - Requires timely reporting on physical and financial progress. - Ensures that road funds are used efficiently and transparently. |
| PROJECT ANNUALISED TARGETS (OUTPUTS) (000s) |  |
| Project annualized targets | Output; Year 0; Year 1; Year 2; Year 3; Year 4; Year 5. Manual routine maintenance of 60km of the road network.; 90,000; 99,000; 108,900; 119,790; 131,769. Mechanized routine maintenance of 150km of the road net work; 600,00; 660,000; 726,000; 798,600; 878,460. Installation of 100 lines culvert across the road network for drainage improvement.; 100,000; 110,000; 121,000; 133,100; 146,410. Opening of 39.5km of District roads (Ntandi – Kahumbu road 8km, Butama – Irango – Kidedeya road 8km, Bumate – Karangusio road 6km, Bundingoma – Bundimirambi – Lamia road 6km, Njule – Tombwe road 3km, Mitunda – Bundikahondo – Bunyangule road 6km, Burambagira – Buyaya – Ngamba mosque 2.5km).; 197,50; 217,250; 238,975; 262,872; 289,159. |
| ESTIMATED PROJECT COST AND FUNDING SOURCES (000s) |  |
| Project annualized cost | Output; Source; Cum. Exp. Up to 2025/26; Yr.1; Yr.2; Yr.3; Yr.4; Yr.5; Recurrent (%); Capital (%). Manual routine maintenance of 60km of the road network.; GOU; 549,459; 90,000; 99,000; 108,900; 119,790; 131,769; 100%. Donor. OSR. NGO. PS. Output2: Mechanized routine maintenance of 150km of the road net work; GOU; 3,663,060; 600,00; 660,000; 726,000; 798,600; 878,460; 100%. Donor. OSR. NGO. PS. Output3: Installation of 100 lines culvert across the road network for drainage improvement.; GOU; 610,510,; 100,000; 110,000; 121,000; 133,100; 146,410; 100%. Donor. OSR. NGO. PS. GOU; 1,205,757; 197,50; 217,250; 238,975; 262,872; 289,159; 100%. Output4: Opening of 39.5km of District roads (Ntandi – Kahumbu road 8km, Butama – Irango – Kidedeya road 8km, Bumate – Karangusio road 6km, Bundingoma – Bundimirambi – Lamia road 6km, Njule – Tombwe road 3km, Mitunda – Bundikahondo – Bunyangule road 6km, Burambagira – Buyaya – Ngamba mosque 2.5km).; Donor. OSR. NGO. PS. Total; 8,421,985; 1,379,500,; 1,517,450,; 1,669,195,; 1,836,114; 2,019,725. |
| PLANNED CUMULATIVE IMPLEMENATATION PERCENTAGE PROGRESSION |  |
| Percentage progress | Output; Year 0; Year 1; Year 2; Year 3; Year 4; Year 5. Overall project progress (%). Manual routine maintenance of 60km of the road network; 25%; 25%; 25%; 25%; 25%. Mechanized routine maintenance of 150km of the road net work; 20%; 40%; 60%; 80%; 100%. Installation of 100 lines culvert across the road network for drainage improvement.; 50%; 50%. Opening of 39.5km of District roads (Ntandi – Kahumbu road 8km, Butama – Irango – Kidedeya road 8km, Bumate – Karangusio road 6km, Bundingoma – Bundimirambi – Lamia road 6km, Njule – Tombwe road 3km, Mitunda – Bundikahondo – Bunyangule road 6km, Burambagira – Buyaya – Ngamba mosque 2.5km).; 50%; 100%. |
| RESULTS MATRIX |  |
| Results matrix | Objective Hierarchy and Description; Indicators; Means of Verification; Baseline; Target; Assumptions. Impact; Improved access to socio-economic services and increased local economic activity in Bundibugyo District; National Service Delivery Survey, UNRA/URF reports, District transport data; 45% of roads are in poor condition; 80% of roads in fair to good condition by end of project; Continued government support and stable macroeconomic environment. Enhanced District road network and reduced travel time and transport costs; Project reports, traffic surveys, community feedback; Avg. travel time: 35 mins per 10 km; Avg. travel time: 20 mins per 10 km; Contractor performance, timely release of funds. Outputs; - Roads rtsconstd; Monthly progress reports, engineer site records, payroll, photos, M&E reports; 0 km constructed 10 km poorly maintained Weak drainage Low employment; 13 km constructed 30 km maintained 10 km of drainage improved 100+ local jobs created; Weather conditions, land acquisition delays, quality of contractors. activities; Conduct technical studies & designs Procure contractors Supervise works Train District staff; All activities completed on schedule; Procurement records, supervision reports, training attendance lists; Efficient procurement; no legal disputes; adequate staffing. |

| STRUCTURE OF THE NDPIII PIP |  |
| --- | --- |
| PROJECT SUMMARY |  |
| Project Title | Rehabilitation, Improvement and construction of Health facilities |
| NDP Program Description | Human Capital Development |
| Implementing Agency/Department | Bundibugyo District Council |
| Location | All health facilities in the district |
| Estimated Project Cost | 18,000,000,000 |
| Current stage of project implementation at commencement of LGDP | The condition of all health facilities is not good. Bundibugyo Hospital was constructed in 1969 while other health facilities lack some of the essential equipment |
| Funding Secured | 3,000,000 |
| Total funding gap | 15,000,000,000 |
| Project Duration/Life span (Financial Years) | 2026 |
|  | 2030 |
| Officer Responsible | District Health Officer |
| PROJECT INTRODUCTION |  |
| Problem Statement | Problem to be addressed Bundibugyo District faces significant challenges in the delivery of quality healthcare due to: - Inadequate infrastructure in key health facilities such as Bundibugyo district referral hospital and and Nyahuka and Kikyo Health Centre IVs based on their capacity - Limited maternity, surgical and outpatient capacity - Inadequate medical equipment - Staffing gaps and poor staff accommodation - Poor sanitation and unreliable water and electricity supply in some facilities This project aims to address these critical service delivery gaps, enhance maternal and child health, strengthen primary healthcare delivery, and reduce referral burdens. |
|  | Causes of the problem The challenges facing road infrastructure in Bundibugyo District stem from a combination of technical, financial, institutional, environmental, and demographic factors. These root causes contribute to the ongoing deterioration of roads and the lack of sufficient coverage across the Districtity. These problems arise due to Inadequate Funding for Road Infrastructure both central government funding and Locally raised funding, Poor Planning and Urban Expansion, Weak Institutional Capacity, Lack of Routine and Preventive Maintenance and Poor Drainage and Erosion Control. |
| Situation Analysis | Health facilities in Bundibugyo district, including the main Bundibugyo General Hospital, suffer from severe underfunding, dilapidated infrastructure, outdated/broken equipment, overcrowding (often beyond 3x capacity), and critical staff shortages, leading to poor service, especially for border-crossing patients, though some capacity-building projects by partners like Enabel have shown positive results in planning and staff skills. Local leaders and reports highlight urgent needs for renovation, equipment, more staff, and better resource allocation to meet regional demands and improve maternal/general care. |
|  | Ongoing interventions (include figures to support the achievements of outputs and budget allocations) Enabel have shown positive results in planning and staff skills. Local leaders and reports highlight urgent needs for renovation, equipment, more staff, and better resource allocation to meet regional demands and improve maternal/general care. |
|  | Challenges The primary health facility, Bundibugyo Hospital, is severely strained and operating beyond its capacity. - Dilapidated Buildings and Overcrowding: The hospital structures, built in the 1960s, are deteriorating and designed for a much smaller population, leading to severe overcrowding in wards. - Outdated/Broken Equipment: Essential medical equipment, such as X-ray and ultrasound machines, are often broken down or absent, forcing patients to travel long distances (e.g., to Fort Portal) for basic diagnostic services. Lack of Facilities: There is a shortage of essential infrastructure like adequate isolation facilities for infectious disease outbreaks (such as measles or Ebola), functional triage systems, and even basic staff accommodation, which contributes to poor working conditions |
|  | Crosscutting aspects Low uptake of critical services: There is a significant challenge in encouraging community members to use available services like immunization and facility-based deliveries, often due to fear, misinformation (e.g., during the COVID-19 pandemic), and cultural practices. Poverty and income levels: Household income poverty affects the ability of residents to access health services and other necessities like education, even when facilities are available. Community relations: Unfriendly interpersonal relations between health workers and patients have been a concern, impacting the perceived quality of care and potentially discouraging people from seeking help. Gender-related challenges: Socio-cultural attitudes can create specific challenges, such as those affecting girls' education, which can have long-term impacts on health outcomes. . |
| Relevance of the project idea | Alignment to NDP, SDPs and Agency plans The Health Facilities Service Improvement and Infrastructure Development Project in Bundibugyo District is well aligned with key national, sectoral, and local development frameworks: The project contributes to National Development Plan IV (NDP IV) through supporting the Human Capital Development programme, Contributes to Universal Health Coverage (UHC) and Enhanced access to quality healthcare, clean water, and sanitation in public health facilities. Sustainable Development Goals (SDGs). The project contributes to SDG 3 Good Health & Well-being, SDG 6 Clean Water & Sanitation, SDG 5 Gender Equality and SDG 9 & 11 Infrastructure and Sustainable Communities Uganda Vision 2040. Contributes to the national goal of a healthy and productive population by strengthening public healthcare infrastructure. |
| Stakeholders | Direct beneficiaries Residents of Bundibugyo District |
|  | Indirect beneficiaries Health workers Bundibugyo District Council |
|  | Likely project affected persons - Landowners - Tenants/Occupants - Health workers - Health Facility Clients / Community Members |
| Project objectives/outcomes/outputs | Objectives - Upgrade and rehabilitate infrastructure at Bundibugyo Hospital and all health facilities in the district - Improve water, sanitation, and hygiene (WASH) systems in targeted health facilities. - Equip health facilities with essential medical and surgical equipment. - Construct/rehabilitate staff houses to improve health worker retention. - Enhance service delivery capacity through recruitment, training, and supervision. |
|  | Outcomes - Increased access to quality healthcare - Functional maternity and surgical services - Increased availability of essential medical equipment - Improved staff productivity and motivation - Enhanced emergency response capacity - Strengthened Health Unit Management Committees (HUMCs) |
|  | Outputs - Maternity wards constructed or rehabilitated (at HC IV and two HC IIIs) - Staff houses constructed or renovated - Outpatient departments upgraded - Water supply systems installed/improved - Supply of solar lighting and/or backup generators for both health facilities - Medical waste management systems installed (placenta pits, incinerators, waste zones) - Health equipment (delivery beds, autoclaves, examination tables and other Theatre equipment etc.) procured - Health workers recruited/deployed - Community outreach programs conducted to promote facility-based care - Mortuary Constructed |
|  | Activities - Renovation of Bundibugyo Hospital, Nyahuka Health centre 1V - Construction of maternity ward - Construction of Health Centre III in Western Division - Expansion of OPD at Kikyo HC IV - Staff house construction - Install rainwater harvesting and piped water system - Construct VIP latrines, placenta pits, medical waste zones - Procurement of delivery beds, theater tables, oxygen cylinders, sterilizers - Recruitment of midwives, clinical officers, anesthetists - In-service training on emergency obstetric care - Monthly monitoring visits - Quarterly progress reviews - Technical audits |
| Project inputs/activities/interventions | Inputs - Financial Resources: UGX 7 billion from government and donors - Human Resources: Project managers, engineers, contractors, labor force, trainers, and M&E staff. - Equipment and Machinery: Excavators, graders, trucks, rollers, pavers, and related construction vehicles. - Materials and Supplies: Asphalt, gravel, concrete, drainage pipes, signage, and road safety materials. - Technology and Tools: Surveying instruments, project management software, M&E systems, and GIS tools. - Legal Resources: Permits, environmental assessments, and contracts. - Community Resources: Public consultations, awareness campaigns, and community support. - Environmental and Social Safeguard Resources: Mitigation measures, resettlement plans, and social monitoring. - Monitoring & Evaluation Resources: Data collection tools, baseline studies, and M&E frameworks. |
| STRATEGIC OPTIONS |  |
| Strategic options (indicate the existing asset, non-asset, and new asset solution) | Village Health Teams (VHTs): Utilizing and strengthening VHTs is a core strategy. Their roles include health education, mobilizing communities for services (e.g., immunization), treating common ailments, and bridging the gap between residents and formal health facilities. Incentives for Service Uptake: Simple incentives have proven highly effective. For instance, providing free soap to mothers who used health facilities for delivery or immunization dramatically increased facility attendance from 52% to 90% in one area. Radio Campaigns: Using local radio stations (like UBC FM in Bundibugyo) to run interactive talk shows and SMS polls is an effective way to raise awareness on health issues, collect citizen data, and promote hygiene and sanitation practices in local dialects. Health Promotion & Awareness: Continuous community awareness interventions are vital for promoting healthy behaviors, preventing diseases, and ensuring residents understand how to access services Expanding and Upgrading Facilities: Government and partners have invested in expanding access to health facilities, including upgrading existing Health Centre IIIs and proposing the elevation of the district hospital to a regional referral status to handle the influx of patients from neighboring Ntoroko District and DR Congo. Improved Water and Sanitation (WASH): Addressing insufficient access to clean water and sanitation is a primary strategy for preventing waterborne diseases and improving overall public health. Solar Electrification: Electrifying health centers improves their capacity to handle emergency cases, admit patients, and provide a full range of services. Reliable Medicine Supply Chain: Implementing controls and regular audits to ensure consistent availability of essential medicines and prevent stock-outs and theft is crucial for effective care delivery. |
|  | Alternative means of financing stating the advantages and disadvantages of each Public-Private Partnerships (PPPs). Collaborations between government and private entities to finance, build, and/or maintain infrastructure (e.g., build-operate-transfer, lease-operate models). Advantages Mobilizes private capital and expertise. Risk-sharing between public and private sector. Improved efficiency and innovation. Disadvantages: Legal and regulatory complexity. Risk of high user fees (e.g. tolls). Long negotiation periods and risk of renegotiation. |
|  | Comparison of the alternatives, indicate methodologies used in the assessment |
|  | Selected approach, highlight reasons for the superiority of the proposed approach/project Blended Financing Model After comparing all financing alternatives using multi-criteria assessment (cost-efficiency, sustainability, risk, feasibility, and stakeholder acceptability), the blended financing model has been selected as the most suitable and superior approach. |
| Coordination with government agencies | Indicate the roles of other stakeholders respecting legal and policy mandates, embrace integrated planning, define the roles of each agency in project implementation #### Ministry of Health #### The Ministry of Health (MoH) improves health services in Bundibugyo by providing leadership and stewardship through policy formulation, resource mobilization, setting standards, and supervising the implementation of national health programs at the district level. #### Development partners #### Various development partners have been involved in improving health services in the Bundibugyo district, including international organizations and NGOs that collaborate with the Ugandan government. . |
| PROJECT ANNUALISED TARGETS (OUTPUTS) (000s) |  |
| Project annualized targets | Total Cost for the Plan Period (UGX in Million). Outputs; Total (000); FY2025/26; FY 2026/27; FY 2027/28; FY 2028/29; FY 2029/30. Project 1:Completion of the Maternity ward Complex at Nyahuka HC IV ( 3 storey structure) plus equipping it; 3,200,000; 1,000,0000,000; 700,000,000; 700,000,000; 600,000,0000; 200,000,000. Project 2: Construction/establishment of a health centre III in Ntotoro sub-county(Completion-Phase II); 700,000; 700,000,000. Project 3: Construction of staff house at the newly established HC III in Ntotoro Sub-County; 190,000; 190,000,000. Project 4: Equipping of the newly established HC III; 250,000; 250,000,000. Project 5:Re-Construction of Kayenje HC II with upgrade to HC III( Busengerwa); 1,000,000; 250,000,000; 250,000,000; 500,000,000. Project 6: Renovation of Bundibugyo General Hospital; 3,000,000; 500,000,000; 500,000,000; 1,000,000,000; 1,000,000,000. Project 7:Construction and equipping of In-Patient Wards at Butama HC III, Kisubba HC III and Kakuka HC III; 2,500,000; 500,000,000; 500,000,000; 500,000,000; 500,000,000; 500,000,000. Project 8: Establishment of HC III in 5 sub-counties without any HC ( Ndugutu, Buganikere, Mabere, Mbatya, Kagugu, ); 6,000,000. Project 9: Upgrading of HC IIs to HC III( Kasulenge, Bundingoma, Busoru, Bulyambwa,; 2,400,000; 700,000,000; 700,000,000; 700,000,000; 700,000,000. Project 10: Construction of walkways ( with a shelter/shade )at all newly upgraded HC IIIs( Buhanda, Mirambi, Tombwe, Burondo, Bupomboli, Busunga, Bundimulagya; 80,000; 10,000,000; 20,000,000; 20,000,000; 20,000,000; 10,000,000. Project 11: Procurement of medical equipment; 150,000; 30,000,000; 30,000,000; 30,000,000; 30,000,000; 30,000,000. Project 12: Establishing laboratories at newly upgraded HC III( Buhanda, Kyondo, and Tombwe HC IIIs); 90,000; 15,000,000; 50,000,000; 25,000,000. Project 13: Construction of OPD at Bupomboli HC III; 300,000; 100,000,000; 100,000,000; 100,000,000. Project 14: Construction of a permanent Isolation unit at Bundibugyo General Hospital; 1,000,000. Project 15: Construction of incinerators and waste pits at 4 Health Centre IIIs; 120,000. Project 16: Construction of ANC and immunisation shelters at 5 newly upgraded HCs; 250,000; 50,000,000; 50,000,000; 50,000,000; 100,000,000. Project 17: Construction of and equipping mortuaries Bundibugyo Hospital, Nyahuka and Kikyo HC IVs; 400,000; 100,000,000; 100,000,000; 100,000,000; 100,000,000. |
| ESTIMATED PROJECT COST AND FUNDING SOURCES (000s) |  |
|  | Output; Source; Cum. Exp. Up to 2029/30; Yr.1; Yr.2; Yr.3; Yr.4; Yr.5; Recurrent (%); Capital (%). Output1 Completion of the Maternity ward Complex at Nyahuka HC IV ( 3 storey structure) plus equipping it; GOU; 3,200,000; 1,000,0000,000; 700,000,000; 700,000,000; 600,000,0000; 3,200,000; 100%. Donor. OSR. NGO. PS. Output 2: Construction/establishment of a health centre III in Ntotoro sub-county(Completion-Phase II); GOU; 700,000; 700,000,000. Donor. OSR. NGO. PS. Output3; GOU. Donor. OSR. NGO. PS. |
| PLANNED CUMULATIVE IMPLEMENATATION PERCENTAGE PROGRESSION |  |
| Percentage progress | Output; Year 0; Year 1; Year 2; Year 3; Year 4; Year 5. Overall project progress (%). |
| RESULTS MATRIX |  |
| Results matrix | Objective Hierarchy and Description; Indicators; Means of Verification; Baseline; Target; Assumptions. Impact. Outputs. activities. |

# Annex 3: Results and Reporting Framework

Programme: Agro-Industrialization

| Strategic Objectives and Interventions | Key Outputs | Output Indicator | Baseline FY2023/24 | Target FY29/30 |
| --- | --- | --- | --- | --- |
| Strategic Objective 1: Sustainably increase production and productivity in agriculture |  |  |  |  |
| Intervention 1: Increase uptake of fertilizers | Fertilizer access and application increased | Number of farmer groups linked to credit services | 5 | 15 |
|  | Fertilizers procured | Number of fertilizer dealers and premises registered | 2 | 7 |
| Intervention 2: Produce, multiply and distribute quality seed and inputs | Small-scale irrigation equipment distributed | Number of farmer groups supported with micro-irrigation equipment | 7 | 27 |
|  |  | Number of crop compliance certificates issued (agro-chemicals dealers, premises) | 2 | 7 |
|  | Quality seed production increased | Number of households trained in seed production | 0 | 100 |
|  | Improved livestock units established | Number of farmers trained in zero-grazing | 0 | 34 |
| Intervention 3: Strategically invest in the fisheries sub-sector and aquaculture development | 1.1.3.1: Aquaculture production promoted | Number of community fish ponds established | 150 | 300 |
|  |  | Number of community groups supported with starter inputs packages | 150 | 300 |
|  |  | Number of domestic feed processors supported to produce quality fish feed | 2 | 4 |
|  |  | Number of extension Staff trained | 40 | 55 |
|  |  | Number of farmer groups formed |  |  |
|  |  | Number of farmer groups supported | 2700 | 4500 |
|  |  | Number of fingerings acquired (thousands fingerlings) | 2700 | 4500 |
|  |  | Number of hatcheries certified | 200,000 | 450000 |
|  |  | Number of hatcheries certified | 1 | 2 |
| Intervention 3: Increase access to water for agricultural production | Solar-powered irrigation systems installed | Number of micro-irrigation systems established | 12 | 15 |
| Intervention 4: Support research, genetics and technology uptake | Livestock mini-laboratory constructed | No. of laboratories constructed | 0 | 1 |
|  | Research–extension–farmer linkages strengthened | No. of MSIPs established | 12 | 21 |
|  | Soil analysis enhanced | Number of parish-level demo technology centers | 0 | 2 |
| Strategic Intervention 4: Support to large scale commercial farming entities | Output 1.1.5.1: Production capacity of large scale commercial farmers expanded | Number of solar powered irrigation demonstrations established | 27 | 27 |
|  |  | Number of tractors with assorted implements acquired | 2 | 5 |
|  |  | No. of medium & large-scale commercial farms supported | 4 | 10 |
|  |  | Number of large land owners supported to plant coffee | 2 | 5 |
|  |  | Number of large scale commercial farmers supported | 2 | 5 |
| Strategic Intervention 5: Increase access to and use of water for agricultural production | Output 1.1.2.1: Facilities, equipment and machinery managed and maintained | Number of government farms on which water infrastructure is renovated | 1 | 1 |
|  | Output 1.1.2.2: On-farm water for production infrastructure established | No. of solar powered small scale water for production systems for demonstration established | 27 | 100 |
|  |  | No. of valley dams constructed |  |  |
|  |  | Number of communal dams constructed | 0 | 2 |
|  |  | Number of Individual valley tanks constructed | 0 | 6 |
|  |  | Number of micro-irrigation systems established | 40 | 100 |
|  |  | Number of solar powered small-scale irrigation systems constructed |  |  |
| Strategic Intervention 8: Strengthen farmer organizations and cooperatives ecosystems | Output 1.1.4.1: Functionality and sustainability of farmer groups, MSMEs and cooperatives improved | No. of farmer groups, MSME, Cooperatives trained | 15 | 24 |
|  |  | Number of farmer groups registered | 2700 | 4500 |
|  |  | No. of farmer groups, MSME, Cooperatives supported with inputs | 2700 | 4500 |
| Strategic Intervention 9: Strengthen pest, vector, disease management and control | Output 1.1.3.3: Antimicrobial resistance and disease surveillance enhanced | Number of surveillance and outbreak investigations undertaken | 100 | 100 |
|  |  | Quarterly antimicrobial surveys undertaken | 4 | 4 |
|  |  | Laboratory turnaround time for diagnostic samples submitted (hrs) | 4 | 4 |
| Strategic Objective 1: Strategic Objective 1: Promote Domestic and Inbound Tourism |  |  |  |  |
| Strategic Intervention 3.1: 1. Conserve Uganda’s natural and cultural and cultural sites: | Cultural sites - museums maintained and developed | Number of cultural sites maintained | 0 | 10 |
| Strategic Intervention Conduct awareness and sensitization campaigns amongst communities in and around the protected areas | Communities around the park and protected areas sensitized | Number of sensitization meetings conducted | 4 | 20 |
| Intervention 1.1 Undertake district wide awareness and campaigns on cultural heritage conservation and importance of cultural heritage | Cultural museum developed and equipped | Number of cultural museums developed and equipped. | 1 | 10 |
|  |  | Number of community sensitization conducted | 4 | 20 |
| 1.4 Develop plans and undertake feasibility studies for water-based tourism falls- Ngitte and Nyahuka, and Sempaya hot springs. | Output 5: Cultural tourism circuits developed. | Number of water-based tourism sites developed (cumulative) | 1 | 2 |

Programme: Natural Resources, Environment, Climate Change, Land and Water Management

| Strategic Objectives and Interventions | Key Outputs | Output Indicator | Baseline FY2023/24 | Target FY29/30 |
| --- | --- | --- | --- | --- |
| Strategic Objective 1: Protect, restore and add value to forests and wetlands |  |  |  |  |
| Interventions |  |  |  |  |
| 3.1 Increased Forest and wetland cover for socio-economic and ecological benefits | Output 1.1.1: Forest reserves restored and protected | Output Indicator 1: Area (ha) of forest reserves protected from illegal activities | 20 | 340 |
|  |  | Output Indicator 2: Area (ha) of degraded forests restored | 2 | 5 |
|  | Output 1.1.2: Seed production increased | Output Indicator 1: Number of quality tree seed, tree seedlings supplied | 500.000 | 1,400,000 |
| 3.2 Protect and increase the wetland cover | Output 1.2.1: Gender responsive wetlands management plans and District/city wetland action plans developed and implemented. | Output Indicator 1: Area (ha) of wetlands under management plans | 4 | 10 |
|  | Output 1.2.2: Wetland alternative livelihood options promoted and supported | Output Indicator 1: Number of households supported with alternative livelihood options | 200 | 300 |
|  | Output 1.2.3: Wetland boundaries surveyed and demarcated | Output Indicator1 Length (Km) of wetlands boundaries demarcated. | 20 | 50 |
|  | Output 1.2.4: Degraded wetlands restored | Output Indicator 1 Area (Ha) of wetlands restored | 4 | 15 |
|  | Output 1.2.5: Wetland resources knowledge and information products produced. | Output Indicator1 Number of wetland resources knowledge and information products | 30 | 70 |
|  | Output 1.2.6: Wetlands mapped across the country and the National wetland Inventory updated | Output Indicator 1 Number of mapping interventions | 2 | 10 |
|  |  | Output Indicator2 Number of district Inventory reports | 0 | 1 |
| Strategic Objective 2: To ensure a clean, healthy and productive environment |  |  |  |  |
| The Interventions |  |  |  |  |
| 4.1 Strengthen regulation and enforcement against environmental pollution and degradation | Output 2.1.1: I Regulation and enforcement against environmental degradation strengthened | Output Indicator 1 Number of environmental and social impact assessments reviewed | 30 | 30 |
|  |  | Output Indicator 2: Number environmental compliance monitoring and inspections carried out | 10 | 8 |
|  | Output 2.1.2: Fragile and threatened ecosystems restored and protected (Rangelands, hilly and mountainous areas, river banks and lakeshores) | Output Indicator 1: Area (Ha) of River Banks/Lakeshores restored protected | 30 | 50 |
| Strategic Objective 6: To strengthen policy, legal, regulatory and coordination frameworks |  |  |  |  |
| The Interventions |  |  |  |  |
| 6.1 Integrate crosscutting issues in the programme | Output 3.1.1: Crosscutting issues mainstreamed in the programme | Output Indicator 1: Number of Gender mainstreaming interventions implemented. | 0 | 1 |
|  |  | Output Indicator 2: Number of HIV/AIDS mainstreaming interventions undertaken. | 0 | 50 |
|  |  | Output Indicator 3: Number of projects supported with Social and Environmental safeguards | 10 | 30 |

Programme: Private Sector Development

| Strategic Objectives and Interventions | Key Outputs | Output Indicator | Baseline FY2023/24 | Target FY29/30 |
| --- | --- | --- | --- | --- |
| Strategic Objective 1: Sustainably Lower the Cost of Financing |  |  |  |  |
| Intervention 1.1.1.1: Increase Access and Affordability of Financial Services | Access to convenient financial services increased | Number of digital financial service users | 10 million | 18 million |
|  | Women & PWDs benefiting from financial services | Number of women-led enterprises supported | 150 | 300 |
| Intervention 1.1.2.1: Increase Access to Short-Term Finance | Emyooga SACCOs and client institutions financed | Value of financing to women, youth & PWDs (UGX) | 180M | 120M |
|  |  | Number of Emyooga SACCOs financed | 36 | 80 |
| Intervention 1.1.2.2: Implement Financial Literacy Programs | Public awareness in financial services enhanced | % of financially included adults | 81% | 86% |
|  | Green financing promoted | Value of green financing (UGX Bn) | 0 | 150 |
| Strategic Objective 3: Support Capacity Development for Private Sector Institutions & MSMEs |  |  |  |  |
| Intervention 3.1.1.1: Roll Out Business Development Services (BDS) | Compliance with corporate governance improved | Number of annual returns filed | 100 | 100 |
|  | National BDS Framework operational | Number of MSMEs trained | 75 | 100 |
|  |  | % increase in MSMEs accessing bank financing after BDS | 5% | 5% |
| Intervention 3.1.3.1: Promote Business Registration & Formalization | Uptake of business registration enhanced | Number of new business registrations (companies + business names) | 15 | 70 |

Programme: Human Capital Development

| Strategic Objectives and Interventions | Key Outputs | Output Indicator | Baseline FY2023/24 | Target FY29/30 |
| --- | --- | --- | --- | --- |
| Strategic Objective 1: Improve the foundation of human capital development |  |  |  |  |
| Intervention 1: Institutionalize Pre-primary teacher training at public teacher training institutions | Institutionalize pre-primary teacher training at public teacher training institutions | Number of pre-primary teachers trained in-service through CPDs | 178 | 986 |
| Strategic Intervention 2: Improve Physical and Cognitive development of children below 8 years | Improve physical and cognitive development of children below 8 years | Number of caregivers/parents trained on effective parenting | 0 | 300 |
|  |  | Number of LLGs implementing strategies to prevent/respond to abuse | 0 | 27 |
|  | Compliance to Early Childhood Development services strengthened | Proportion of ECD centres compliant to national standards | 0 | 0.85 |
| Strategic Intervention 3:Promote optimal Maternal, Infant, Young child, Adolescent and Elderly Nutrition Practices | Promote optimal maternal, infant, young child nutrition practices | % of health facilities designated as mother-baby friendly | 100% | 100% |
| Strategic Intervention 4: Increase access to immunization against childhood diseases | Increase access to immunization | % of under-5 children dewormed in last 6 months | 311% | 31% |
| Strategic Intervention 5: Strengthen the family Unit to reduce domestic violence, child deprivation, abuse and child labor | Strengthen the family unit | No. of families accessing counselling services | 0 | 100 |
| Strategic Intervention 6: Equip all lagging schools to meet BRMS | Equip all lagging schools | Number of classroom furniture (desks/tables/chairs/stools) provided | 100 | 100 |
|  |  | Number of schools constructed in each of the parishes | 78 | 130 |
|  |  | Number of existing public primary schools rehabilitated. | 35 | 107 |
|  |  | Number of existing public primary schools renovated | 56 | 107 |
|  | Institutionalize pre-primary teacher training at public teacher training institutions | Number of pre-primary teachers trained in-service through CPDs | 26 | 26 |
| Strategic Objective 2: Produce appropriate knowledgeable, skilled and ethical labor force |  |  |  |  |
| Intervention 1: Increase access to TVET training in skills scarce TVET programmes to reverse the currently inverted skills triangle | Increase access to TVET training in scarce skills programmes | Number of TVET trainers recruited | 76 | 350 |
|  | Competence-based curricula developed and implemented | Number of instructors retooled on revised curriculum | 19 | 30 |
| Strategic Objective 3: Improve population health, safety and management |  |  |  |  |
| Strategic Intervention 1: Increase community ownership, access and utilization of health promotion, environmental health and community health services | Increase community ownership, access, and utilization of health services | % of sick children managed by VHTs who recovered | 65% | 80% |
|  | Reduce burden of communicable diseases | % of population sleeping under ITN | 30% | 80% |
|  | Improve maternal, neonatal, child & adolescent health services | % of deliveries in health facilities | 89.4% | 100% |
|  | Improve curative, palliative, rehabilitative & geriatric care | Malaria case fatality rate per 10,000 | 15% | 10% |
| Strategic Objective 4: Promote decent work and productive employment |  |  |  |  |
| Strategic Intervention 1: Strengthen compliance with labour standards and rights | Strengthen compliance with labour standards | Number of workplaces with OSH systems in place | 4 | 100 |
| Strategic Intervention 2: Improving Occupational Safety and Health (OSH) management | Employment opportunities, safety & compliance increased | Number of jobs created in formal & informal sector | 2000 | 3000 |
| Strategic Objective 5: Reduce vulnerability, gender inequality & inequity along lifecycle |  |  |  |  |
| Strategic Intervention 1 : Expand scope and coverage of livelihood enhancement and economic empowerment programmes for Youth, Women, Older Persons, PWDs and ethnic minorities | Youth, Women, Older Persons, PWDs, indigenous ethnic minorities and refugee’s livelihood and empowerment programmes implemented | Number of youths benefitting from livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 1200 | 10,000 |
|  |  | Number of women in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 1,800 | 4,000 |
|  |  | Number of Older Persons Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 1324 | 1,500 |
|  |  | Number of PWDs Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 78 | 100 |
|  | Provide holistic social care & support services | Number of children accessing social care/support services | 2,303 | 1,500 |
|  | Social protection systems strengthened | Functional social protection systems in place | 3 | 10 |

Programme: Public Sector Transformation

| Strategic Objectives and Interventions | Key Outputs | Output Indicator | Baseline FY2023/24 | Target FY29/30 |
| --- | --- | --- | --- | --- |
| Strategic Objective 1: Strengthen accountability for results across government |  |  |  |  |
| Intervention 1:Strengthen efficiency of D/CSCs | D/CSCs fully constituted and functional | Number of D/CSCs fully constituted | 1 | 1 |
|  | Disciplinary cases timely concluded with complete submissions | Number of disciplinary cases concluded | 30 | 20 |
| Strategic Objective 2: Strengthen human resource management for improved service delivery |  |  |  |  |
| Intervention 1: Strengthen recruitment in MDAs and LGs | Approved Recruitment Plans of MDAs and LGs implemented | Number of vacancies declared within the financial year filled | 89 | 100 |
| Intervention 2: Improved efficiency, effectiveness in Payroll management | Access to payroll regulated | % of staff accessing payroll within 30 days after assumption of duty | 80% | 100% |
|  |  | % increase of pensioners accessing payroll within 30 days after retirement | 92% | 100% |
|  | Implementation of the Reports of the Auditor General on active and pension payroll undertaken | % of recommendations of Auditor General implemented | 90 | 100 |
| Intervention 3: Reform the pension schemes and systems | Public Service Pension Fund operationalized | Operationalized (1 = Yes) | 0 | 1 |
| Strategic Objective 3: Deepen Decentralization and Citizen Participation in Local Development |  |  |  |  |
| Intervention 1: Build LG decentralization and self-reliance capacity | Local revenue allocated to community development | % of Local revenue invested in community services | 3% | 10% |
| Strategic Objective 1: Strengthen institutional coordination and enforcement of policies, laws and regulatory frameworks |  |  |  |  |
| Intervention 1: Enhance Institutional Coordination and Administrative Efficiency | Staff salaries and related costs paid | % of staff whose salaries processed by 28th of every month | 100% | 100% |
|  | Planning and budgeting undertaken | No. of quarterly Physical Progress reports prepared | 4 | 4 |

Programme: Regional Development

| Strategic Objectives and Interventions | Key Outputs | Output Indicator | Baseline FY2023/24 | Target FY29/30 |
| --- | --- | --- | --- | --- |
| Strategic Objective 1: Enhance and Sustain Local Economic Development |  |  |  |  |
| Intervention 1: Implement the National LED Strategy | LED Strategies developed | % of Regional LED strategies developed | 0 | 1 |
|  |  | % of LG LED strategies developed | 0 | 1 |
|  |  | % of LGs trained on Local Business Assessment | 0 | 1 |
| Intervention 2: Develop lower level PDPs to operationalize the National Physical Development Plan | Integrated District and Local Physical Development Plans implemented | Number of Town councils with approved integrated Physical Development Plans | 0 | 7 |
|  |  | Number of Rural Growth centers with approved integrated Physical Development Plans | 0 | 1 |
| Intervention 3: Integrate Physical Planning with LED | Integrated Regional, District, and Local Physical Development Plans implemented | Number of Local SMEs linked to Regional and Global markets | 0 | 3 |
| Intervention 4: Link Enterprises to Local, Regional and International markets | Increased access to markets | Number of KMs of Community Access Roads constructed/rehabilitated | 58 | 100 |
|  |  | Number of Agro-processing facilities constructed | 3 | 5 |
| Intervention 5: Strengthen implementation of PDM Pillars & EMYOOGA | PDM implementation coordination strengthened | % of PDM households accessing PRF | 68.35% | 95% |
|  | Governance and management structures strengthened | Percentage of households of subsistence accessing credit facilities (Thousands) | 34.3 | 60% |
| Strategic Objective 2: Enhance Local Revenue |  |  |  |  |
| Intervention 1: Implementation of Local Government Revenue Mobilization Strategy | Local revenue mobilized and generated | Amount of Local Revenue collected (000) | 700,000 | 2,000,000 |
|  |  | Number of new Local Revenue taxpayers registered | 850 | 1000 |
| Intervention 2: Strengthen legal frameworks for Local Government funding | Improved utilization of discretionary funds to LGs | Number of Advocacy engagements held for discretionary funding | 0 | 4 |
|  |  | Number of LG work plans adhering to DDEG guidelines | 4 | 4 |
| Strategic Objective 3: Strengthen affirmative action in lagging regions and refugee hosting communities |  |  |  |  |
| Intervention 1: Implement Social Economic Programs to address sub regional needs | Households benefiting from government programs/projects in affirmative action areas | % of households benefitting from government programs/projects | 60 | 85 |
|  | Community Social and Economic Infrastructure Projects implemented | % of safe and clean water points constructed | 64% | 90% |

Programme: Development Plan Implementation

| Strategic Objectives and Interventions | Key Outputs | Output Indicator | Baseline FY2023/24 | Target FY29/30 |
| --- | --- | --- | --- | --- |
| Strategic Objective 1: Strengthen Capacity for Evidence-Based Development Planning across Government |  |  |  |  |
| Intervention 1: Build capacity in development planning and project formulation at all levels of government | Gender and equity responsive plans | Proportion of LGs with gender and equity responsive plans | 50% | 100% |
|  | Aligned Development Plans to NDP | Proportion of LGs plans aligned to NDP | 65% | 100% |
|  | Updated Administrative data and Statistics | Proportion of LGs with updated NDP Administrative data | 80% | 90% |
|  | Quality data and statistics produced from nontraditional sources | Number of indicators compiled from non-traditional data sources | 0 | 12 |
| Intervention 2: Plan for National Statistical Development (PNSDIV) | Functional statistical units in MDALGs | Proportion of functional statistical units in MDALGs | 75% | 95% |
| Strategic Objective 2: Enhance Resource Mobilization to Finance the National Development Plan |  |  |  |  |
| Intervention 1: Strengthen Local Government Revenue Mobilization | Local Government own source revenue growth | Percentage increase in local revenues year-over-year | 3% | 7% |
|  | Percentage increase in own source revenue | Percentage increase in own source revenue | 3% | 7% |
| Strategic Objective 3: Strengthen Budgeting and Accountability Systems |  |  |  |  |
| Intervention 1: Strengthen alignment of MDALGs budgets to NDP priorities during budget preparation and execution | Credible budget | Percentage of budget released against originally approved budget | 106% | 110% |
| Intervention 2: Strengthen budget execution across government | Efficiency and compliance in Public Procurement | Proportion of contracts completed on time | 68% | 100% |
|  | Budget support services | Percentage of funds absorbed against funds released | 90% | 100% |
| Strategic Objective 4: Strengthen Oversight, Coordination and M&E across Government |  |  |  |  |
| Intervention 1: Strengthen the oversight function across government | High quality, specialized and impact-driven audits | Level of implementation of audit recommendations | 95% | 100% |
|  | High quality, specialized and impact-driven audits | Level of implementation of audit recommendations | 95% | 100% |
| Intervention 2: Strengthen the M&E function across government | Mid Term Review of NDPIV, Vision 2040 and End-term evaluations conducted | No. of Mid Term Review reports of NDPIV in place | 0 | 1 |